## FS Plan Summary
0 | 0 | 0 | 0 | 0 | 0 | Estimated Duration | Target Start Date | Target End Date | Staffing Considerations / Lead Responsibility | MR | LS | AT | RD | BH | RL | AM (HR) | HB | AD | DJ (ST) | Systems | Web | Pgmr 1 | Pgmr 2 | Comments
A | 0 | 0 | PROJECT MANAGEMENT |  |  | 0% | 2002-11-15 | 2002-05-16 | PMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 0 | PLAN THE UPGRADE |  |  | 2 weeks - 2 months | 2002-11-15 | 2002-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | INSTALL THE SOFTWARE |  |  | 7-10 days | 0 | 2002-12-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | PREPARE DATABASE |  |  | 0 | 2002-01-06 | 2002-01-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | APPLY PEOPLETOOLS CHANGES |  |  | 1-2 days | 2002-01-21 | 2002-01-22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | RUN AND REVIEW COMPARE REPORTS |  |  | 6-12 Days | 2002-01-23 | 2002-01-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 0 | 0 | APPLY APPLICATION CHANGES |  |  | 1-2 Weeks | 2002-01-27 | 2002-02-10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | COMPLETE DATABASE CHANGES |  |  | 0 | 2002-02-10 | 2002-02-24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | USER TEST CYCLE 1 (7-30) |  |  | 2 weeks | 2002-02-24 | 2002-03-10 | Users | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | CREATE CYCLE 2 |  |  | 1 week | 2002-03-10 | 2002-03-17 | UT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | USER TEST CYCLE 2 |  |  | 2 weeks | 2002-03-17 | 2002-03-31 | Users | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | CREATE CYCLE 3 |  |  | 1 week | 2002-03-31 | 2002-04-07 | UT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | USER TEST CYCLE 3 |  |  | 4 weeks | 2002-04-07 | 2002-05-05 | Users | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 0 | 0 | PERFORM THE MOVE TO PRODUCTION (8-3) |  |  | weekend | 2002-05-02 | 2002-05-05 | UT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 0 | 0 | CONDUCT POST GO LIVE REVIEW |  |  | 0 | 2002-05-12 | 2002-05-16 | PMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## FS Plan Detail
[6 empty] | Estimated Duration | Target Start Date | Target End Date | Staffing Considerations / Lead Responsibility | MR | LS | AT | RD | BH | RL | AM (HR) | HB | AD | DJ (ST) | Systems | Web | Pgmr 1 | Pgmr 2 | Comments
A |  |  | PROJECT MANAGEMENT | [5 empty] | PMT
| 1 |  |  | Develop Project Plan |  |  |  |  | PMT
|  | 1 |  |  | Prepare plan
|  | 2 |  |  | review and approve plan |  |  | 2002-12-02
| 2 |  |  | Create Project Organization |  |  |  | 2002-12-02 | PMT
|  | 1 |  |  | Form ACS project team
| 3 |  |  | Present Status |  |  |  |  | PMT
|  | 1 |  |  | Consuct Steering Committee Meetings
|  | 2 |  |  | Conduct Project Management Meetings
|  | 3 |  |  | Conduct Project Team
| 4 |  |  | Conduct Project Kickoff |  |  |  |  | PMT
|  | 1 |  |  | Prepare for kickoff | [18 empty] | Week or January 6
|  | 2 |  |  | Conduct project kickoff
| 5 |  |  | Establish Space and Equipment |  |  |  | 2002-12-02 | MR
| 6 |  |  | Train Project Team |  |  |  | 2002-12-31 | PMT
|  | 3 |  |  | Schedule, complete PeopleSoft team training
| 7 |  |  | Issue Management |  |  |  |  | PMT
| 8 |  |  | Control Project |  |  |  |  | PMT
1 |  |  | PLAN THE UPGRADE |  |  | 2 weeks - 2 months | 2002-11-15 | 2002-12-31
| 1 |  |  | Learn about the new release |  |  |  |  | PMT | X | X | X | X | X | X | X | X | X | X
| 2 |  |  | Conduct business fit gap analysis |  |  |  |  | PMT | X | X | X |  | X | X |  | X | X | X
| 3 |  |  | Review technical requirements |  |  |  |  | UT |  | X | X | X
| 4 |  |  | Assess business requirements |  |  |  |  | PMT | X | X | X
| 5 |  |  | Assemble the upgrade project team |  |  |  |  | Already Above
| 6 |  |  | Define the upgrade project plan |  |  |  |  | PMT | X | X | X
| 7 |  |  | Define testing strategy |  |  |  |  | PMT | X | X | X
| 8 |  |  | Train upgrade team members |  |  |  |  | PMT | X | X | X
| 9 |  |  | Download the upgrade information |  |  |  |  | Complete |  | X | X | X
| 10 |  |  | Learn about the upgrade assistant |  |  |  |  | UT |  | X | X | X
| 11 |  |  | Understand the upgrade process |  | 2-4 days |  |  | UT | X | X | X | X | X | X | X | X | X | X | X | X | X | X
2 |  |  | INSTALL THE SOFTWARE |  |  | 7-10 days |  | 2002-12-31
| 1 |  |  | Install the new release |  |  |  | 2002-12-06 | Systems | [10 empty] | X
| 2 |  |  | Apply updates required for upgrade |  |  |  |  | RR/RD |  |  |  | X
| 3 |  |  | Install the upgrade assistant |  |  |  | 2002-12-16 | Steve Adams | [10 empty] | X
| 4 |  |  | Create an upgrade assistant job |  |  |  |  | UT |  | X | X | X
| 5 |  |  | Review upgrade step properties |  |  |  |  | UT |  | X | X | X
3 |  |  | PREPARE DATABASE |  |  |  | 2002-01-06 | 2002-01-20
| 1 |  |  | Review upgrade notes and tips |  |  | 2002-12-16 | 2002-12-31 | UT |  | X | X | X
| 2 |  |  | Copy production database |  |  |  | 2002-12-06 | Systems | [10 empty] | X |  |  |  | or 12-13 FS 7.02 depends on Steve Allen
| 3 |  |  | Apply project UPGOPT |  |  |  |  | UT | [10 empty] | X
| 4 |  |  | Update statistics |  |  |  |  | UT | [10 empty] | X
| 5 |  |  | Run initial audit reports |  |  |  |  | UT |  | X | X | X
| 6 |  |  | Perform general options setup |  |  |  |  | UT |  | X | X | X
| 7 |  |  | Review COUNTRY TBL DATA |  |  |  |  | UT |  | X | X | X
| 8 |  |  | Run GL pre-upgrade reports |  |  |  |  | UT |  | X | X | X
| 9 |  |  | Set GL pre-upgrade options |  |  |  |  | UT |  | X | X | X
| 10 |  |  | Evaluate and complete GL setup |  |  |  |  | GL |  | X |  |  | X
| 11 |  |  | Evaluate and complete GL processes |  |  |  |  | GL |  | X |  |  | X
| 12 |  |  | Run the interunit report |  |  |  |  | UT |  | X | X | X
| 13 |  |  | Prepare Asset Management defaults |  |  |  |  | AssetManagement | X | [8 empty] | X
| 14 |  |  | Run receivables overpayment report |  |  |  |  | UT |  | X | X | X
| 15 |  |  | Gather customer data |  |  |  |  | N/A
| 16 |  |  | Complete order management |  |  |  |  | N/A
| 17 |  |  | Complete billing tasks |  |  |  |  | ??
| 18 |  |  | Post receivables transactions |  |  |  |  | N/A
| 19 |  |  | Perform payables options setup |  |  |  |  | AP | [5 empty] | X | X
| 20 |  |  | Seup receivables conversations |  |  |  |  | ??
| 21 |  |  | Setup projects integrations |  |  |  |  | GG |  | X | X |  | X
| 22 |  |  | Execute match rules and transactions (ap) |  |  |  |  | AP | [5 empty] | X | X
| 23 |  |  | Complete inventory |  |  |  |  | ??
| 24 |  |  | Complete purchasing tasks |  |  |  |  | PO | [7 empty] | X | X
| 25 |  |  | Plan costing method changes |  |  |  |  | GL |  | X |  |  | X
| 26 |  |  | Understand ADB for GL |  |  |  |  | GL |  | X |  |  | X
| 27 |  |  | Update VAT transaction information |  |  |  |  | GL | [5 empty] | X | X
| 28 |  |  | Setup banks |  |  |  |  | GL | [5 empty] | X | X | X | X
| 29 |  |  | Plan chartfield configuration |  |  |  |  | GL |  | X | X |  | X
| 30 |  |  | Indentify Mass Change customizations |  |  |  |  | UT |  | X | X | X
| 31 |  |  | Prepare for fieldname conversion |  |  |  |  | UT |  | X | X | X
| 32 |  |  | Renam field BUDGET YEAR |  |  |  |  | UT |  | X | X | X
| 33 |  |  | Report row count for tables |  |  |  |  | UT |  | X | X | X
| 34 |  |  | Prepare database |  |  |  |  | UT |  | X | X | X
| 35 |  |  | Backup after prepare database |  |  |  |  | Systems | [10 empty] | X
4 |  |  | APPLY PEOPLETOOLS CHANGES |  |  | 1-2 days | 2002-01-21 | 2002-01-22
| 1 |  |  | Verify upgrade user |  |  |  |  | Systems | [10 empty] | X
| 2 |  |  | Perform script modifications |  |  |  |  | Systems | [10 empty] | X
| 3 |  |  | Update PeopleTools system tables |  |  |  |  | Systems | [10 empty] | X
| 4 |  |  | Load model definition data |  |  |  |  | Systems | [10 empty] | X
| 5 |  |  | Verify non-base language pages |  |  |  |  | Systems | [10 empty] | X
| 6 |  |  | Load base data |  |  |  |  | Systems | [10 empty] | X
| 7 |  |  | Rename PeopleTools records |  |  |  |  | Systems | [10 empty] | X
| 8 |  |  | Load language data |  |  |  |  | Systems | [10 empty] | X
| 9 |  |  | Load SQR string data |  |  |  |  | Systems | [10 empty] | X
| 10 |  |  | Load currency code data |  |  |  |  | Systems | [10 empty] | X
| 11 |  |  | Turn off change control |  |  |  |  | Systems | [10 empty] | X
| 12 |  |  | Update language data |  |  |  |  | Systems | [10 empty] | X
| 13 |  |  | Compare PeopleTools objects |  |  |  |  | Systems | [10 empty] | X
| 14 |  |  | Export and copy projects |  |  |  |  | Systems | [10 empty] | X
| 15 |  |  | Populate Tablespace data |  |  |  |  | Systems | [10 empty] | X
| 16 |  |  | Load message data |  |  |  |  | Systems | [10 empty] | X
| 17 |  |  | Create PeopleTools views |  |  |  |  | Systems | [10 empty] | X
| 18 |  |  | Load stored statement data |  |  |  |  | Systems | [10 empty] | X
| 19 |  |  | Convert PeopleCode |  |  |  |  | Systems | [10 empty] | X
| 20 |  |  | Convert fieldnames |  |  |  |  | Systems | [10 empty] | X
| 21 |  |  | Convert workflow objects |  |  |  |  | Systems | [10 empty] | X
| 22 |  |  | Convert Crystal reports |  |  |  |  | Systems | [10 empty] | X
| 23 |  |  | Configure the upgrade environment |  |  |  |  | Systems | [10 empty] | X
| 24 |  |  | Configure steps to un on the server |  |  |  |  | Systems | [10 empty] | X
| 25 |  |  | Convert PeopleTools objects |  |  |  |  | Systems | [10 empty] | X
| 26 |  |  | Perform the custom compare process |  |  |  |  | Systems | [10 empty] | X
| 27 |  |  | Backup after PeopleTools upgrade |  |  |  |  | Systems | [10 empty] | X
5 |  |  | RUN AND REVIEW COMPARE REPORTS |  |  | 6-12 Days | 2002-01-23 | 2002-01-24
| 1 |  |  | Rename records and fields |  |  |  |  | UT |  | X | X | X
| 2 |  |  | Rename tables |  |  |  |  | UT |  | X | X | X
| 3 |  |  | Copy select tables |  | 1 day |  |  | UT |  | X | X | X
| 4 |  |  | Run upgrade compare reports |  | 5-11 days |  |  | UT |  | X | X | X
| 5 |  |  | Review the compare reports |  |  |  |  | All | X | X | XX | X | X | X | X | X | X | X |  | X | X | X
6 |  |  | APPLY APPLICATION CHANGES |  |  | 1-2 Weeks | 2002-01-27 | 2002-02-10
| 1 |  |  | Prepare for application changes |  |  |  |  | All |  | X | X | X
| 2 |  |  | Run the upgrade copy |  |  |  |  | UT |  | X | X | X
| 3 |  |  | Update database overrides |  |  |  |  | UT |  | X | X | X
| 4 |  |  | Backup after the upgrade copy |  |  |  |  | Systems | [10 empty] | X
| 5 |  |  | Configure chartfields |  |  |  |  | UT |  | X | X | X
| 6 |  |  | Modify the database structure |  |  |  |  | UT |  | X | X | X
| 7 |  |  | Load data for data conversion |  |  |  |  | UT |  | X | X | X
| 8 |  |  | Set costing methods |  |  |  |  | UT |  | X | X | X
| 9 |  |  | Set interunit options |  |  |  |  | UT |  | X | X | X
| 10 |  |  | Set asset management defaults |  |  |  |  | UT |  | X | X | X
| 11 |  |  | Apply updates before data conversions |  |  |  |  | UT |  | X | X | X
| 12 |  |  | Backup before data conversions |  |  |  |  | UT |  | X | X | X
| 13 |  |  | Run data conversions |  |  |  |  | UT |  | X | X | X
| 14 |  |  | Backup after data conversion |  |  |  |  | UT |  | X | X | X
| 15 |  |  | Finalize the database structure |  |  |  |  | UT |  | X | X | X
| 16 |  |  | Load data to complete system setup |  |  |  |  | UT |  | X | X | X
| 17 |  |  | Load stored statements |  |  |  |  | UT |  | X | X | X
| 18 |  |  | Configure committement control |  |  |  |  | UT |  | X | X | X
| 19 |  |  | Convert data after alter with delete |  |  |  |  | UT |  | X | X | X
| 20 |  |  | Update object version numbers |  |  |  |  | UT |  | X | X | X
7 |  |  | COMPLETE DATABASE CHANGES |  |  |  | 2002-02-10 | 2002-02-24
| 1 |  |  | Reapply customizations |  |  |  |  | All | X | X | X | X | X | X | X | X | X | X |  | X | X | X
| 2 |  |  | Convert images |  |  |  |  | UT |  | X | X | X
| 3 |  |  | Convert panels to pages |  |  |  |  | UT |  | X | X | X
| 4 |  |  | Clear process and report tables |  |  |  |  | UT |  | X | X | X
| 5 |  |  | Setup security |  |  |  |  | Jason Moeller
| 6 |  |  | Run the final audit reports |  |  |  |  | UT |  | X | X | X
| 7 |  |  | Set country tbl |  |  |  |  | UT |  | X | X | X
| 8 |  |  | Complete inventory setup |  |  |  |  | UT |  | X | X | X
| 9 |  |  | Update customer and contact setup |  |  |  |  | UT |  | X | X | X
| 10 |  |  | Complete billing setup |  |  |  |  | UT |  | X | X | X
| 11 |  |  | Configure order management |  |  |  |  | UT |  | X | X | X
| 12 |  |  | Prepare treasury setup |  |  |  |  | UT |  | X | X | X
| 13 |  |  | Setup bank reconciliation |  |  |  |  | UT |  | X | X | X
| 14 |  |  | Convert AM book currency |  |  |  |  | UT |  | X | X | X
| 15 |  |  | Convert AM rate type |  |  |  |  | UT |  | X | X | X
| 16 |  |  | Clean up internal bank cash accounts |  |  |  |  | UT |  | X | X | X
| 17 |  |  | Setup projects interfaces |  |  |  |  | UT |  | X | X | X
| 18 |  |  | Modify depreciation conventions |  |  |  |  | UT |  | X | X | X
| 19 |  |  | Set VAT processing |  |  |  |  | UT |  | X | X | X
| 20 |  |  | Perform interunit analysis |  |  |  |  | UT |  | X | X | X
| 21 |  |  | Update new distribution types |  |  |  |  | UT |  | X | X | X
| 22 |  |  | Update te GL |  |  |  |  | UT |  | X | X | X
| 23 |  |  | Validate payables withholding |  |  |  |  | UT |  | X | X | X
| 24 |  |  | Perform payables setup |  |  |  |  | UT |  | X | X | X
| 25 |  |  | Set letter code content |  |  |  |  | UT |  | X | X | X
| 26 |  |  | Complete receivables changes |  |  |  |  | UT |  | X | X | X
| 27 |  |  | Update seed timezone data |  |  |  |  | UT |  | X | X | X
| 28 |  |  | Stamp the database |  |  |  |  | UT |  | X | X | X
| 29 |  |  | Backup before testing |  |  |  |  | Systems | [10 empty] | X
8 |  |  | USER TEST CYCLE 1 (7-30) |  |  | 2 weeks | 2002-02-24 | 2002-03-10 | Users
9 |  |  | CREATE CYCLE 2 |  |  | 1 week | 2002-03-10 | 2002-03-17 | UT
10 |  |  | USER TEST CYCLE 2 |  |  | 2 weeks | 2002-03-17 | 2002-03-31 | Users
11 |  |  | CREATE CYCLE 3 |  |  | 1 week | 2002-03-31 | 2002-04-07 | UT
12 |  |  | USER TEST CYCLE 3 |  |  | 4 weeks | 2002-04-07 | 2002-05-05 | Users
13 |  |  | PERFORM THE MOVE TO PRODUCTION (8-3) |  |  | weekend | 2002-05-02 | 2002-05-05 | UT
14 |  |  | CONDUCT POST GO LIVE REVIEW |  |  |  | 2002-05-12 | 2002-05-16 | PMT