## Notes
Notes for Field Plan and Work Plan
General
The Field Plan table is a filterable table that allows the user to select desired treatment types for a given year.
Each treatment should be checked off upon completion. (Typing a "P" will make check marks in check columns).
Work compliance surveys and stand evaluations form a foundation for adaptive management. Results are recorded in forest database and inventory.
Treatments
Stands to be commercially harvested (clearcut or commercial thin) need to be inventoried (cruised) well before operations begin in order to prepare contracts and Forest Practices Application (FPA).
Timing of commercial harvests should remain flexible to market trends. Therefore, it is advisable to have most inventory, contract preparations and FPA completed well in advance (1-3 years).
Planting must be preceded by a contract seedling order, which must be placed two growing seasons in advance and bed space reserved the autumn before the seedlings are sown.
Since harvest operations are on a flexible schedule, the exact area scheduled for planting may change by the time contracted seedlings are ready for planting. For example, when a large sale is postponed, a large a surplus of seedlings will result that is to cumbersome to easily manage. Therefore, seedling orders should be for a "hedged-bet" quantity - perhaps a three-year expected average. It is easy to sell a small surplus of seedlings and likewise easy and not too expensive to purchase a few over the counter.
Seedling orders should be tailored to the need of the operation, evaluate disease, site conditions, desired species, etc.
This is a list of potential seedling species for planting and natural regeneration. The first group consists of commercially valuable species natively found at Pack Forest: Douglas-fir, western redcedar, western hemlock, grand fir, western white pine (rust resistant), red alder, bigleaf maple and black cottonwood. Other species that could be considered for commercial regeneration include: hybrid poplar, noble fir, shore pine (Pinus contorta) and ponderosa pine (western Cascade variety). Some of the naturally regenerated species can be retained as non-dominants during thinning operations, such as bitter cherry, pacific madrone and other non-commercial hardwood trees. Species diversity may benefit by placing/encouraging poorly represented non-commercial species, such as Oregon ash and hawthorn, in wetlands and other sensitive sites.
Regeneration surveys should continue until stand is no longer threatened by browse and other significant causes of seedling mortality. Surveys are accompanied by needed interplanting and may require some over-the-counter seedling purchases. The final regeneration survey should be entered into the inventory and database.
Hardwood control is the removal of competitive weed species, including trees and shrubs. An effort is made during weeding operations to leave a representation of native hardwoods for species diversity. This is commonly done by leaving well-spaced hardwoods in areas not stocked with planted trees or by leaving non-dominants that pose little risk of suppressing planted trees.
Hardwood control evaluations are scheduled at the end of fourth growing season (late summer) after planting to determine if and when a control treatment is needed. If immediate action is required contracts can be written up for following spring/summer. Once evaluation is completed, the Field Plan table is updated to reflect evaluated course of action. Hardwood control can be sceduled for one or a series of years.
Pre-commercial thinning (PCT) evaluations are scheduled for 12 growing seasons after a clearcut harvest to determine best window of opportunity for PCT and if further hardwood control is needed. Evaluations result in either a free-to-grow conclusion, an appropriate treatment window or a schedule for future evaluations. Once evaluation is completed, the Field Plan table is updated to reflect evaluated course of action. PCT can be sceduled for one or a series of years.
Field Plan Table Key
Stand name cells highlighted in yellow indicate stands that have been added or treatments that have been changed (see notes column in Field Plan table).
Stand name cells highlighted in green indicate treatments that have been changed from one planning cycle to another.
Stand name cells highlighted in pink indicate scheduled treatments that have been dropped.
Final harvest operations are highlighted in tan.
Plantation maintenance operations are highlighted in light green.
Commercial thin operations are highlighted in lavender.
Selection harvest operations are highlighted in rose.
Red treatment cells indicate that there are concerns about the timing or application of the treatment and it needs further evaluation.
Notes for 2002 Work Plans
The work plan table contains the scheduled work for just the indicated year. It serves as a quick summary of stands requiring treatment. It is redundant to the Field Plan table for the given year, but is "cleaner" and closer view. It also serves as a useful worksheet to be edited and frequently updated without impact to the Field Plan table.
Once stands that have been scheduled for evaluation have been evaluated, they can be checked-off as completed on the Work Plan. If treatment is required in the same year, the stand can be added to a scheduled treatment category (i.e. PCT, Hardwood control, etc). If the evaluation results in a treatment scheduled for a subsequent year or window of years, it should be checked-off as "Evaluated" on the Work Plan table and scheduled on the Field Plan table.

## 2000-2009 Field Plan
Stands | Acres | Notes | P | 2000 | P | 2001 | P | 2002 | P | 2003 | P | 2004 | 2005 | 2006 | 2007 | 2008 | 2009
BR_1300_ROAD | 15.495 |  |  |  | P | PCT-180 |  | Compliance/Inventory
BR_B&T_NORTH | 33.532 |  |  |  | P | PCT-180 w/HW |  | Compliance/Inventory
BR_EBETH_RID | 167.949 | [10 empty] | 2005: PCT-180 (Eval & Inv.)
BR_Highpoint | 27.7 | added | [5 empty] | Hardwood Evaluation
BR_LJ_MAC | 7.208 |  |  |  | P | PCT-180 |  | Compliance/Inventory
BR_LONECEDAR | 13.41 |  |  |  | P | PCT-180 |  | Compliance/Inventory
BR_Midway | 27.846 | added | [7 empty] | Hardwood Evaluation
BR_NF_CCUT | 20.015 | [10 empty] | 2005: PCT-200 (Eval & Inv.)
BR_NF_CLUMP | 27.153 | [5 empty] | P | Hardwood Control |  | Compliance/Inventory |  | 2005: PCT-200 (Eval & Inv.)
BR_NF_DISP | 14.305 | [5 empty] | P | Hardwood Control |  | Compliance/Inventory
BR_PEEWEE_RA | 2.258 |  |  |  | P | PCT-180 w/HW |  | Compliance/Inventory
BR_PWT | 53.428 | [6 empty] | Order Seedlings |  |  |  | 2004: Inventory, FPA & Contracts; 2005: Clearcut & Plant 300
BR_SILV_CTRL | 20.66 | [8 empty] | Order Seedlings |  | 2006: Clearcut & Plant 300
BR_TRI | 34.514 |  |  |  | P | Clearcut & Plant 300 |  | Regeneration survey |  | Regeneration survey |  | 2005: Hardwood Evaluation
BR_TRI_27 | 13.41 |  |  |  | P | Clearcut & Plant 300 |  | Regeneration survey |  | Regeneration survey |  | 2005: Hardwood Evaluation
BR_UP_MURPHY | 78.084 | [10 empty] | 2004: Order Seedlings; 2007: Clearcut & Plant 300
HC_1200_RD | 18.498 |  |  |  |  | Order seedlings |  |  |  | Inventory, FPA & Contracts |  | 2004: Clearcut & Plant 300; 2007: Hardwood Evaluation
HC_1400-01 | 9.311 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_1400-02 | 11.877 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_1400NRSRV | 57.893 | [6 empty] | PCT-180 (Eval & Inv.)
HC_1400SRSRV | 26.188 | [6 empty] | PCT-200 (Eval & Inv.)
HC_2000_FINL | 28.321 | [6 empty] | PCT-200 (Eval & Inv.)
HC_27_CREEK | 52.797 | [6 empty] | PCT-180 (Eval & Inv.)
HC_CL | 23.031 | Added Hardwood Eval | [5 empty] | Hardwood Evaluation |  |  |  | 2007: PCT-180 (Eval & Inv.)
HC_CL_EAST | 22.963 |  |  |  |  | Order seedlings |  |  |  | Inventory, FPA & Contracts |  | 2004: Clearcut & Plant 300; 2007: Hardwood Evaluation
HC_CL_FWOOD | 26.727 | REMOVED
HC_CL_SOUTH | 42.285 | [6 empty] | PCT-180 (Eval & Inv.)
HC_CORVUS | 25.708 | Moved hardwood Eval to 2002 from 2005 | [5 empty] | Hardwood Evaluation
HC_DAM_CNYON | 6.633 | [10 empty] | 2005: PCT-200 (Eval & Inv.)
HC_EHUGO_RID | 23.821 |  |  |  | P | PCT-180 w/HW |  | Compliance/Inventory
HC_ENEWT_CR | 52.556 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_H_RIDGE | 30.481 |  |  |  | P | PCT-200 |  | Compliance/Inventory
HC_JUNGLE | 31.527 |  |  |  | P | Clearcut & Plant 300 |  | Regeneration survey |  | Regeneration survey |  | 2005: Hardwood Evaluation
HC_KEN_MAR | 18.946 |  | P | PCT-180 |  | Compliance/Inventory
HC_L_PWDR_TH | 43.693 | [10 empty] | 2009: Clearcut & Plant 300
HC_LOOK_ROAD | 95.225 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_NEWT_DIV | 30.221 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_NISQ_SLVG | 9.684 |  | P | PCT-180 w/HW |  | Compliance/Inventory
HC_PORCUPINE | 16.139 | [6 empty] | Inventory, FPA & Contracts |  | Clearcut & Plant 300 |  | 2004: Regeneration survey; 2006: Hardwood Evaluation
HC_PWDRFINAL | 6.402 | [6 empty] | Hardwood Control
HC_PWEE_CL | 12.712 | [6 empty] | PCT-180 (Eval & Inv.)
HC_PWEE_YUM | 25.38 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_RACESTUDY | 11.412 | Moved hardwood Eval to 2002 from 2005 | [5 empty] | Hardwood Evaluation
HC_RFNRP I | 20.3 | added | [5 empty] | Hardwood Evaluation
HC_RFNRP II | 22.7 | added | [5 empty] | Hardwood Evaluation
HC_Ridgetop | 25.443 | added | [5 empty] | Hardwood Evaluation
HC_SCRUB_OG | 18.161 | [6 empty] | Clearcut & Plant 300
HC_STOCKPILE | 34.06 |  | P | PCT-180 |  | Compliance/Inventory
HC_SWITCHBK | 3.198 | Moved from 2000 CC moved to 2009, postpone Harwood treatment to 2010 | [9 empty] | 2009: Clearcut & Plant 300
HC_THAWK_SAL | 8.892 | Moved hardwood Eval to 2002 from 2005 | [5 empty] | Hardwood Evaluation
HC_TOMAHAWK | 6.45 | [6 empty] | Hardwood Evaluation |  |  |  | 2005: PCT-180 (Eval & Inv.)
HC_UP_27_CR | 18.73 |  |  |  | P | PCT-180 |  | Compliance/Inventory
HC_UP_PWDR | 17.522 | [6 empty] | Inventory, FPA & Contracts |  | Clearcut & Plant 300 |  | 2004: Regeneration survey; 2006: Hardwood Evaluation
MF_BOULDER_N | 6.524 | [6 empty] | Hardwood Control
MF_BOULDER_S | 13.096 |  |  |  | P | Hardwood Control | [5 empty] | 2005: PCT-180 (Eval & Inv.)
MF_BTAIL_CRS | 31.397 | [10 empty] | 2004: Hardwood Evaluation; 2008: PCT-180 (Eval & Inv.)
MF_DOE_DFH | 8.639 | [6 empty] | PCT-180 (Eval & Inv.)
MF_DOE_DFL | 2.527 | [6 empty] | PCT-180 (Eval & Inv.)
MF_GATE_WP | 6.866 |  |  |  | P | Hardwood Control |  | Compliance/Inventory
MF_Geissen_Spec | 5.1 | added | [7 empty] | Hardwood Evaluation
MF_GES_FINAL | 24.441 | [10 empty] | 2008: PCT-180 (Eval & Inv.)
MF_GIES_SPEC | 5.056 |  |  |  | P | Clearcut & Plant 300 |  | Regeneration survey |  | Regeneration survey |  | 2005: Hardwood Evaluation
MF_HWY_7_REV | 14.401 |  |  | PCT-180 w/HW |  | Compliance/Inventory
MF_JAMERSON | 9.061 | REMOVED Hardwood Control 2000
MF_JNCT_FIN | 4.839 | [10 empty] | 2004: Hardwood Evaluation; 2008: PCT-180 (Eval & Inv.)
MF_MASH_FLAT | 25.478 | [10 empty] | 2004: Hardwood Evaluation
MF_MCSTENNIS | 42.272 |  |  | PCT-180 |  | Compliance/Inventory
MF_MOTEL | 13.08 | [10 empty] | 2004: Hardwood Evaluation; 2009: PCT-200 (Eval & Inv.)
MF_OPENING | 1.194 | [10 empty] | 2005: Hardwood Evaluation
MF_Phellinus | 80.29 | added |  |  | P | PCT-180 |  | Compliance/Inventory
MF_POWERLINE | 18.086 | [6 empty] | PCT-200 (Eval & Inv.)
MF_RR_FINAL | 22.941 | [6 empty] | Hardwood Evaluation |  |  |  | 2005: PCT-180 (Eval & Inv.)
MF_SPAC_TRLS | 67.897 | [6 empty] | PCT-180 (Eval & Inv.)
MF_VALENTINE | 14.007 | Treatment Changed from CT-100 to PCT 180 |  |  | P | PCT-180 |  | Compliance/Inventory
MF_VAN_ISLND | 5.738 | [6 empty] | CT-100
MF_WY_BIOSOL | 63.69 | [6 empty] | Order Seedlings |  | Inventory, FPA & Contracts |  | 2004: Selection Harvest & Plant 80
MF_WY_UNTR | 28.957 | [6 empty] | Order Seedlings |  | Inventory, FPA & Contracts |  | 2004: Selection Harvest & Plant 80
MR_BIG_PONDS | 59.428 | [8 empty] | Inventory, FPA & Contracts |  | 2004: CT-120
MR_BUCK_N | 14.194 | [6 empty] | PCT-180 (Eval & Inv.)
MR_BUCK_S | 16.251 |  |  |  | P | PCT-180 |  | Compliance/Inventory
MR_CCUT_CTRL | 12.759 | [6 empty] | PCT-180 (Eval & Inv.)
MR_GEORGE_SP | 61.28 |  |  |  | P | PCT-180 |  | Compliance/Inventory
MR_GRO | 37.519 | [8 empty] | Inventory, FPA & Contracts |  | 2004: CT-140
MR_LLMASH_E | 20.227 | Moved hardwood Eval to 2003 from 2005 | P | Clearcut & Plant 300 |  | Regeneration survey |  | Regeneration survey |  | Hardwood Evaluation
MR_LLMASH_W | 19.224 | Moved hardwood Eval to 2003 from 2005 | P | Clearcut & Plant 300 |  | Regeneration survey |  | Regeneration survey |  | Hardwood Evaluation
MR_LMASHELL | 23.013 |  | P | Hardwood Control |  | Compliance/Inventory
MR_NWTIC_MDW | 13.236 | [6 empty] | PCT-180 (Eval & Inv.)
MR_Ponds | 5.004 | completed |  |  | P | PCT-180 |  | Compliance/Inventory
MR_SEEDTREE | 7.555 | [6 empty] | Hardwood Control |  | Compliance/Inventory
MR_SHELTERWOOD | 8.2 | ADDED TO SCHEDULE | [5 empty] | Hardwood Control |  | Compliance/Inventory
MR_SLIDE | 7.124 | [6 empty] | Hardwood Control |  | Compliance/Inventory
MR_SUBDIV | 25.747 | [6 empty] | Clearcut & Plant 300 |  | Regeneration survey |  | 2004: Regeneration survey; 2006: Hardwood Evaluation
MR_WELL | 24.126 | Moved hardwood Eval to 2002 from 2005 | [5 empty] | Hardwood Evaluation
MR_Y_THIN | 6.601 | [6 empty] | Order Seedlings |  | Inventory, FPA & Contracts |  | 2004: CT-40
SE_1ST_COUG | 30.868 | [6 empty] | Order Seedlings |  | Inventory, FPA & Contracts |  | 2004: CT-40
SE_B&T_SOUTH | 5.34 |  |  |  | P | PCT-180 w/HW |  | Compliance/Inventory
SE_BELUGA | 16.939 | [6 empty] | PCT-180 (Eval & Inv.)
SE_COUGAR | 25.904 |  | P | Clearcut & Plant 300 |  | Compliance/Inventory |  |  |  | Hardwood Evaluation
SE_Cougar | 25.904 | added | [7 empty] | Hardwood Evaluation
SE_FALL_FIRS | 8.521 | Moved from 2005, moved to 2003, added hardwood evaluation 2007 | [5 empty] | Order seedlings |  | Inventory, FPA & Contracts |  | 2004: Clearcut & Plant 300 WRC; 2007: Hardwood Evaluation
SE_INGLIS | 12.182 | [5 empty] | P | Hardwood Control |  | Compliance/Inventory |  | 2005: PCT-200 (Eval & Inv.)
SE_MATERIALS | 28.829 | Added hardwood Eval | [5 empty] | Hardwood Evaluation |  |  |  | 2008: PCT-200 (Eval & Inv.)
SE_MUTUAL | 72.598 | [6 empty] | PCT-180 (Eval & Inv.)
SE_NOVELLI | 99.08 | [10 empty] | 2007: Selection Harvest & Plant 80
SE_RAY | 1.947 | ADDED TO SCHEDULE | [5 empty] | Hardwood Control |  | Compliance/Inventory
SE_TALMADGE | 12.904 | [6 empty] | PCT-180 (Eval & Inv.)
SE_TALMO | 101.963 |  |  |  |  | Hardwood Control | [5 empty] | 2004: PCT-200 (Eval & Inv.)
SE_WALLIN | 12.259 | [5 empty] | P | Hardwood Control |  | Compliance/Inventory

## 2002 Work Plan
Stands | Acres | P | 2002 | Treatment Sum Acres | Details
Commercial Thin |  |  |  |  | Actual Acres | Final TPA | Volume Harvested | Conifer SL Volume | Planting Compliance?
MF_VAN_ISLND | 5.738 |  | CT-100 | 5.738
Clearcut & Plant 300 |  |  | Clearcut & Plant 300 | 43.908 | Actual Acres | Logging Compliance? | Volume Harvested | Conifer SL Volume | Planting Compliance?
HC_SCRUB_OG | 18.161
MR_SUBDIV | 25.747 |  | Acres completed | 0
Regeneration survey |  |  | Regeneration survey | 123.958 | Stocking | Species mix | Browse Protection? | # trees interplant | Survey Next Year?
BR_TRI | 34.514
BR_TRI_27 | 13.41
HC_JUNGLE | 31.527
MF_GIES_SPEC | 5.056
MR_LLMASH_E | 20.227
MR_LLMASH_W | 19.224 |  | Acres completed | 0
Order Seedlings |  |  | Order Seedlings | 192.065 | Contract or OTC. | TPA | # Trees | # Species 1 | # Species 2 | # Species 3
BR_PWT | 53.428 | [5 empty] | 0
MF_WY_BIOSOL | 63.69 | [5 empty] | 0
MF_WY_UNTR | 28.957 | [5 empty] | 0
MR_Y_THIN | 6.601 | [5 empty] | 0
SE_1ST_COUG | 30.868 | [5 empty] | 0
SE_FALL_FIRS | 8.521 |  | Acres completed | 0 |  |  | 0
Compliance/Inventory |  |  | Compliance/Inventory | 558.543 | Prev Treatment | Final TPA | Pass Compliance?
BR_1300_ROAD | 15.495 |  |  |  | PCT-180
BR_B&T_NORTH | 33.532 |  |  |  | PCT-180
BR_LJ_MAC | 7.208 |  |  |  | PCT-180
BR_LONECEDAR | 13.41 |  |  |  | PCT-180
BR_PEEWEE_RA | 2.258 |  |  |  | PCT-180
HC_1400-01 | 9.311 |  |  |  | PCT-180
HC_1400-02 | 11.877 |  |  |  | PCT-180
HC_EHUGO_RID | 23.821 |  |  |  | PCT-180
HC_ENEWT_CR | 52.556 |  |  |  | PCT-180
HC_H_RIDGE | 30.481 |  |  |  | PCT-200
HC_LOOK_ROAD | 95.225 |  |  |  | PCT-180
HC_NEWT_DIV | 30.221 |  |  |  | PCT-180
HC_PWEE_YUM | 25.38 |  |  |  | PCT-180
HC_UP_27_CR | 18.73 |  |  |  | PCT-180
MF_GATE_WP | 6.866 |  |  |  | HW Control
MF_Phellinus | 80.29 |  |  |  | PCT-180
MF_VALENTINE | 14.007 |  |  |  | PCT-180
MR_BUCK_S | 16.251 |  |  |  | PCT-180
MR_GEORGE_SP | 61.28 |  |  |  | PCT-180
MR_Ponds | 5.004 |  |  |  | PCT-180
SE_B&T_SOUTH | 5.34 |  | Acres completed | 0 | PCT-180
Hardwood Evaluation |  |  | Hardwood Evaluation | 247.532 | Control Needed? | Approx. Acres | Treatment Window | Arial or Hand? | Contract or hourly?
BR_Highpoint | 27.7
HC_CL | 23.031
HC_CORVUS | 25.708
HC_RACESTUDY | 11.412
HC_RFNRP I | 20.3
HC_RFNRP II | 22.7
HC_Ridgetop | 25.443
HC_THAWK_SAL | 8.892
HC_TOMAHAWK | 6.45
MF_RR_FINAL | 22.941
MR_WELL | 24.126
SE_MATERIALS | 28.829 |  | Acres completed | 0
Hardwood Control |  |  | Hardwood Control | 103.651 | Actual Acres | Pass Compliance? | Final TPA
BR_NF_CLUMP | 27.153
BR_NF_DISP | 14.305
HC_PWDRFINAL | 6.402
MF_BOULDER_N | 6.524
MR_SEEDTREE | 7.555
MR_SHELTERWOOD | 8.2
MR_SLIDE | 7.124
SE_INGLIS | 12.182
SE_RAY | 1.947
SE_WALLIN | 12.259 |  | Acres completed | 0
PCT-180 (Eval & Inv.) |  |  | PCT-180 (Eval & Inv.) | 387.38 | Pre-treat Stocking | Species mix | Bear Damage? | Treatment Window | Contract or hourly?
HC_1400NRSRV | 57.893
HC_27_CREEK | 52.797
HC_CL_SOUTH | 42.285
MF_DOE_DFH | 8.639
MF_DOE_DFL | 2.527
MF_SPAC_TRLS | 67.897
MR_BUCK_N | 14.194
MR_CCUT_CTRL | 12.759
MR_NWTIC_MDW | 13.236
SE_BELUGA | 16.939
SE_MUTUAL | 72.598
SE_TALMADGE | 12.904
HC_PWEE_CL | 12.712 |  | Acres completed | 0
PCT-200 (Eval & Inv.) |  |  | PCT-200 (Eval & Inv.) | 72.595 | Pre-treat Stocking | Species mix | Bear Damage? | Treatment Window | Contract or hourly?
HC_1400SRSRV | 26.188
HC_2000_FINL | 28.321
MF_POWERLINE | 18.086 |  | Acres completed | 0
PCT-180 |  |  | PCT-180 | 0 | Actual Acres | Final Spacing | Final Species Mix
|  |  | Acres completed | 0
PCT-200 |  |  | PCT-200 | 0 | Actual Acres | Final Spacing | Final Species Mix
|  |  | Acres completed | 0
Inventory, FPA & Contracts |  |  | Inv, FPA & Contracts | 0 | Scheduled Treatment | Actual Acres | Cruised Volume | Conifer SL Volume | Cable Required? | FPA Approved? | Contracts Prepared?
Scheduled for 2003
HC_PORCUPINE | 16.139 |  |  |  | CC
HC_UP_PWDR | 17.522 |  |  |  | CC
Scheduled for 2004
HC_1200_RD | 18.498 |  |  |  | CC
HC_CL_EAST | 22.963 |  |  |  | CC
MR_BIG_PONDS | 59.428 |  |  |  | CT-120
MR_GRO | 37.519 |  |  |  | CT-140
MR_Y_THIN | 6.601 |  |  |  | CT-40
SE_1ST_COUG | 30.868 |  |  |  | CT-41
SE_FALL_FIRS | 8.521 |  | Acres completed | 0 | CC
Note on F2: Mason McKinley: Based on GPS, boundary traverse. Did boundary change from GIS?
Note on H2: Mason McKinley: This data is essential for monitoring forest growth.
Note on F4: Mason McKinley: Based on GPS, boundary traverse. Did boundary change from GIS?
Note on H4: Mason McKinley: This data is essential for monitoring forest growth.
Note on F7: Mason McKinley: Final stocking and specied mix need to be entered into inventory.
Note on H7: Mason McKinley: List type of protection recommended
Note on I7: Mason McKinley: Add number to "Order Seedling" category - on Work plan if ordering this year, on Field Plan if next year.
Note on J7: Mason McKinley: If "yes". Enter into Field Plan
Note on A14: Mason McKinley: Add estimates for interplanting and other projects.
Note on F14: Mason McKinley: Contract needs to be ordered early Fall before first growing season (P+1 need two growing seasons). OTC should be ordered preferably during spring/summer before planting but many species can be found right up to planting date.
Note on G21: Mason McKinley: Data needs to be entered into inventory. Not required for Hardwood control.
Note on A43: Mason McKinley: Hand slashing needs to be done in summer. Foliar spray is done in Spring or Fall. Basal treatements have a wide window.
Note on H43: Mason McKinley: Estimate window seasons for treatment. A contract can be put together if many acres can be grouped.
Note on A56: Mason McKinley: Hand slashing needs to be done in summer. Foliar spray is done in Spring or Fall. Basal treatements have a wide window.
Note on F56: Mason McKinley: Not all of stand may need treatement. Enter estimated acres or GPS area.
Note on H56: Mason McKinley: Not required measurement. Enter into inventory if available.
Note on H67: Mason McKinley: Describe extent of damage if found.
Note on I67: Mason McKinley: Estimate window seasons for treatment. A contract can be put together if many acres can be grouped.
Note on H81: Mason McKinley: Describe extent of damage if found.
Note on I81: Mason McKinley: Estimate window seasons for treatment. A contract can be put together if many acres can be grouped.

## 2000-09 All Stands
Stands | 00-Treatments | 05-Treatments
BR_PWT |  | Clearcut & Plant 300
BR_SILV_CTRL |  | Clearcut & Plant 300
BR_UP_MURPHY |  | Clearcut & Plant 300
HC_L_PWDR_TH |  | Clearcut & Plant 300
SE_FALL_FIRS |  | Clearcut & Plant 300
BR_TRI | Clearcut & Plant | Hardwood Control
BR_TRI_27 | Clearcut & Plant 300 | Hardwood Control
HC_1200_RD | Clearcut & Plant 300 | Hardwood Control
HC_CL_EAST | Clearcut & Plant 300 | Hardwood Control
HC_CORVUS |  | Hardwood Control
HC_JUNGLE | Clearcut & Plant 300 | Hardwood Control
HC_PORCUPINE | Clearcut & Plant 300 | Hardwood Control
HC_RACESTUDY |  | Hardwood Control
HC_SWITCHBK | Clearcut & Plant 300 | Hardwood Control
HC_THAWK_SAL |  | Hardwood Control
HC_UP_PWDR | Clearcut & Plant 300 | Hardwood Control
MF_GIES_SPEC | Clearcut & Plant 300 | Hardwood Control
MF_OPENING |  | Hardwood Control
MR_LLMASH_E | Clearcut & Plant 300 | Hardwood Control
MR_LLMASH_W | Clearcut & Plant 300 | Hardwood Control
MR_SUBDIV | Clearcut & Plant 300 | Hardwood Control
MR_WELL |  | Hardwood Control
SE_COUGAR | Clearcut & Plant 300 | Hardwood Control
BR_EBETH_RID |  | PCT-180
HC_TOMAHAWK | Hardwood Control | PCT-180
MF_BOULDER_S | Hardwood Control | PCT-180
MF_BTAIL_CRS | Hardwood Control | PCT-180
MF_JNCT_FIN | Hardwood Control | PCT-180
MF_RR_FINAL | Hardwood Control | PCT-180
HC_CL |  | PCT-180 w/HW
MF_GES_FINAL |  | PCT-180 w/HW
BR_NF_CCUT |  | PCT-200
BR_NF_CLUMP | Hardwood Control | PCT-200
MF_MOTEL | Hardwood Control | PCT-200
SE_INGLIS | Hardwood Control | PCT-200
SE_MATERIALS |  | PCT-200
HC_DAM_CNYON |  | PCT-200 w/HW
BR_1300_ROAD | PCT-180
BR_B&T_NORTH | PCT-180 w/HW
BR_B&T_NORTH_200ft
BR_BETH_1300
BR_HIGH_PNT
BR_LJ_MAC | PCT-180
BR_LONECEDAR | PCT-180
BR_MIDWAY
BR_MIDWAY_200ft
BR_NF_CLUMP_50ft
BR_NF_DISP | Hardwood Control
BR_NF_WLDCOR
BR_PEEWEE_RA | PCT-180 w/HW
BR_RA_EA
BR_SILV_DEMO
BR_SILV_DEMO_200ft
BR_STEEPLES
HC_1400-01 | PCT-180
HC_1400-02 | PCT-180
HC_1400NRSRV | PCT-180
HC_1400SRSRV | PCT-200
HC_2000_FINL | PCT-200 w/HW
HC_2000_THIN
HC_27_CREEK | PCT-180
HC_CENTURY
HC_CL_ALDER
HC_CL_FWOOD | Hardwood Control
HC_CL_SOUTH | PCT-180 w/HW
HC_CL_THIN
HC_COVINGTON
HC_DOE_BRIDG
HC_DOE_RAL
HC_ECOL_AREA
HC_EHUGO_RID | PCT-180 w/HW
HC_ENEWT_CR | PCT-180
HC_ENEWT_CR_50ft
HC_G&H
HC_H_RIDGE | PCT-200
HC_HP_TRANS
HC_HUGO_WP
HC_JUNGLE_50ft
HC_KEN_MAR | PCT-180
HC_LATH_DR_B
HC_LATH_DR_S
HC_LOOK_ROAD | PCT-180
HC_MURRELET
HC_NEWT_DIV | PCT-180
HC_NISQ_SLVG | PCT-180 w/HW
HC_PAYCHECK
HC_PWDRFINAL | Hardwood Control
HC_PWEE_CL | PCT-180 w/HW
HC_PWEE_CL_50ft
HC_PWEE_YUM | PCT-180
HC_RFNRP_1
HC_RFNRP2
HC_RIDGETOP
HC_SCRUB_OG | Clearcut & Plant 300
HC_STOCKPILE | PCT-180
HC_TPU
HC_TPU_50ft
HC_UP_27_CR | PCT-180
HC_WHUGO_RID
MF_BALLFIELD
MF_BIO_INTER
MF_BLACKBERY
MF_BOULDER_N | Hardwood Control
MF_CAMP_BUFF
MF_CAMPUS
MF_CORP
MF_DECADES
MF_DOE_DFH | PCT-180 w/HW
MF_DOE_DFL | PCT-180 w/HW
MF_DOE_RAH
MF_FRONT_VIL
MF_GATE_THIN
MF_GATE_WP | Hardwood Control
MF_GES_IRRIG
MF_GES_THIN
MF_GONYEA
MF_HWY_7_REV | PCT-180 w/HW
MF_JAMERSON | Hardwood Control
MF_JNCT_THIN
MF_LATH_DR_N
MF_MADBOBCAT
MF_MASH_FLAT | Hardwood Control
MF_MASH_RMZ
MF_MASH_RMZ_200ft
MF_MCSTENNIS | PCT-180
MF_MILL_POND
MF_NISQ_RMZ
MF_NISQ_RMZ_200ft
MF_PHELLINUS
MF_POWERLINE | PCT-200
MF_ROBERTO
MF_ROCKPILE
MF_RR_THIN
MF_RR_WETLND
MF_SAND_PIT
MF_SP_TRIAL
MF_SPAC_TRLS | PCT-180
MF_STINK_ELK
MF_STINK_ELK_200ft
MF_VALENTINE | CT-100
MF_VAN_ISLND | CT-100
MF_VANESSA
MF_WASTEWATR
MF_WETLANDS
MF_WY_BIOSOL | Selection Harvest & Plant 80
MF_WY_UNTR | Selection Harvest & Plant 80
MF_XA4
MR_27CR_E_TH
MR_27CR_RMZ
MR_27CR_W_TH
MR_BIG_PONDS | CT-120
MR_BIG_PONDS_200ft
MR_BUCK_N | PCT-180
MR_BUCK_S | PCT-180
MR_BUCK_WET
MR_CCUT_CTRL | PCT-180
MR_FIBER
MR_GEORGE_SP | PCT-180
MR_GRO | CT-140
MR_HY_POPLAR
MR_LM_WATERFALL
MR_LMASH_RMZ
MR_LMASHELL | Hardwood Control
MR_MURPHYFLD
MR_NON_FOR
MR_NWTIC_MDW | PCT-180 w/HW
MR_PONDS
MR_SEEDTREE | Hardwood Control
MR_SHELTERWD
MR_SLIDE | Hardwood Control
MR_Y_THIN | CT-40
SE_1ST_COUG | CT-40
SE_1ST_COUG_50ft
SE_B&T
SE_B&T_200ft
SE_B&T_SOUTH | PCT-180 w/HW
SE_BELUGA | PCT-180
SE_CEDAR_EA
SE_CLAY_PIT
SE_COW_EAST
SE_COW_WEST
SE_DACCARDO
SE_ELKMEADOW
SE_ELKMEADOW_50ft
SE_ELMA_PLY
SE_KELLY
SE_LESS_MUD
SE_LOG_CAMP
SE_LOG_CAMP_50ft
SE_MATERIALS_50ft
SE_MUD
SE_MUD_50ft
SE_MUTUAL | PCT-180
SE_MUTUAL_200ft
SE_NOVELLI |  | Selection & Plant 80
SE_NOVELLI_50ft
SE_RAY
SE_TALMADGE | PCT-180 w/HW
SE_TALMO | PCT-200 w/HW
SE_TALMO_50ft
SE_THINS
SE_WALLIN | Hardwood Control