## GPM Course Project Plan
Game Project Management: Mr. Emrich
Course Project Plan
Duration of Class by Week
(C = 'in class;' H = 'homework' to be done during the week between lessons)
Task | Who? | 1 C | 1 H | 2 C | 2 H | 3 C | 3 H | 4 C | 4 H | 5 C | 5 H | 6 C | 6 H | 7 C | 7 H | 8 C | 8 H | 9 C | 9 H | 10 C | 10 H | 11 C
Get a Job (including job description) | Every
Form a Team | Team
Switch Job and / or Team (if desired) | Individual
Create 3x ideas for corporate identity | Individual
Decide upon corporate identity | Team
Create corporate buss cards & letterhead | Art Dir.?
Corporate buss cards & letterhead due [12 points total] | Team
Create 3x ideas for game to pitch | Individual
Decide upon game idea to pitch | Team
Discuss vision for game to pitch | Team
Write draft Concept Document for the game | Writer
Draft Concept document due [8 points] | Team
Break down tasks for Homework Gantt chart | Individual
Create draft of Homework Gantt chart | Producer
Submit Homework Gantt chart to Teammates | Producer
Review, amend, approve Homework Gantt Chart | Team
First Examination [20 points] | Individual
In-Class Milestones
Survival Test | Team
Peer Review: JOAT [9 points] | Team
Game Review (draft) due | Individual
Second Examination [25 points] | Individual
Peer Review: Art Director [9 points] | Team
Game Review (final) due [8 points] | Individual
Peer Review: Technical Director [9 points] | Team
Practice Pitch 1 [9 points; graded on progress] | Team
Peer Review: Lead Writer / Designer [9 points] | Team
Letter of Recommendation due [8 points] | Individual
Peer Review: Producer [9 points] | Team
Practice Pitch 2 [9 points; graded on substance] | Team
Third Examination [30 points] | Individual
Dress Rehearsal (not graded; style judged) | Team
Final Pitch Presentation [62 Team & Individual points] | Team
Sample Marketing Plan Tasks
Conduct Marketing Research to validate game | Producer
Draft Marketing Research paper | Producer
Submit Marketing Research paper to team | Producer
Redraft Marketing Research paper | Producer
Submit Marketing Research paper to Lead Writer for incorporation into Pitch Packet | Producer