## Summary Report
NSR Proprietary
| Oversight Summary Report |  |  |  |  | 2003-08-13
Product/Service | Component | Component Schedule | Component Quality | Component Risk | Component Complete | Comments
Project Management | Project Planning |  |  |  |  | New Direction Changes Schedule
| Communication Management |  |  |  |  | Some changes expected with new vendor
| Risk Management |  |  |  |  | New Direction = New Critical Success Factors
Change Request Management
Performance Management
| Budget Management |  |  |  |  | No current budget issues
Resource Management
Release Management
| Contract Management |  |  |  |  | PAQ Requirements not clear, contract not signed
Software Development | Requirements Analysis |  |  |  |  | Final requirements document needed
| Design |  |  |  |  | Report Designs are still in progress
| Development/Configuration |  |  |  |  | New direction changes development schedule
Configuration Mgmt/Version Ctrl
Database Development | Database Analysis
Database Design
Database Construction
Operational Data Store
Quality Assurance | Integration Test |  |  |  |  | Test planning is still in progress
System Test
User Acceptance Test
Data Conversion | Conversion Requirements Analysis
Conversion Scripts Development
Conversion Scripts Implementation
User Training | Planning |  |  |  |  | Training plan drafted, not yet in synch with deployment
| Curriculum Development |  |  |  |  | Sample curriculum and materials formats determined
Training Material Generation
Training Implementation
System Deployment | Pilot Site Deployment |  |  |  |  | Deployment/Implementation Plan still in progress
Statewide Deployment
Interfaces | Internal Interfaces
External Interfaces
Support Services | Help-Desk |  |  |  |  | Help-Desk Operations Manual in Draft
| Software Maintenance |  |  |  |  | Software Maintenance Plan in Draft
| Status Legend: |  | All deliverables are on schedule and have satisfactory quality. No actions
necessary
Potential schedule overrun or questionable quality. Special attention in this area
can prevent an impact to overall project budget/schedule.
Schedule overrun or poor quality. Extensive effort or project scope change
is needed to avoid overall project budget/schedule impact. Project Improvement
Plan required

## Project Management
NSR Proprietary
Project Management
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Project Planning | Project Management Plan |  | Project Workplan |  |  | WBS
|  | Master Project Workplan |  | Project Schedule |  |  | Tasks
|  |  |  | Project Organization Chart |  |  | Task Durations
Deliverable Milestones
Critical Path Identified
Weekly progress on deliverables
Resources Identified
Key Stakeholders Identified
Work Definition (Scope)
|  | Project Control/Scope Document |  |  |  |  | Project Scope Definition
| Communications Management | Communications Plan
Stakeholder Communications
Communications Channels
Emergency/Crisis Response Plan
Communications/Involvement Metrics
Monitor Readiness
|  | Project Status Reports |  |  |  |  | Bi-weekly Project Status
|  | Metrics Reports |  |  |  |  | Accomplishments
|  | Issues Reports |  |  |  |  | Deliverables Provided
|  | Status Meetings |  |  |  |  | Planned Activities
|  | Report on Tasks |  |  |  |  | Planned Deliverables
|  | Task Coordination |  |  |  |  | Activities Behind Schedule
|  | Team Agency Activity |  |  |  |  | Issues Reports
Metrics
Project Summary
|  | Project Management Meetings |  | Status Updates |  |  | Weekly Updates
|  | Oversight Committee Meetings |  | Status Updates |  |  | Weekly Updates
|  | Oversight Summary Report |  |  |  |  | New, Old, Closed Issues
Oversight Issues Report
Project Website/Collaboration Tool
| Risk Management | Risk Management/Mitigation Plan |  |  |  |  | Risk Identification Process
List of potential risk areas
|  | Top ## Risk List (updated monthly) |  |  |  |  | Top ## Risks List
|  | Risk/Issues Mitigation Reports |  |  |  |  | Risk Mitigation Strategy
|  | Critical Succss Factors |  |  |  |  | Reviewed/Updated as Necessary
| Change/Scope Management | Change Management Plan (Process) |  |  |  |  | Change Request Procedures
Change Types/Appropriate Actions
Review Cycle/Procedures
|  |  | Change Tracking Form/Tool/System |  |  |  | Change Tracking Tool/System
Change Request Form
| Performance Management |  | Project Improvement Plans
| Budget Management | Budget Plan |  |  |  |  | Budget Baseline
|  | Payment Milestones/Schedule |  |  |  |  | Budget Reviews & Updates
|  | Budget and Cost constraints list |  |  |  |  | Budget vs. Actual Metrics
Burn Rate
Budget Issues
| Resource Management | Resource Management Plan
Project Organization Chart
Project Roles and Responsibilities
| Release Management/Version Control | Version Control/Configuration Management Plan
| Contract Management | PAQ and Contract Artifacts
Legislation
Organization & Management Directives
Policy, Guidelines, and Standards Documents
Note on C5: Risks: - A breakdown of documentation requirements and associated tasks should be defined (the WBS). - All activities associated with each level must be defined including: project planning and control, configuration management, quality assurance and documentation. - Inadequate quantity of people to design and deliver project components, or people with the needed skills not involved or available. - Failure to meet planned delivery dates delaying project schedule or increasing project costs.
Note on C15: Risks: -Lack of common understanding among leadership, including conflicting priorities, differing expectations regarding scope, or varying commitment levels.
Note on C19: The Communication Plan is critical to the project success. - It indicates what effort by staff other than the project team is going to be required. - It gives time frames for management/stakeholders to schedule staff and themselves - It is the primary tool to keep all stakeholder groups informed, interested and involved in the project. - Clearly and concisely defines the rules of engagement between the Government team and the contractors involved. Risks - Communication and involvement not integrated into normal day-to-day activities. - If all collaborators are not involved in project communications, the benefits of the system may not be fully realized and the system may not contain the functionality required. - Not gaining access to needed data/information and/or not being able to schedule meetings with project executives and stakeholders.
Note on C27: Risk: - Key issues not being identified and resolved quickly result in project delays or wasted effort.
Note on C55: Risks: - Ensures broad participation from the stakeholders and project team in understanding the implications of the system. - No ability to control software defects and enhancements.
Note on C65: Risks: - Budget impacts are recorded against approved funding and for contract validation and modification, if required.

## Software Development
NSR Proprietary
Software Development
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Requirements Analysis | Business Models (Rules, Processes) or Use Cases (Actors and Actions)
Functional Requirements Specification
Requirements Traceability Matrix
Subject Matter or Functional Expert List
Focus Group/JAD Sessions
| Design | Functional Design Specification or Object Model
GUI Design (Screen definitions)
Reports Design
Interfaces Design (Internal and External)
Security Design
Functional Prototype
Technical Design Specification
Architecture Model (systems, sub-systems, API)
Hardware/Infrastructure Design
Network Design
Security Design
Performance Specification
| Development | Developer’s Handbook (standards, protocols, and best practices)
Built and Tested Application Components:
Operational Technical Architecture (Network, Storage, Infrastructure, Environments)
Operational Database
Application Logic
User Interfaces
Reports
System Interfaces (Internal and External)
Security
Application Security (Authentication and Authorization)
Data Transmission Security
Physical Security
Personnel Security
Administrative Security
| Configuration Management/Version Ctrl. | Code Repository - Configuration Manamgent Tools

## Database Development
NSR Proprietary
Database Development
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Database Analysis | Data Entities/Data Definition
| Database Design | Logical Database Design
Physical Datamodels
Entity Relationship Diagram
Technical Design Specification
| Database Construction | Physical Database(s)
Operational Datastore

## Quality Assurance
NSR Proprietary
Quality Assurance
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Integration Test | Integration Test Plan
Integration Test Scripts
| System Test | System Test Plan
System Test Scripts
System Defect Tracking Tools
| User Acceptance Test | User Acceptance Test Plan
User Acceptance Test Scripts
Go-live Requirements Check-list

## Data Conversion
NSR Proprietary
Data Conversion
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Conversion Requirements Analysis | Conversion Analysis and Design
Data Identification and Mapping
| Conversion Scripts Development | Data Conversion Development (Conversion Scripts)
| Conversion Scripts Implemetation | Data Conversion and Mitigation Plan
Mock Conversions

## Training
NSR Proprietary
End-User Training
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Planning | End-User Training Plan
| Curriculum Development | Curriculum Definition and Syllabus
| Training Materials Generation | User Manuals
On-line Help
| Training Implementation | Train-the-Trainer Training
End-User Training

## Deployment
NSR Proprietary
Deployment
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Planning | System Deployment Plan and Schedule
| Pilot Site Deployment | Pilot Site Deployment (Verification and Validation)
| Statewide Deployment | Production Deployement - Fully Operational System

## Interfaces
NSR Proprietary
Interfaces
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Internal Interfaces | Internal Interface Components
| External Interfaces | External Interface Components

## Support Services
NSR Proprietary
Support Services
| Component | Deliverable |  | Dependency | Status | Responsible | Quality Factor | Deliverable Requirement
|  | Required | Recommended |  |  | Party
| Help-Desk | Help-Desk Handbook
Help-Desk Training
| Software Maintenance | Systems Maintenance and Operations Plan
System Administration and Operations Handbook
Systems Administration and Operations Training
System Tuning and Remediation