## Sheet1
Mechanical Design & Detail Estimates for NSFCAM2, with Options
2002-04-09
Assembly Name |  | Chng | New | Comments on Change/New | Ds/Dt Hrs | Options and Comments | Ds/Dt Hrs (Opt)
Array Mount Old |  | N |  | For Ref. Only
Closed Cycle Cooler |  | Y |  | Fit to New Vacuum Jacket | 80 | 1050 CTI, (needed?) | 160
Cold Structure Turret Cell |  | Y |  | 2 New Lens Cell Assys, no FPW | 160 | 1 LensCell+fix Turret (with FPW) | 80
Cvf Housing |  | N
Cvf Wheel | And Drive | Y |  | Change Drive due to New VJ | 80
Dichroic Turret And Drive |  | Y |  | Dichroic moves up ~ 3 inch | 160
Filter Wheel And Drive |  | Y |  | Change Drive due to New VJ | 80 | Wollaston Prism in CVF Wheel | 60
Focal Plane Wheel, FPW |  |  | Yes | eliminate making 2 Lens Cell Assys |  | New FPW to Nsfcam Upgrade | 160
Lens Cell Assemblies |  |  | Yes | Design 2 identical Lens Assys | 120
Lens Turret And Drive |  | Y |  | Fit New Lens Cell Assemblies,Drive | 160
Nsfcam 2K Upgrade |  |  | Yes | Modify Rockwell Array Mt | 100
Optics |  | N |  | For Ref. Only
Preamp Box |  |  | Yes | Due to Nsfcam 2K Upgrade (Array Mt) | 80
Radiation Shield |  | Y |  | Extend (modify) existing Rad. Shield | 120 | Design New Radiation Shield | 160
Ray Traces |  | Y |  | For Ref Only
Thermal Straps 2K Array |  | Y |  | Redesign for 2K Array | 120
Nsfcam Interface |  |  | Yes | Required | 80 | Possibility of using Old Mount
Vacuum Jacket ,VJ |  |  | Yes | Due to new location of Dichroic | 160 | E.B.Weld vs Plate Constr.
Cold Mass Support |  | Y |  | Relocate shear webs closer to CofG | 20 | Redesign Dewar for V-Trusses | 40
|  |  |  | Total Design/Detailing (no options) | 1520
[6 empty] | Total Ds/Dt (w.options) | 1780
Additional Comments:
1) The Vacuum Jacket has to be rebuilt/redesigned because of the new position for the Dichroic
2) The Thermal Clamp will be removed. The available space can be used for the new FPW
3) If a 1050 CTI is required for cooling, the CCC Box will have to be redesigned (incls in 160hrs)
4) Only selected parts of Nsfcam have been modeled in I-deas, time for further modeling is not included
5) This estimate also includes the Detail Drawings
6) A preliminary estimate for Fabrication is about 1/3 to 1/2 of Design/Detailing Times
7) We may want to change to Animatics Motors. Only Fabrication time will be needed.