## On-Going
Student Systems Maintenance Projects | [8 empty] | 2004-03-31 15:30
Vistas/SAR
On-Going
Project Description | Date Submitted | Client Office | Client Contact | System | Assigned | Priority | Status | Estimated Completion Date | Comments
*** SAR ***
SAR Merge Accounts (4 Records) | 2003-12-16 | UAR | L. Kiehne | SAR | Jim | Low | On-Going
Dependent Tuition Refund Error | 2003-12-04 | UAR | L. Kiehne | SAR | Laura | Low | Testing
FRIT/FRIS Problem - Not posting pmts | 2004-01-06 | UAR | L. Kiehne | SAR | Tom | Medium | On-Going
FRIS - Being Blanked Out | 2004-01-26 | UAR | L. Kiehne | SAR | Tom | Medium | On-Going
FRIS - Fees incorrect for NSES | 2004-01-28 | REG | D. Esquibel | SAR | Tom | Low | Pending |  | Not DB2 error;Leland has work-around;Pending info by Leland
SARZ5035/SARZ5036 - Empty report to E-Print | 2004-03-01 | UAR | L. Kiehne | SAR | Laura | Low | On-Going
Tuit Calc - Increased Tuition For TX Waiver | 2004-03-11 | UAR | L. Kiehne | SAR |  | High | Open |  | Need info from Leland;TBA RTW
*** VISTAS ***
RGUG/RGGR Grade Option Change | 2003-12-08 | REG | D. Esquibel | VIS | Laura | High | Testing |  | OK per Cuca 3/24/2004
NAMX - Mass Unofficial Transcript Ordering | 2003-12-17 | ADM | D. Wilson | VIS |  | Low | Open
RGUG/RGGR Wrong Time Display on BFAT | 2003-12-22 | ICT | J. Wilson | VIS | Laura | High | Migrate
Course Prerequisites | 2004-01-07 | AS | J. Brown | VIS | Bruce | High | On-Going |  | Fix Math course grade checks
AHUG/AHGR - Acad Sanction/Athletic Warning | 2004-01-08 | REG | D. Esquibel | VIS | Bruce | Low | On-Going
SCCL - Room Scheduling Conflict Warning | 2004-01-15 | REG | D. Esquibel | VIS | Tom | Low | On-Going
THSC Table Performance | 2004-01-12 | ADM | D. Wilson | VIS |  | Low | Open
REGC5258 - Diplomatic Downloaded | 2004-01-13 | REG | D. Esquibel | VIS | Laura | Medium | On-Going
RGUG - 500+ Block Undergrads (allow PB's) | 2004-01-14 | ICT | J. Wilson | VIS | Laura | High | Testing |  | OK per Cuca 3/24/2004
Changing of Courses From UG to GR (Cum hrs. error) | 2004-01-23 | REG | D. Esquibel | VIS | Siiri | High | Testing |  | Pending changes to AHUG/AHGR Dual Trail Error
AHUG/AHGR - Dual Trail Error | 2004-02-24 | ICT | J. Wilson | VIS | Bruce | High | On-Going
Repeat Fixer - Future Repeats | 2004-01-23 | REG | J. Wilson | VIS | Jim | Medium | On-Going |  | Should be fixed with grading
E-Mail Addresses on Vistas (SINQ/SINF) | 2004-01-30 | REG | S. Cooper | VIS | Tom | Medium | On-Going |  | Only send changes;On bottom on screen/protected
Grade Testing in U Region | 2004-02-06 | ICT | J. Wilson | VIS |  | Medium | Open |  | After Distance Ed
CCFS - Abends in DB2D | 2004-02-09 | ICT | J. Wilson | VIS | Tom | Low | On-Going
RGUG - Overload Limit | 2004-02-11 | ICT | J. Wilson | VIS | Bruce | High | On-Going |  | Fix Probationary students
First/last attended sweep & error report | 2004-02-16 | ICT | J. Wilson | VIS | Siiri | High | On-Going |  | NOT working;REGZATTN;Waiting on response from Siiri
AHUG - ACO Error On First Record | 2004-03-02 | REG | D. Esquibel | VIS | Bruce | Low | On-Going
MPEX - Performance Issue | 2004-03-03 | ICT | J. Wilson | VIS |  | Medium | Open
Withdrawl Rules | 2004-03-04 | ICT | J. Wilson | VIS |  | High | Open |  | Pending ADAC decision/rules
CRMS Enhancements - Changes For Fall | 2004-03-04 | CRMS | Y. Flores | VIS |  | Medium | Open
SADU - Adm Actn Edits/Activity Records | 2004-03-05 | ICT | J. Wilson | VIS | Laura | High | Testing |  | Sent to client 3/23/2004
AHUG - Delete Confirmation Msg. Missing | 2004-03-05 | ICT | J. Wilson | VIS | Bruce | Low | On-Going
SADR - Key field error with change | 2004-03-16 | REG | J. Wilson | VIS | Jim | Low | Testing
DSPS - ASRA w/ multiple ? On Services/Agency | 2004-03-16 | REG | J. Wilson | VIS | Jack | Low | On-Going
REGC0310 - ASRA w/ CS on RGWD | 2004-03-17 | REG | M. Scott | VIS | Jim | High | On-Going |  | Due to adding courses, next line partially erased
RGWD - Clean-Up Report | 2004-03-17 | REG | D. Esquibel | VIS |  | High | TBA
SADU - Should Not Accept Inactive Campus | 2004-03-19 | REG | J. Wilson | VIS | Laura | High | Testing |  | Sent to client 3/23/2004
RGDT - Date File Problem | 2004-03-24 | REG | D. Esquibel | VIS |  | High | TBA |  | Research what programs update RGDT
REGZ5122 - Not Printing Totals | 2004-03-24 | REG | C. Saenz | VIS | Laura | Low | Testing |  | Sent to client 3/31/2004
RGUG/RGGR - Next Field Not Displaying | 2004-03-30 | ICT | J. Wilson | VIS | Bruce | Low | On-Going
Readmission Error - Registration w/o application | 2004-03-31 | ALAMO | M. Scott | VIS |  | Medium | TBA
REGZ5287/DGUG - Attendance Flag | 2004-03-31 | REG | V. Remington | VIS | Laura | Medium | On-Going |  | Need more info from Vivian
BFAT - Shows future dates on DS | 2004-03-31 | REG | J. Gabriel | VIS |  | High | TBA
*** Other ***
Program Narrative on Web | 2003-12-15 | ICT | J. Wilson | WEB | Ben | Low | On-Going
New Help Screens on Web (from Leland) | 2003-12-23 | UAR | L. Kiehne | WEB | Laura/Ben | Low | On-Going
Update Technical Document | 2004-02-23 | ICT | J. Wilson | OTHER | Laura | High | On-Going
Open = Decision/Information Required | 465616627 | 2004FA
TBA = To Be Assigned | 1025464 | AG E 337
| 1026958 | ECON 337
| 1025793 | AXED 446 | 1025792
| 1026026 | BUSA 365
| 1026028 | BUSA 421
| 1026032 | BUSA 422
CTFM 270
| 1027214 | ENGL 203
| 1027231 | ENGL 211
| 1027250 | ENGL 218
| 1027280 | ENGL 311
| 1027283 | ENGL 318
HNFS 421
| 1028271 | MATH 210
| 1029265 | STAT 251
WLSC 258

## Resolved
Student Systems Maintenance Projects | [8 empty] | 2004-03-31 15:30
Vistas/SAR
Resolved
Project Description | Date Submitted | Client Office | Client Contact | System | Assigned To | Priority | Status | Actual Completion Date | Comments
*** SAR ***
Staff Waiver Error (ST/SP same ID) | 2003-12-11 | UAR | L. Kiehne | SAR | John | High | Resolved | 2003-12-12
ARIB Incorrect Posting | 2003-12-08 | UAR | L. Kiehne | SAR | Bruce | High | Resolved | 2003-12-15
Staff Tuition Waiver Error | 2003-12-05 | UAR | L. Kiehne | SAR | Tom | Medium | Resolved | 2003-12-23
CASH Screen Not Posting Staff Waivers | 2003-12-16 | UAR | L. Kiehne | SAR | Tom | High | Resolved | 2004-01-05
SARGRAD Not Posting Transactions | 2003-12-23 | UAR | C. Miranda | SAR | Laura | High | Resolved | 2004-01-12 | Timing issue in Dec.
FRIS Interface Error - SAM Tables | 2004-01-14 | UAR | L. Kiehne | SAR | Tom | High | Resolved | 2004-01-15 | Leave Sam tbl up;call from client
FRIS - Tuition Calc Error | 2004-01-22 | UAR | L. Kiehne | SAR | Tom | High | Resolved | 2004-01-23
FRIS - Updating Non-existing Records | 2004-01-22 | UAR | L. Kiehne | SAR | Tom | High | Resolved | 2004-01-23
Missing FRIT Transactions | 2004-01-29 | UAR | L. Kiehne | SAR | Bruce | Low | Resolved | 2004-01-30 | Scrolling issue
Testing of FRIS Roll | 2004-01-20 | ICT | J. Wilson | SAR | Tom | High | Resolved | 2004-01-30 | Before month end
SARZ5039 - HRSZ Step | 2004-01-30 | UAR | L. Archer | SAR | Laura | High | Resolved | 2004-02-02 | Client verified
SARZ5022 - No output (-904 unavailable resources) | 2004-01-28 | UAR | L. Kiehne | SAR | Laura | High | Resolved | 2004-02-03 | Ran 1/30/2004 OK; client verified
SARZ5035/SARZ5036 To E-Print | 2003-12-23 | UAR | L. Kiehne | SAR | Laura | High | Resolved | 2004-02-04
SARZ5039 - Error Report | 2004-02-04 | UAR | N. Qualkenbush | SAR | Laura/Doug | High | Resolved | 2004-02-05 | Pending client checking after run
SARZ5035/SARZ5036 - Sort By Offset Acct | 2004-02-11 | UAR | L. Kiehne | SAR | Laura | Low | Resolved | 2004-02-16
SARZ5025 Running Too Long | 2004-01-05 | ICT | L. Ramirez | SAR | Bruce | Low | Resolved | 2004-02-16
SARZ5035/SARZ5036 - No Output | 2004-02-17 | FIN AID | L. Montoya | SAR | Laura | Low | Resolved | 2004-02-16 | Leland will give e-print access
TRA 1098-T | 2003-11-01 | UAR | L. Kiehne | SAR | Bruce | High | Resolved | 2004-02-18
ADRS - Name Not Appearing On Other Screens | 2004-02-13 | UAR | L. Kiehne | SAR | Jack | Medium | Resolved | 2004-03-01
ARSY - Tuition & Other | 2004-03-01 | UAR | L. Kiehne | SAR | Jim | Low | Resolved | 2004-03-01
SARZ5014 Change | 2003-12-15 | UAR | L. Kiehne | SAR | Jack | Low | Resolved | 2004-03-01
ARSY - Incorrect Amount on RETN code | 2004-02-23 | UAR | L. Kiehne | SAR | Jim | Low | Resolved | 2004-03-01
Correct FINAID Disbursement Receipt Errors | 2004-03-04 | UAR | L. Kiehne | SAR | Jim | Low | Resolved | 2004-03-11 | Leland requested to be removed from list
SARC0121 - Staff/Spouse Waiver 4 cr For Summer | 2004-02-24 | UAR | L. Kiehne | SAR | Laura | Low | Resolved | 2004-03-18
ASNMSU/HlthActity - Use Billable Hours | 2004-03-03 | UAR | L. Kiehne | SAR | Laura | High | Resolved | 2004-03-18
Tuit Category Change - Registration Doc | 2004-03-03 | UAR | L. Kiehne | SAR | Laura | High | Resolved | 2004-03-18
*** VISTAS ***
SADU Blank/Invalid Elig Flags | 2003-12-10 | REG | D. Wilson | VIS | Jack | High | Resolved | 2003-12-12
REGZ5077 Nightly Abend | 2003-12-08 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2003-12-11
REQT Now Type Code/Date | 2003-12-04 | REG | D. Esquibel | VIS | Jack | High | Resolved | 2003-12-12
RGWD/AHUG Partial Withdrawl | 2003-12-11 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2003-12-12
ADRS/SADR Zip Code Error | 2003-12-10 | REG | D. Esquibel | VIS | Bruce | Medium | Resolved | 2003-12-15
CCSM/CCPM in DEV | 2003-12-15 | ICT | J. Wilson | VIS | John | High | Resolved | 2003-12-16
SCCL Instructor (=) Error | 2003-12-15 | ALAMO | L. Beaver | VIS | Tom | High | Resolved | 2003-12-16
ATHL Report | 2003-12-12 | ATHL | V. Martinez | VIS | Jack | High | Resolved | 2003-12-18
REQT Now Type/Date Rollback | 2003-12-15 | REG | D. Esquibel | VIS | Jack | High | Resolved | 2004-01-08 | JRB can't duplicate error
RGGD Mass Grades Entered Error | 2003-12-16 | REG | D. Esquibel | VIS | Tom | High | Resolved
REGO0313 - First/Last Attend Sem Missing | 2003-12-17 | REG | D. Esquibel | VIS | Tom | High | Resolved
REGZ5116 - Type Code Missing | 2003-12-17 | REG | D. Esquibel | VIS | Bruce | High | Resolved
REGZ5217 - S322 - Infinite Loop | 2004-01-05 | P&C | Drake | VIS | Jack | High | Resolved | 2004-01-06
REGZ5226 - Route output to users | 2003-12-23 | ICT | J. Wilson | VIS | Laura | Low | Resolved | 2004-01-06 | To requestor (S. Cooper)
DEGX - ID Search - System Down | 2003-12-10 | ICT | L. Ramirez | VIS | Tom | High | Resolved | 2004-01-06
DGGR - Application for MJ C EP not working | 2003-12-01 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-01-08
Changing Printer Def on RGUG | 2004-01-09 | H&SS | G. Nunez | VIS | Jack | High | Resolved | 2004-01-12 | Logging out, defined printer
STUFICA | 2003-12-08 | ICT | P. Jeffries | VIS | Jack | High | Resolved | 2004-01-12 | Will test in June
Source Lib Dataset Clean-up (Dev) | 2004-01-05 | ICT | J. Wilson | VIS | Laura | High | Resolved | 2004-01-12
REGZ5143 - List Option Not Working | 2004-01-13 | ICT | J. Wilson | VIS | Bruce | High | Resolved | 2004-01-14
REGC5089 - Basic Skills (Activity Records) | 2004-01-07 | A&S | D. Hands | VIS | Jack | High | Resolved | 2004-01-14
RGUG - Abend 4038 for GR/CA Campuses | 2004-01-14 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-01-14 | Missing ASDO0175
REGZ6164 - Class List for Soc/Anth | 2004-01-14 | A&S | N. Howell | VIS | Laura | Low | Resolved | 2004-01-14 | Client got report
SCCL - Abend and M204 Message | 2004-01-08 | REG | D. Esquibel | VIS | Jim | Low | Resolved | 2004-01-14 | Can't duplicate
SADG Blank College Error | 2003-12-22 | ICT | J. Wilson | VIS | Jim | High | Resolved | 2004-01-15 | 1 student incident
REGZ5107 - Data Exception for ATHL | 2004-01-14 | P&C | L. Archer | VIS | Jack | High | Resolved | 2004-01-15
REGZ5103 - Sort and Data Exception | 2004-01-15 | P&C | L. Archer | VIS | Jack | High | Resolved | 2004-01-16
REGZ5143 - List Option Not Working | 2004-01-16 | ICT | J. Wilson | VIS | Jack | High | Resolved | 2004-01-16
REGZ5080 - Grade Mailer Program Clean-up | 2004-01-13 | ICT | J. Wilson | VIS | Jack | High | Resolved | 2004-01-16
REGZ5235 - Registration Tracking for Athletes | 2004-01-15 | VP | V. Martinez | VIS | Tom | High | Resolved | 2004-01-20
MCLA on REG Menu | 2003-12-03 | ICT | J. Wilson | VIS | Laura | Low | Resolved | 2004-01-20 | No one uses it per Jim
REGC5015 - Housing Addr Updates | 2004-01-14 | P&C | L. Archer | VIS | Bruce | High | Resolved | 2004-01-21
SADU Readmission/Date Error | 2003-12-08 | ADM | D. Wilson | VIS | Tom | Medium | Resolved | 2004-01-21
SADU Test Score Rcvd Flags | 2003-12-12 | ADM | D. Wilson | VIS | Jack | High | Resolved | 2004-01-21
SADU 558 Error Removed | 2003-12-15 | ICT | J. Wilson | VIS | Jack | Low | Resolved | 2004-01-21
SCCL/REGZ5019/REGZ5182 - Not cancelling courses | 2004-01-13 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-01-22
Repeat Fixer Processing | 2004-01-20 | ICT | J. Wilson | VIS | Siiri | High | Resolved | 2004-01-22
RGUG - Reg Docs Not Printing | 2004-01-21 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2004-01-26 | Caused by dup BI codes
SASM/SADU - Name Changes Error | 2004-01-08 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-01-26
REGC5130 Academic interest | 12/19/2003 1/12/2004 | H&SS AG | C. MacAllister B. Weathers | VIS | Laura | Low | Resolved | 2004-01-26 | HS problem due to wrong AI AG will request sort #3
Fix Old Duplicate Address Codes | 2004-01-26 | REG | J. Wilson | VIS | Jim | High | Resolved | 2004-01-28 | Manually fixed
CRMS - REGZ5247 | 2003-12-15 | CRMS | Y. Flores | VIS | Jack | High | Resolved | 2004-01-28
Cum GPA Correct/SADG GR GPA Incorrect | 2004-01-23 | REG | D. Esquibel | VIS | Siiri | High | Resolved | 2004-01-29
Sweep To Recalc All Grad Gpa's | 2004-01-23 | REG | J. Wilson | VIS | Siiri | High | Resolved | 2004-01-29
CERT - Branch offices can't enter | 2004-01-13 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2004-01-30
Testing of CHE Drop | 2004-01-20 | ICT | J. Wilson | VIS | Jack | High | Resolved | 2004-01-30
REGZ5143 - Add meals processing | 2004-02-02 | ICT | J. Wilson | VIS | Laura | High | Resolved | 2004-02-02
RGGR Ineligible/Independent Study | 2003-12-15 | REG/GS | Esquibel/Vasquez | VIS | Jack | High | Resolved | 2004-02-03
RGUG/RGGR - Duplicate sections not allowed | 2004-01-13 | REG | D. Esquibel | VIS | Laura | High | Resolved | 2004-02-03
RGUG/RGGR - Error withdrawing course | 2004-02-01 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2004-02-03
CRMS - REGZ5029/REGC5031 | 2004-01-28 | REG | J. Wilson | VIS | Jack | High | Resolved | 2004-02-03
RGGR - Allowing Registration After Census | 2004-02-04 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2004-02-04
REGC0310 - First/Last Attended | 2004-01-13 | REG | D. Esquibel | VIS | Siiri | High | Resolved | 2004-02-04 | Run prog REGEATTN to check
RGUG - Abend 4038 For Carlsbad | 2004-02-06 | REG | E. Shannon | VIS | Bruce | High | Resolved | 2004-02-09
Basic Skills Reopened | 2004-01-15 | A&S | D. Hands | VIS | Jack | High | Resolved | 2004-02-09
REGC5009 - CC13 On Summer Rolls | 2004-02-09 | P&C | L. Archer | VIS | Jack | High | Resolved | 2004-02-10 | Chg sem validation routine
GPA Calc - Combine GRD1 & GRD2 | 2003-12-17 | ICT | J. Wilson | VIS | Jack | Low | Resolved | 2004-02-10 | JRB told P&C to run summer file
REGZ5187 - Performance Issue (missing grd sheets) | 2003-12-17 | ICT | J. Wilson | VIS | Jack | Low | Resolved | 2004-02-12
REGZ5122 Report - SUM 1 2001 | 2004-02-16 | BA&E | V. Arias | VIS | Jim | Low | Resolved | 2004-02-16 | Data has been purged
TWHO - M204 Message | 2004-02-16 | REG | D. Esquibel | VIS | Jim | Low | Resolved | 2004-02-17
Verify ASD to DB2 Loadlibs | 2004-01-14 | ICT | J. Wilson | VIS | Jim | Low | Resolved | 2004-02-23 | Check all modules;i.e. ASDC0175
Mass Compile in U Region | 2004-02-06 | ICT | J. Wilson | VIS | Jim | Low | Resolved | 2004-02-23
Class Cancellation Error Reopened | 2004-02-17 | REG | Esquibel/Scott | VIS | Laura | Medium | Resolved
Basic Skills Problems | 2004-02-09 | ICT | J. Wilson | VIS | Jack | High | Resolved | 2004-02-23 | Old record issue
REGC5089 - Abend Issue | 2004-02-10 | ICT | J. Wilson | VIS | Jack | High | Resolved | 2004-02-23 | Debbie: check students tomorrow
More call numbers for DABCC | 2004-02-25 | DABCC | B. Altamirano | VIS | Jack | Low | Resolved | 2004-02-26
RGUG/RGGR - Athletic Warning | 2004-01-08 | REG | D. Esquibel | VIS | Bruce | High | Resolved | 2004-02-26 | Sent to client for testing on 2/17/2004;resolved,not an error
REGZ5102 - Cum Credits Earned (ATHL) | 2004-01-23 | VP | V. Martinez | VIS | Jack | Medium | Resolved | 2004-02-27
REGC5133 - Grade Sheet Error (Minis) | 2004-03-02 | P&C | L. Archer | VIS | Bruce | High | Resolved | 2004-03-02
EVUG Scrolling | 2003-12-01 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-03-04
EVUG ADPL/Previous Record Not Found | 2003-12-01 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-03-04
EVUG - Approval Error For HS | 2004-02-17 | REG | D. Esquibel | VIS | Tom | Medium | Resolved | 2004-03-04
REGZ5069 - Duplicate dataset | 2003-12-17 | ICT | J. Wilson | VIS | Jim | Low | Resolved | 2004-03-04
Batch Contention Issues | 2004-02-10 | ICT | J. Wilson | VIS | Jim | High | Resolved | 2004-03-04
Crimson data cleanup | 2004-02-19 | CRMS | Y. Flores | VIS | Jack | High | Resolved | 2004-03-04 | Cleanup as a result of UCC multiple runs
Transcript Print Problem | 2004-02-26 | ICT | J. Wilson | VIS | Jim | High | Resolved | 2004-03-04
REGC5008/HRSZ0070 | 2004-02-27 | ICT | L. Ramirez | VIS | Laura/Doug | High | Resolved | 2004-03-04
RGWD - Withdrawl Restore Error | 2004-03-02 | ICT | J. Wilson | VIS | Bruce | High | Resolved | 2004-03-04
EVUG #7 - Course Match Outside Catalog Semester | 2004-03-04 | REG | D. Esquibel | VIS | Jim | High | Resolved | 2004-03-05
MCSU - Mixed Case in Dev | 2004-03-04 | ICT | J. Wilson | VIS | Laura | Low | Resolved | 2004-03-05
EVUG - NSES Grades/Blank Univ w/ ADPL | 2004-03-03 | REG | D. Esquibel | VIS | Tom | High | Resolved | 2004-03-05
MCRS - Blank Course Info on Dev (SPCH) | 2004-03-05 | ICT | J. Wilson | VIS | Tom | Low | Resolved | 2004-03-05 | Blank prefix on table will not have course info on MCRS
RGWD - Withdrawl Restore Cleanup | 2004-03-04 | ICT | J. Wilson | VIS | Jim | High | Resolved | 2004-03-08 | (Jessica Torres - fixed by Denise)
RGWD - Performance Issue | 2004-03-08 | REG | J. Wilson | VIS | Bruce | High | Resolved | 2004-03-08
Basic Skills Still Not Working | 2004-02-24 | ICT | J. Wilson | VIS | Jack | High | Resolved | 2004-03-08 | Followed-up w/ Debbie Hands 3/9/2004
REGZ5091 - Change of PBA to BA report | 2004-02-19 | BA | R. Byrum | VIS | Jack | Medium | Resolved | 2004-03-10
FINAID Activity Records - Removed | 2004-02-04 | REG | B. Schaa | VIS | Bruce | Low | Resolved | 2004-03-15
Transfer Keys Clean-Up/Deletion | 2004-02-04 | REG | B. Schaa | VIS | Bruce | Low | Resolved | 2004-03-17 | New program: REGC5274
CRMS Documentation | 2004-02-17 | ICT | J. Wilson | VIS | Jack | Low | Resolved | 2004-03-17
Distance Ed Billing | 2003-12-15 | DIST ED | C. Gonzales | VIS | Laura | High | Resolved | 2004-03-18
Distance Ed Screen Changes | 2004-02-02 | DIST ED | C. Gonzales | VIS | Laura | High | Resolved | 2004-03-18 | SCSS,SCCL,SCSM,SCAS,SCIS,ARDT,FRIS,CHEC,RGDC, ? Support (ok)
Distance Ed Reporting | 2004-02-13 | DIST ED | C. Gonzales | VIS | Laura | High | Resolved | 2004-03-18 | Requirements Being Defined
CHEC - Instructor Change/Interface Error | 2004-03-01 | REG | D. Esquibel | VIS | Laura | Low | Resolved | 2004-03-18
SASM - Missing Cum Line | 2004-02-09 | ICT | J. Wilson | VIS | Jack | Medium | Resolved | 2004-03-18
REGZ5019 - Removing invalid char in SEM field | 2004-03-04 | ICT | J. Briggs | VIS | Jack | Low | Resolved | 2004-03-19
AHUG - Rebuild On History | 2004-03-04 | REG | D. Esquibel | VIS | Jim | High | Resolved | 2004-03-19 | Pending other information from Denise
DE - Le to MA Sweep/Inactivate Le Campus | 2004-03-19 | REG | C. Gonzales | VIS | Tom/Jesus | High | Resolved | 2004-03-19 | Both Vistas & Banner
More call numbers for CA | 2004-03-22 | CA | J. Carnathan | VIS | Jack | High | Resolved | 2004-03-22
Review Activity Record Deletion | 2004-02-17 | ICT | J. Wilson | VIS | Bruce | Low | Resolved | 2004-03-24 | 1 old Basic Skills record out there
Test V7 on DB2U (Monday) | 2004-03-19 | REG | J. Wilson | VIS | Laura/Jim | High | Resolved | 2004-03-24
DGGR - Tint Validation Error | 2004-03-08 | REG | D. Esquibel | VIS | Jack | High | Resolved | 2004-03-26
REQT - Scrolling Problem | 2004-03-08 | REG | D. Esquibel | VIS | Jack | Medium | Resolved | 2004-03-26
RGUG/RGGR - Fall Registration Stopping Sum Reg. | 2004-03-29 | CRMS | Y. Flores | VIS | Bruce | High | Resolved | 2004-03-29
REGM0441 - Disabled/Centennial Time Error | 2004-03-29 | CRMS | Y. Flores | VIS | Bruce | High | Resolved | 2004-03-29
DGGR - MBIO Major Error | 2004-03-29 | REG | V. Remington | VIS | Laura | Medium | Resolved | 2004-03-30
MCFL - Scrolling Stops on S A 255 | 2004-03-05 | ICT | L. Ramirez | VIS | Jack | Low | Resolved | 2004-03-30
REGC5015 - Dup BI Code - Halts Print Docs | 2004-01-26 | REG | J. Wilson | VIS | Bruce | Low | Resolved | 2004-03-30
*** Other ***
Banner Roll - Incomplete ACT date | 2003-12-18 | ADM | D. Wilson | BAN | Laura | High | Resolved | 2004-01-12 | Roll in DEV ok;act date fine
Vistas Form/Training for new employee | 2004-01-09 | GEOL | L. Hubbard | TRAIN | Laura | Low | Resolved | 2004-01-14 | She will call M. Zimmerman
GAFINAID Focus Report | 2003-12-19 | GS | S. Moreno | REPT | Dave | High | Resolved | 2004-01-13 | Client got report
Crystal Reports Installation | 2004-01-14 | GS | P. Powell | OTHER | Laura | Low | Resolved | 2004-01-14 | Client will call Help Desk
Class Ring Mailing List | 2004-01-16 | BOOK | R. Benson | REPT | Corina | High | Resolved | 2004-01-30
ACT Received Date Error | 2004-01-23 | ADM | D. Wilson | BAN | Laura | Low | Resolved | 2004-02-13
Copy of Prod to Dev and User | 2003-12-23 | ICT | J. Wilson | OTHER | Jim | Low | Resolved | 2004-02-23 | Just request it
Engineering Focus Report | 2004-01-16 | ENGR | S. Castillo | REPT | Ben | High | Resolved | 2004-03-05 | Working on executable (Cecil)
List of Reports/Processes on Web | 2004-03-05 | ICT | J. Wilson | OTHER | Ben | Low | Resolved | 2004-03-24

## Abends
Student Systems Maintenance Projects | [5 empty] | 2004-03-31 15:30
Vistas/SAR/SAM
Nightly Abends
Project Description | Date Abended | System | Programmer | Status | Actual Completion Date | Comments
*** SAR ***
SARZ5025 - Ran too long | 2003-12-17 | SAR | Tom | Resolved | 2003-12-17 | Indexing conflict
SARC5027 - Not in prod library | 2003-12-19 | SAR | Tom | Resolved | 2003-12-19
SARC5007 - Bad Control Card (0 vs. O) | 2004-01-20 | SAR | Drake | Resolved | 2004-01-20
SARZ5014 - CC16 | 2004-01-23 | SAR | Tom | Resolved | 2004-01-23
SARZ5025 - Ran too long (2 hrs) | 2004-01-27 | SAR | Laura | Resolved | 2004-01-27 | Last SSN: 999-99-9975
SARZ5015 - CC16 | 2004-01-30 | SAR | Laura | Resolved | 2004-01-30
SARZ5004 - SB37 | 2004-01-30 | SAR | Liz | Resolved | 2004-01-30
SARZ5039 - SYS213 | 2004-01-30 | SAR | Laura | Resolved | 2004-01-30 | flat file: asd.db2p.loadlib
SARZ5025 - Ran too long | 2004-02-03 | SAR | Bruce | Resolved | 2004-02-03 | Wob Conflict
SARC5017 - CC13 | 2004-02-12 | SAR | Liz | Resolved | 2004-02-12 | Wrong CC
SARZ5025 - CC16 | 2004-02-27 | SAR | Liz/Alex | Resolved | 2004-02-27 | Re-run
SARZ5035 - CC8 FTP | 2004-02-27 | SAR | Liz/Alex | Resolved | 2004-03-01 | Re-run
SARZ5036 - CC8 FTP | 2004-02-27 | SAR | Liz/Alex | Resolved | 2004-03-01 | Re-run
SARC5008/SARC5049 - Datasets Not Found | 2004-03-03 | SAR | Laura | Resolved | 2004-03-03
*** Vistas ***
REGZ5077 - Data exeception | 2003-12-10 | VIS | Bruce/Corina | Resolved | 2003-12-11
REGCGRD1 - SQL Bind Error | 2003-12-17 | VIS | Bruce | Resolved | 2003-12-17
REGCGRD2 - File Contention Error | 2003-12-17 | VIS | Bruce | Resolved | 2003-12-17
REGZ5107 - File Contention Error (Sam tables) | 2003-12-17 | VIS | Bruce | Resolved | 2003-12-17
REGZ5069 - Duplicate Dataset Name | 2003-12-17 | VIS | Tom | Resolved | 2003-12-17
REGZ5159 - Abend S322 | 2003-12-17 | VIS | Tom | Resolved | 2003-12-17
REGZ5239/REGC5089 - Running wrong exec | 2003-12-17 | VIS | Jack | Resolved | 2003-12-17
REGZ5177 - Abend S322 Datasets not found | 2003-12-18 | VIS | Tom | Resolved | 2003-12-18
REGZ5272 - Wrong sem control card | 2003-12-18 | VIS | Drake | Resolved | 2003-12-18 | Re-run in Jan.
REGC5185 - Sem control card missing | 2003-12-19 | VIS | Drake | Resolved | 2003-12-19
REGC5130 - Sem control card missing | 2003-12-19 | VIS | Drake | Resolved | 2003-12-19
REGZ5143 - CC13 | 2003-12-19 | VIS | Drake | Resolved | 2003-12-19
REGC5130 - CC13 - Closed Cursor | 2004-01-07 | VIS | Jack | Resolved | 2004-01-07
REGZ5272 - Missing dataset/ wrong parameters | 2004-01-07 | VIS | Drake | Resolved | 2004-01-07
REGZ5080 - SO4C | 2004-01-09 | VIS | Jack | Resolved | 2004-01-13 | Reply to PC (grd mailer)
REGZ5069 - Duplicate Dataset Name | 2004-01-14 | VIS | Liz | Resolved | 2004-01-14 | Chgd disp on dataset
REGC5015 - CC 04C | 2004-01-14 | VIS | Bruce | Resolved | 2004-01-21
REGZ5107 - Data Exception | 2004-01-14 | VIS | Jack | Resolved | 2004-01-15 | Report only
REGZ5103 - CC16 on Sort & Data Exception | 2004-01-15 | VIS | Jack | Resolved | 2004-01-16 | Report only
REGZ5272 - CC16 | 2004-01-23 | VIS | Tom | Resolved | 2004-01-23
REGZ5272 - CC16 | 2004-01-27 | VIS | Liz | Resolved | 2004-01-27
REGZ5069 - Duplicate Dataset Name | 2004-01-29 | VIS | Liz | Resolved | 2004-01-29
REGZ5272 - CC16 | 2004-02-09 | VIS | Liz | Resolved | 2004-02-09
REGZ5213 - CC16 | 2004-02-09 | VIS | Liz | Resolved | 2004-02-09
REGC5089 - Ran too long | 2004-02-09 | VIS | Jack | Pending
REGZ5007/REGC5013/REGM5009 - CC13 | 2004-02-09 | VIS | Jack | Resolved | 2004-02-10
REGC5008 - Dataset Not Found | 2004-02-09 | VIS | Jack | Resolved | 2004-02-09 | Chg ver to PRD
REGZ5275 - CC13 | 2004-02-12 | VIS | Liz | Resolved | 2004-02-12 | Wrong CC
REGC5108 - CC16 | 2004-02-19 | VIS | Drake | Resolved | 2004-02-19
REGZ5019 - CC16 | 2004-03-01 | VIS | Linda/Dudley | Resolved | 2004-03-01
REGC5133 - Grades Sheets (minis) | 2004-03-01 | VIS | Liz/Bruce | Resolved | 2004-03-02
REGZ5239/REGC5089 - Running wrong exec | 2004-03-08 | VIS | Jack | Resolved | 2004-03-08
REGZ5285 - CC13 | 2004-03-12 | VIS | Liz | Resolved | 2004-03-12
REGZ5003 - CC13 | 2004-03-17 | VIS | Drake | Resolved | 2004-03-17 | Fixed control card
REGZ5122 - CC13 | 2004-03-19 | VIS | Drake | Resolved | 2004-03-19 | Control card LE invalid
REGZ5182 - CC13 | 2004-03-19 | VIS | Drake | Resolved | 2004-03-19 | Control card LE invalid
REGZ5122 - CC13 | 2004-03-22 | VIS | Alex | Resolved | 2004-03-22 | Control card chgd to AS (coll)
REGC5274 - Failed | 2004-03-26 | VIS | Alex | Resolved | 2004-03-26 | Missing comma
*** SAM ***
CASU80 - CC0904 | 2003-12-17 | SAM | Indexing conflict | Resolved | 2003-12-17
CASU80 - CC805 (CASITBL Failure) | 2004-01-23 | SAM | Tom/Corina | Resolved | 2004-01-23 | Rebind all IO modules
SAMU41/SAMK100A/SAMN25 - CC0100 | 2004-02-12 | SAM | Tom | Resolved | 2004-02-12
SAMU08 - CC12 | 2004-02-16 | SAM | Tom | Resolved | 2004-02-14