## Timeline Information
Project Plan for Putting Green Construction
Task # | Task Name | Duration | Start Date | End Date | Dependency | Resource | Estimated Expense
1 | Construct Subgrade | 4 | 2001-08-01 | 2001-08-05
1.1 | Remove Grass |  |  |  | 1 | Sod Cutter | 70
1.2 | Remove Soil to 16" Depth |  |  |  | 1.1
1.3 | Shape and Contour |  |  |  | 1.2
1.4 | Water and Compact |  |  |  | 1.3 | Turf Roller | 15
2 | Set Drainage Layer - 4" | 1 | 2001-08-06 | 2001-08-07 | 1.4 | Survey transit? | 192.1852
2.1 | establish grid pattern |  |  |  | 1
2.2 | groove drainage channels |  |  |  | 2.1
2.3 | Lay 1" Gravel layer |  |  |  | 2.2 | 1" of 1/4" pea gravel (4" layer)
2.4 | Lay drainage pipe |  |  |  | 2.3 | 4" perforated PVC
2.5 | Cover with remaining Gravel |  |  |  | 2.4 | 3" of 1/4" gravel
2.6 | Establish grade stakes |  |  |  | 2.5 | 3 Grade stakes
2.7 | Line level stakes for future layers |  |  |  | 2.5
3 | Coarse Sand Layer - 2" | 0.5 | 2001-08-08 | 2001-08-08 12:00 | 2.7 | 2" pure coarse sand | 92.5926
3.1 | Spread sand |  |  |  | 2.7
3.2 | rake sand to line level of 2" |  |  |  | 3.1
3.3 | roll smooth |  |  |  | 3.2 | Turf Roller | 15
4 | Root Zone Layer - 12" | 1 | 2001-08-09 | 2001-08-10 | 3.3 | Medium/fine sand | 222.2222
4.1 | Mix 75% Sand / 25% Peat |  |  |  | 3.3 | Organic Peat
4.2 | Spread root zone layer to 12" |  |  |  | 4.1 | Mixer | 70
4.3 | smooth, wet and roll to perfection |  |  |  | 4.2
5 | Planting | 1 | 2001-08-10 | 2001-08-11 | 4.3
5.1 | Apply Starter fertilizer |  |  |  | 4.3 | 10-20-20 mix
5.3 | Rake into top 3" layer of root zone and surrounding area |  |  |  | 5.1 | Seed | 25
[6 empty] | Estimated total cost | 702
Formulas:
End Date = +[Start Date]+[Duration]

## Material Calculator
Total Putting Area (sqft) | 600
Layer | Depth ("'s) | Mixture | Yards Required | Cost Per Yard | Total Cost
Subgrade | 0 | 100% | 0 | 20 | 0
Drainage | 4 | 100% | 7.4074 | 25 | 185.1852
Intermediate | 0 | 100% | 0 | 25 | 0
Coarse Sand | 2 | 100% | 3.7037 | 25 | 92.5926
Root Zone
Medium/Fine Sand | 12 | 75% | 16.6667 | 10 | 166.6667
Organic Pete Moss | 12 | 25% | 5.5556 | 10 | 55.5556
4" Drainage Pipe (Lin ft) | 100 |  | n/a | 0.07 | 7
Seed (lbs) | 1lb per 1000 sqft |  |  |  | 25
532
Instructions:
Fill in the required information in the blue cells, the worksheet will calcuate the rest for you
4" PVC Drainage pipe will run about $2 per 10ft

## TimelineWizardData (hidden)
C:\PROGRAM FILES\VISIO\SOLUTIONS\BUSINESS DIAGRAM\Project Timeline Wizard.exe