## Weekly SUS Telecon
Weekly SUS Meeting
Agenda & Summary Notes from January 13, 2004
Every Tuesday at 9am Pacific/Noon Eastern/5pm Glasgow
MEETING AGENDA
1 | Review of action items
2 | Sapphire/fused silica downselect
3 | 10 cm flats on test masses, just in the center of the barrel. See |  |  |  | http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/PeterFritschel_on_mirror_flats.pdf
4 | Wire bending point. See |  |  | http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/WireBendingPoint_Justin.pdf
5 | and also see |  | http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/WireBendingPoint_Phil.pdf
6 | Blade Test Facility
7 | Suspension modeling - MATLAB and Mathematica
Attendees
1 | Calum, Helena, Mark, Jay, Eric Black, Dennis, Janeen | [7 empty] | CIT
2 | Caroline, Mike P, Ken, Russell | [7 empty] | Glasgow
3 | Norna | [7 empty] | Standford
4 | Justin, Ian | [7 empty] | RAL
5 | David | [7 empty] | MIT
6 | Luke and Lonnie Houck | [7 empty] | Florida
7 | [8 empty] | Birmingham
8 | Carol , Doug | [7 empty] | LHO
SUMMARY NOTES AND ACTIONS FROM PREVIOUS MEETINGS
1 | Document Updates
ACTION | M000202 Development Plan |  |  | Dennis said that discussions with Justin will facilitate a development plan. Within a week or |  |  |  |  | Dennis | ASAP | High
two there should be a new development plan or memorandum of understanding
ACTION | T000053 Universal SUS DRD |  |  | Again, Mark's been working on eddy current damping stuff |  |  |  |  | Mark | 2003-11-18 | High
ACTION | T010007 SUS DRD | [7 empty] | Mark | 2003-11-18 | High
ACTION | E000037 Configuration Control | [7 empty] | Dennis | ASAP | High
2 | Structure Resonance Requirements
ACTION | Dennis/Systems to provide direction | [7 empty] | Systems | Oct 1st | High
DECISION | Suspension designs shall have a 1st mode resonance of 150 Hz or greater.
3 | Actual hanging mass for all suspensions
ACTION | Dennis will finalize by Oct 1st the seismic payload which will include contingency. | [7 empty] | Dennis/SEI | Oct 1st | High
4 | Length of quads and their proposed installation at LASTI
ACTION | Norna will look at the shorter ITM and ETM. | [7 empty] | Norna | 2003-02-01 | Medium
ACTION | The suspension team will have a more advanced design on aspects of the quad that matter to the SUS team by Feb 1st | [7 empty] | SUS Team | 2003-02-01 | Medium
5 | Blade Matching |  | See Justin's email from Oct 29th
ACTION | Calum and Mike P. have agreed to provide Justin some history of the cost of the GEO blades | [6 empty] | DONE - Justin has all he needs. | Calum/Mike P. | 2003-12-31 | Medium
ACTION | Mark will provide the calculations that Justin asked for in his e-mail on Oct 29th | [5 empty] | Mark hopes to get this done in a day or 2. |  | Mark | 2003-12-31 | Medium
6 | Electrostatic Charging
ACTION | Formulate a research plan to address the concern about electrostatic charging in suspensions and how to deal with it. | [7 empty] | Gregg/Helena | March '04 | Medium
7 | Suspension Modeling - MATLAB and Mathematica
Mark's been doing modeling of eddy current damping for triples and quads. If you put an ECD in line with the center of the optic, you get good performance,
however, if you offset the ECD from the optic centerline the performance degrades. If ECDs are placed symmetrically around the optic center you get
good performance. They've isolated a number of sources of confusion.
8 | Osem Development
There will be a meeting on osem development in Birmingham on February 4th.
Justin reported that the purpose of the meeting is to look at the development work and decide which approach should be pursued.
Most likely the decision will be to pick a promising approach and then a good back-up. Dennis said that this meeting sounds like a conceptual design review,
as we define it in LIGO. There will be no PPARC participation in the review - it will be very technical in nature. Dennis said that he' d like some documentation
to review prior to the meeting if it is a conceptual design review. Carol would like a formal review with a review board. Dennis said that membership on the review
board will include LSC folks along with LIGO people. Dennis said that Peter Fritschel, as the Advanced LIGO Chief Scientist, should iterate with Birmingham
on documentation for the review. Ken Strain said that he sees this meeting as a preliminary meeting to the conceptual design review. A review would be
subsequent to this. The Feb 4th meeting will make recommendations to LIGO.
ACTION | Carol will plan a review committee | [7 empty] | Carol | Feb | High
ACTION | Justin will report on when the conceptual design review will be held. | [7 empty] | Justin | Feb | High
9 | Blade Processes - creating and adopting a plan.
Justin, Mike Plissi, Calum and Norna agreed to form a Blade Committee. Their goal is to look into the different processes - heat treat
at 480C for 4 hours or 435C for 100 hours, constrain blades during heat treatment, inert gas during heat treatment, weighing blades
down for a week and baking the blades for a week, etc. - and create a maraging steel blade process spec. for Advanced LIGO blades.
ACTION | Blade Committee to create blade process spec. | [7 empty] | Blade Comm | PDR | Low
The factor of safety on the load must be revisited
ACTION | Set up first meeting for the Blade Committee | [7 empty] | Blade Comm | Feb 1st | High
10 | Sapphire/fused silica dowselect date implications
Norna broke down the issue into four categories: mechanical, thermal, electronics and scheduling.
Mechanical - some detail designs, for example, tablecloths
Thermal - no heavy glass experiments if fused silica
Electronics - gold coating for reaction masses for noise prototypes
Scheduling Issue - Justin said that there's no particular reason to keep to a date, but letting it slip is cumulative. He agrees with Ken; no strong
objections. Caroline said that she needs to check something but her feeling is that it shouldn't affect anything. Gregg said that they want to
make more Q measursements for silica. They don't have confidence in measurements scale and geometry. David mentioned TNI's problem
with sapphire coatings and the hopes that new coatings can be tested in April. Gregg says that a couple of months of measurements from
TNI would be useful. Helena and Gari will review the process that TNI is planning for the sapphire coatings and provide a go/no-go. Helena
is concerned about roughness if etching process is used to remove bad coating.
Jim mentioned maybe going with sapphire ETMs and leave the downselect for the ITMs. David said that the materials would most likely be the
same for the ETMs and ITMs. Justin said that we should have maximum commonality of design. Norna asked if David will try to pin down a date
for the downselect and David responded, yes. David said that we should plan for money coming in October 2005 for FY06. We should know
more by Dec 2004 from Congress. David said that the key to budget issues is to provide flexibility in emergency issues.
David will make both dates known - decision on whether to push out downselect and when new downselect will be. Janeen suggests David
David consider making January the cutoff for a decision on whether to push out the downselect and consider making the end of June the
date for the actual downselect decision.
ACTION | David to determine if downselect of sapphire/fused silica will be pushed out, and when it will be pushed out to. | [7 empty] | David | 2003-01-30 | High
ACTION | Norna will send around an e-mail about implications to a delay in the downselect. She needs a proposed new date from David.
| Implications include underutilized money or labor put on hold. | [7 empty] | Norna | 2003-01-30 | High
SUMMARY NOTES AND ACTIONS FROM THIS MEETING
11 | 10 cm long flats on test masses, just in the center of the barrel. See |  |  |  |  | http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/PeterFritschel_on_mirror_flats.pdf
There is some diffraction loss due to the flats if they extend the width of the optic out to the faces. Peter suggested making the flats inside of the OD of the optic - as a cutout on the sides.
Helena said that this configuration would be very, very expensive and would make bonding ears and welding fibers very difficult.
ACTION | COC (Bill Kells) will make the loss calculation for a 10cm long flat. This is an action from the COC CDR. | [7 empty] | COC/Bill Kells | April | High
12 | Wire Bending Points. See |  |  | http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/WireBendingPoint_Justin.pdf
| Also see | http://www.ligo.caltech.edu/~ctorrie/SUS_MEETING/daylinks/WireBendingPoint_Phil.pdf
Justin will send an e-mail of document detailing derivation.
13 | Blade Test Facility
Ian provided a summary of last week's meeting. A prototype is being made. Ian's started to do some work designing a wire clamp.
They're starting with the blade geometry detailed in Norna's conceptual design document.
Janeen reported that there was a glitch in the deliver of the maraging steel to the machine shop for cutting. She still hopes
to mail out the material by Tuesday of next week. They will use the blade specifiction currently in place, as opposed to waiting for a new one.
RAL has a furnace so rework can be accomplished. Ian will be writing a design support document, Justin reported, but said that Ian
hadn't started it yet. Justin estimates that the blade test facility should be done in about 2 months or so.
Agenda items for next meeting, January 13, 2003
1) Review of action items
2) Sapphire/fused silica downselect
3) MC installation test at LASTI in May
4) Blade clamping [creep analysis]
5) Blade Test Facility
6) Suspension modeling - MATLAB & Mathematica