## Milestone Plan
| GTPM |  | Gestion Technique des Pannes Majeures |  |  |  |  | Approval
Planned date | Appli | PVSS | SCM | SVV | Code | Milestone description | Date: | Report:
2001-09-15 |  |  |  |  | A1 | Development guidelines available | 2001-10-05 | Draft available - to be reviewed
2001-09-15 |  |  |  |  | A2 | Development strategy available
2001-09-17 |  |  |  |  | P1 | Configuration database for PVSS ready | 2001-09-27 | First view available for TDS data
2001-10-01 |  |  |  |  | A3 | Applications specified | 2002-03-07 | GTPM views
2001-10-22 |  |  |  |  | A4 | Application data available (TCD) | 2002-03-07 | Being specified
2001-10-09 |  |  |  |  | C1 | PVSS database configuration procedures published | 2002-03-07 | First version implemented
2001-10-09 |  |  |  |  | P2 | PVSS database configuration tools operational | 2002-03-07 | First version implemented
2001-10-12 |  |  |  |  | P3 | PVSS supervision module specified | 2002-03-07 | OK / finished
2001-11-05 |  |  |  |  | A5 | application data defined on PVSS | 2002-03-07 | In progress - as GTPM data becomes available
2001-10-10 |  |  |  |  | A6 | GUI library available for first application development | 2002-03-07 | Started
2001-11-01 |  |  |  |  | V1 | Control room op. environment defined | 2002-03-07 | Defined,first panel ready to be installed
2001-11-01 |  |  |  |  | V2 | SIL1 requirements defined | 2002-01-10 | Can be started based on architecture diagram
2001-11-05 |  |  |  |  | P4 | PVSS supervision module development decided | 2001-12-13 | In/house development under way
2001-11-15 |  |  |  |  | V3 | SVVP published | 2002-01-10 | Waiting for TIM URD planned for next week
2001-12-03 |  |  |  |  | P5 | PVSS supervision module available | 2002-03-07 | Test version released
2001-12-03 |  |  |  |  | C2 | SCMP published | 2001-10-25 | EDMS and Razor entries made - SCMP doc not available
2001-12-04 |  |  |  |  | P6 | System set up for operation | 2002-03-07 | linux servers 90% operational - software distribution in progress
2001-12-07 |  |  |  |  | V4 | System tests defined
2001-12-21 |  |  |  |  | V5 | System tests completed
2001-12-07 |  |  |  |  | A7 | Application tests defined
2001-12-21 |  |  |  |  | A8 | Application delivered
2002-01-14 |  |  |  |  | P7 | System running application data
2002-02-01 |  |  |  |  | A9 | Application in operation
2002-02-02 |  |  |  |  | P8 | PVSS pilot system in operation
2002-01-21 | local plcs delivering data
A4
D1
A1
C1
C
C1
A2
A3
A2
P1
A3
A4
P3
C1
P2
A5
A6
V1
V2
V3
P5
C2
P6
V5
V4
A8
P7
P8
A7
P4
A1
A9

## Responsibility Chart
Milestone: | [16 empty] | x execute the work D takes decision solely d takes decision jointly P manages progress T provides tuition on the job I must b | Project sponsors | Project leader | ETM | GTD | Scada Application Support Group | ST desktop support | Equipment group | TCR | Josep | Herve | DB pool | Roberto | Jan | Frederic | Peter
Work content Days | Start Date | Period length : 1 week | [12 empty] | Compl. Date
[16 empty] | Version 1.0 | Approved by
Week
|  | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 |  | Activity
[16 empty] | A1 | Development guidelines available |  | P |  |  | X
[16 empty] | A2 | Development strategy available | [12 empty] | x |  | x
[16 empty] | P1 | Configuration database for PVSS ready | [10 empty] | xP |  | x
[16 empty] | A3 | Applications specified | [6 empty] | x | xP
[16 empty] | A4 | Application data available (TCD) | [6 empty] | x | xP |  |  | x
[16 empty] | C1 | PVSS database configuration procedures published | [10 empty] | xP | x | x
[16 empty] | P2 | PVSS database configuration tools operational | [10 empty] | xP |  | x
[16 empty] | P3 | PVSS supervision module specified |  | x |  |  | I |  |  |  |  | x |  | x |  |  | xP
[16 empty] | A5 | application data defined on PVSS |  |  |  | x | [6 empty] | xP
[16 empty] | A6 | GUI library available for first application development | [7 empty] | x | x |  |  |  | x |  | xP
[16 empty] | V1 | Control room op. environment defined |  | x | [5 empty] | x | [6 empty] | xP
[16 empty] | V2 | SIL1 requirements defined |  | x | [9 empty] | xP
[16 empty] | P4 | PVSS supervision module development decided |  | d |  |  | A
[16 empty] | V3 | SVVP published | [11 empty] | xP
[16 empty] | P5 | PVSS supervision module available |  |  | ? | ? |  |  |  |  | ? | x? |  |  | ? |  | P
[16 empty] | C2 | SCMP published | [11 empty] | xP
[16 empty] | P6 | System set up for operation | [5 empty] | x |  |  | x |  | x | x | x | x | xP
[16 empty] | V4 | System tests defined |  | xP | T |  |  |  |  | A | I |  | I | x |  | I | x
[16 empty] | V5 | System tests completed |  | xP | [5 empty] | x | x |  | x | x |  | x | x
[16 empty] | A7 | Application tests defined |  | P |  |  |  |  | x | x | [5 empty] | x | x
[16 empty] | A8 | Application delivered |  | P |  | ? |  |  |  | x
[16 empty] | P7 | System running application data |  | P |  | x |  |  | x |  |  |  | x |  | x |  | x
[16 empty] | A9 | Application in operation |  |  |  | x | [7 empty] | x |  | x | xP
[16 empty] | P8 | PVSS pilot system in operation |  | dP |  |  |  |  | d | d |  |  | d | d |  |  | d

## Milestone Plan Meeting
Planned date | Actual date | Applications | PVSS | SCM | SVV | Code | Milestone description | Date: | Report:
A4
D1
P1
P2
P4
A1
C1
C
C1
T1
A2
A3
T4
A6
A5
D1
P3
T2
D2
PVSS pilot system in operation
1/2/2002
Analyse d'impact de l'incident
System tests completed
21/12/2001
System tests defined
7/12/2001
(Roberto)
SIL1 requirements defined
1/11/2001
(Roberto)
System set up for op.
3/12/2001
Application delivered
14/1/2002
GUI library available for first applications
8/10/2001
(Jan)
Application tests defined
14/01/2002
Development strategy available
15/09/2001
(Peter & Uwe)
Control room
op. enviroment
defined (c.f. cmx)
1/11/2001
(Peter)
PVSS pilot system in operation
1/2/2002
System tests completed
System tests defined
Acceptance tests defined
SIL1 requirements defined
System configured for op.
Application tests completed
GUI library available for first applications
Application developed
Application tests defined
Development strategy available
Control room
op. enviroment
defined (cmx)
SCMP
published
3/12/2001
(Roberto)
SVVP
published
15/11/2001
(Roberto)
Application
specified
1/10/2001
(Mario)
Application
data received (TCD)
1/10/2001
(Mario)
Application
data defined on PVSS
8/10/2001
(Serge)
PVSS DB config tools
operational
9/10/2001
(Robin & Jan)
Config db for PVSS ready
(TDrefDB)
17/9/2001
(Robin & Serge)
PVSS DB config procedures
published
9/10/2001
(Robin & Jan)
PVSS supervision
module available
3/12/2001
PVSS supervision
module specified
1/10/2001
(Peter)
Application in operation
1/2/2002
System running appli data
14/1/2002 09:34
Application
specification
method established
PVSS supervision
module development decided
5/11/2001
(Uwe)
Development guidelines available
15/09/2001
(Peter)