## Work Schedule Jun02
Tasks | Month
| 2002 | [5 empty] | 2003
| July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
A. Study Purpose
1. Explain why the study is being conducted | bar: 2002 July
Project Initiation Meeting with Study Committee*
B. Goals and Objectives
1. Develop goals and objectives for the study | bar: 2002 Aug to 2002 Sept
2. Develop a set of principals to guide the planning process | bar: 2002 Aug
3. Develop a mission statement for the study | bar: 2002 Aug
Study Committee Meeting #1 | bar: 2002 Aug
C. Study Area Definition
1. Identify boundaries limitations of the study | bar: 2002 Sept
2. Define the Study Area | bar: 2002 Oct
Study Committee Meeting #2 | bar: 2002 Oct
D. Physical Inventory/assessment of Trolley Corridor
1. Identify corridor conversions | bar: 2002 Nov
2. Identify remnant rights-of-way | bar: 2002 Nov
3. Identify former street trackage segments | bar: 2002 Nov
Montgomery County Subcommittee Meeting #1 | bar: 2002 Nov
Bucks County Subcommittee Meeting #1 | bar: 2002 Nov
Montgomery County Public Meeting #1 | bar: 2002 Dec
Bucks County Public Meeting #1 | bar: 2002 Dec
E. Demand for potential use of trail
1. Analyze potential demand for the trail | bar: 2003 Jan to 2003 Feb
2. Define and map the primary service area for local users | bar: 2003 Jan to 2003 Feb
3. Identify trail user origindestination points within service area | bar: 2003 Jan to 2003 Feb
4. Conduct Key Person interviews (by others) | bar: 2003 Jan to 2003 Feb
Montgomery County Subcommittee Meeting #2 | bar: 2003 Feb
Bucks County Subcommittee Meeting #2 | bar: 2003 Feb
F. Alternative Trail Alignments
1. Identify alternative alignments for potential trail development | bar: 2003 Feb to 2003 Mar
Montgomery County Outreach and Education Meeting #1 (by others) | bar: 2003 Jan
Bucks County Outreach and Education Meeting #1 (by others) | bar: 2003 Jan
2. Inventory positive/negative implications of alternative segments
3. Assess need for a citizen survey (performed by the County) | bar: 2003 Feb to 2003 Mar
Montgomery County Outreach/Education Meeting #2 (by others) | bar: 2003 Feb
Bucks County Outreach/Education Meeting #2 (by others) | bar: 2003 Feb
Study Committee Meeting #3 | bar: 2003 Feb
Montgomery County Public Meeting #2a (if "not feasible") | bar: 2003 Feb
Bucks County Public Meeting #2 a (if "not feasible") | bar: 2003 Feb
G. Trail Concept Plan
1. Select a preferred trail alignment | bar: 2003 Mar to 2003 Apr
2. Prepare a Trail Concept Plan that identifies: | bar: 2003 Mar to 2003 Apr
3. Prepare conceptual designs | bar: 2003 Mar to 2003 Apr
4. Evaluate acquisition and/or easement agreements options | bar: 2003 Mar to 2003 Apr
Montgomery County Outreach/Education Meeting #2 (by others) | bar: 2003 Mar
Bucks County Outreach/Education Meeting #2 (by others) | bar: 2003 Mar
Montgomery County Subcommittee Meeting #3 | bar: 2003 Mar
Bucks County Subcommittee Meeting #3 | bar: 2003 Mar
H. Financial Feasibility
1. Assess financial implications | bar: 2003 Apr to 2003 May
2. Develop phased implementation plan | bar: 2003 Apr to 2003 May
Montgomery County Subcommittee Meeting #4 | bar: 2003 Apr
Bucks County Subcommittee Meeting #4 | bar: 2003 Apr
I. Trail Operation, maintenance and management
1. Assess funding (ownership, maintenance, management) | bar: 2003 May
Study Committee Meeting #4 | bar: 2003 May
Montgomery County Public Meeting #2b (if "feasible") | bar: 2003 Jun
Bucks County Public Meeting #2b (if "feasible") | bar: 2003 Jun
J. Conclusions and Recommendations
1. Comprehensive summary of the findings/final recommendations | bar: 2003 Jun
K. Executive Summary
1. Prepare an executive summary as a two-color brochure. | bar: 2003 Jun
Bi-Monthly Meetings with Staff Technical Committee | bar: 2002 Aug; 2002 Oct; 2002 Dec; 2003 Feb; 2003 Apr; 2003 Jun

## Short WS Jun2002
Tasks | Month
| July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
A. Study Purpose | bar: Month July
Project Initiation Meeting with Study Committee* | bar: Month July
B. Goals and Objectives | bar: Month Aug to Month Sept
Study Committee Meeting #1 | bar: Month Aug
C. Study Area Definition | bar: Month Sept to Month Oct
Montgomery County Subcommittee Meeting #1 | bar: Month Oct
Bucks County Subcommittee Meeting #1 | bar: Month Oct
D. Physical Inventory/assessment of Trolley Corridor | bar: Month Nov
Montgomery County Subcommittee Meeting #2 | bar: Month Nov
Bucks County Subcommittee Meeting #2 | bar: Month Nov
Montgomery County Public Meeting #1 | bar: Month Dec
Bucks County Public Meeting #1 | bar: Month Dec
E. Demand for potential use of trail | bar: Month Jan to Month Feb
Montgomery County Subcommittee Meeting #3 | bar: Month Feb
Bucks County Subcommittee Meeting #3 | bar: Month Feb
F. Alternative Trail Alignments | bar: Month Feb to Month Mar
Montgomery County Outreach and Education Meeting #1 (by others) | bar: Month Jan
Bucks County Outreach and Education Meeting #1 (by others) | bar: Month Jan
Montgomery County Outreach/Education Meeting #2 (by others) | bar: Month Feb
Bucks County Outreach/Education Meeting #2 (by others) | bar: Month Feb
Study Committee Meeting #2 | bar: Month Feb
Montgomery County Public Meeting #2a (if "not feasible") | bar: Month Feb
Bucks County Public Meeting #2 a (if "not feasible") | bar: Month Feb
G. Trail Concept Plan | bar: Month Mar to Month Apr
Montgomery County Outreach/Education Meeting #2 (by others) | bar: Month Mar
Bucks County Outreach/Education Meeting #2 (by others) | bar: Month Mar
Montgomery County Subcommittee Meeting #4 | bar: Month Mar
Bucks County Subcommittee Meeting #4 | bar: Month Mar
H. Financial Feasibility | bar: Month Apr to Month May
Montgomery County Subcommittee Meeting #5 | bar: Month Apr
Bucks County Subcommittee Meeting #5 | bar: Month Apr
I. Trail Operation, maintenance and management | bar: Month May
Study Committee Meeting #4\3 | bar: Month May
Montgomery County Public Meeting #2b (if "feasible") | bar: Month Jun
Bucks County Public Meeting #2b (if "feasible") | bar: Month Jun
J. Conclusions and Recommendations | bar: Month Jun
K. Executive Summary | bar: Month Jun
Bi-Monthly Meetings with Staff Technical Committee | bar: Month Aug; Month Oct; Month Dec; Month Feb; Month Apr; Month Jun

## Sheet1
Scope of Services
A. | Study Purpose
B. | Goals and Objectives
Study Committee Meeting (#1)
C. | Study Area Definition
Montgomery County Subcommittee Meeting (#1)
Bucks County Subcommittee Meeting (#1)
D. | Physical Inventory and assessment of the Trolley Corridor
Montgomery County Subcommittee Meeting (#2)
Bucks County Subcommittee Meeting (#2)
Montgomery County Public Meeting (#1)
Bucks County Public Meeting (#1)
E. | Demand for potential use of trail
Montgomery County Subcommittee Meeting (#3)
Buck County Subcommittee Meeting (#3)
F. | Alternative Trail Alignments
Study Committee Meeting (#2)
Montgomery County Public Meeting (#2a--if not feasible)
Bucks County Public Meeting (#2a--if not feasible)
G. | Trail Concept Plan
Montgomery County Subcommitte Meeting (#4)
Bucks County Subcommitte Meeting (#4)
H. | Financial Feasibility
Montgomery County Subcommitte Meeting (#5)
Bucks County Subcommitte Meeting (#5)
I. | Trail Operation, maintenance and management
Study Committee Meeting (#3)
Montgomery County Public Meeting (#2b--if feasible)
Bucks County Public Meeting (#2b--if feasible)
J. | Conclusions and Recommendations
K. | Executive Summary