## RVSM TF2 Task List
ID | Description | Start | Finish | Resource Names
1 | Task Force/1 Meeting (Tokyo) | 1998-11-18 08:00 | 1998-11-18 17:00 | RVSM Task Force
2 | ISPACG/13 (Auckland) | 1998-12-07 08:00 | 1998-12-11 17:00 | ISPACG
3 | Task Force/2 Meeting (Los Angeles) | 1999-02-01 08:00 | 1999-02-05 17:00 | RVSM Task Force
4 | Determine need for Steering Committee | 1999-02-01 08:00 | 1999-02-05 17:00 | RVSM Task Force
5 | Determine need for Sub-groups | 1999-02-01 08:00 | 1999-02-05 17:00 | RVSM Task Force
6 | Identification of Operational Need | 1998-11-18 08:00 | TBD
7 | Agree Operational Concept | 1998-11-18 08:00 | 1999-05-12 | ATC/WG, RVSM Task Force
8 | Japan to provide implementation plan | 1999-02-05 | 1999-04-30 | JCAB
9 | United States to report on Central East Pacific implementation plans | 1999-02-05 | 1999-05-12 | FAA
10 | Fiji to provide implementation plan | 1999-02-05 | 1999-04-30 | CAAF/AFL
10a | Tahiti to provide implementation plan | 1999-05-10 | TBD | SEAC
10b | Identify status of RVSM implementation for Port Moresby FIR | 1999-05-10 | 1999-08-12 | ICAO Regional Office
11 | Benefits Evaluation | 1998-11-18 08:00 | 1999-08-12
12 | Agree what simulations need to be conducted | 1998-11-18 08:00 | 1999-08-12 | RVSM Task Force
13 | Safety Assessment | 1998-11-18 08:00 | 1999-12-31
14 | Review NAT summary data (non-compliant aircraft, aberrant aircraft etc) | 1998-11-18 08:00 | 1999-05-12 | SAM/WG, RVSM Task Force
15 | Examine history of height keeping errors related to ATC clearances and assess possible RVSM impact | 1998-11-18 08:00 | 1999-12-31 | SAM/WG, RVSM Task Force
16 | Confirm RVSM risk model assumptions/parameters are consistent with Pacific airspace | 1998-11-18 08:00 | 1999-11-09 | SAM/WG, RVSM Task Force
17 | Conduct simulations to predict occupancy after RVSM implementation | 1998-11-18 08:00 | 2000-01-22 | SAM/WG, RVSM Task Force
18 | Establish monitoring goals for the Pacific | 1998-11-18 08:00 | 1999-02-05 | SAM/WG, RVSM Task Force
19 | Collect weather and turbulence data for analysis | 1998-11-18 08:00 | 1999-12-31 | SAM/WG, RVSM Task Force
19a | Re-emphasize need to comply with large height deviation reporting procedures | 1999-05-12 | Ongoing | ATC/WG, OPS/AIR/WG, RVSM Task Force
20 | Examine the RVSM permanent/temporary offset procedure and its impact on the TLS in the lateral plane | 1998-11-18 08:00 | DELETED | SAM/WG, RVSM Task Force
21 | Agree Collision Risk Models for incorporation into Guidance Material | 1998-11-18 08:00 | 1999-02-05 17:00 | SAM/WG, RVSM Task Force
22 | Establish regional policy for investigating errors | 1998-11-18 08:00 | 1999-12-31 | SAM/WG, OPS/AIR/WG, ATC/WG, RVSM Task Force
23 | Develop Policy and Procedures for investigation and identification of non-approved aircraft operating at RVSM FLs | 1998-11-18 08:00 | 2000-01-22 | SAM/WG, OPS/AIR/WG, ATC/WG, RVSM Task Force
24 | Evaluate military IFR non-fighter formation risk (e.g. 2xC17) | 1998-11-18 08:00 | 1999-11-05 | SAM/WG, RVSM Task Force
25 | Evaluate lateral path keeping accuracy versus GPS equippage | 1998-11-18 08:00 | 1999-05-12 | SAM/WG, RVSM Task Force
26 | Examine the need to conduct a safety assessment of transition areas | 1999-02-05 | 1999-05-12 | SAM/WG, RVSM Task Force
26a | Examine the need to conduct a safety assessment in aircraft moving from exclusionary to non-exclusionary airspace where RVSM is applied | 1999-05-12 | 1999-11-05 | SAM/WG, RVSM Task Force
27 | Examine the applicability of collision risk modeling to non-exclusionary airspace | 1999-02-05 | 1999-09-20 | Airservices Australia
28 | Recommend decision-making aids to support safety assessment | 1999-02-05 | 2000-01-22 | SAM/WG, RVSM Task Force
29 | Supplement document containing detailed procedures and analyses used for safety assessment | 1999-02-05 | 2000-01-22 | SAM/WG, RVSM Task Force
30 | Compare meteorological and GPS data from monitored flights between North and South Pacific | 1999-02-05 | 2000-01-22 | SAM/WG, RVSM Task Force
31 | Investigate capturing GPS height-keeping data from aircraft on-board systems | 1999-02-05 | 1999-05-12 | SAM/WG, RVSM Task Force
32 | Prepare letter requesting establishment of process for obtaining Mode C data from ATS providers | 1999-02-05 | 2000-01-22 | ICAO Regional Office
32a | Determine the overall procedure to be followed by APARMO in requesting Mode C data from monitored flights | 1999-08-12 | 2000-01-22 | ICAO Regional Office, RVSM Task Force
33 | Develop and publish user procedures for obtaining GPS monitoring | 1999-02-05 | 1999-06-15 | OPS/AIR WG, RVSM Task Force
33a | Complete safety analysis on 2NM offset procedure for wake turbulence | 1999-05-10 | 1999-08-12 | SAM/WG, OPS/AIR/WG, RVSM Task Force
33b | Assess the impact of RVSM-approved VFR aircraft operating within RVSM airspace | 1999-11-05 | 2000-01-22 | RVSM Task Force
34 | Feasibility Analysis | 1998-11-18 08:00 | 1999-08-12
35 | Examine the operational factors and workload associated with implementation | 1998-11-18 08:00 | 1999-05-12 | ATC/WG, RVSM Task Force
36 | Agree what simulations need to be conducted | 1998-11-18 08:00 | 1999-08-12 | RVSM Task Force
37 | Determination of Requirements (airborne & ground systems) | 1998-11-18 08:00 | 2000-01-22
38 | Develop a program to collect, organize and review Pacific height-keeping performance data | 1998-11-18 08:00 | 1999-05-12 | SAM/WG, RVSM Task Force
39 | Determine need and responsibility for a Pacific regional central monitoring agency | 1998-11-18 08:00 | 1999-02-05 17:00 | RVSM Task Force
40 | Identify need for additional GMUs | 1998-11-18 08:00 | 1999-02-05 17:00 | RVSM Task Force
41 | Develop plan for RVSM system performance introduction specification | 1998-11-18 08:00 | 1999-02-05 | SAM/WG, OPS/AIR/WG, RVSM Task Force
42 | Evaluate the feasibility of NAMS as a ground-based height monitoring unit | 1998-11-18 08:00 | 2000-01-22 | JCAB, SAM/WG, OPS/AIR/WG, RVSM Task Force
43 | Plan for Ground System Upgrades/modifications (if required) | 1998-11-18 08:00 | 1999-11-05
44 | States consider the impact of RVSM implementation on controller automation systems (e.g equipment suffixes) | 1998-11-18 08:00 | 1999-11-05 | States, ATC/WG
45 | Aircraft & Operator Approval Requirements | 1998-11-18 08:00 | 2000-02-24
46 | Determine operational approval process | 1998-11-18 08:00 | 1999-02-05 17:00 | OPS/AIR/WG, RVSM Task Force
47 | Publish operational approval process | 1999-02-08 08:00 | 1999-03-01 | OPS/AIR/WG, RVSM Task Force
48 | Notify States when significant changes occur to RVSM documentation | 1999-02-05 | 2000-02-24 | OPS/AIR/WG, RVSM Task Force
49 | Perform Rulemaking (if required) | 1998-11-18 08:00 | 2000-01-22
50 | Recommend State airspace regulatory documentation | 1998-11-18 08:00 | 2000-01-22 | States
51 | Perform Necessary Industry & International Co-ordination | 1998-11-18 08:00 | 2000-01-22
52 | Confirm funding arrangements for GMS | 1999-02-05 | 1999-05-12 | SAM/WG
53 | Identify agency to serve as clearing house for funds to support GMUs | 1998-11-18 08:00 | 1999-02-05 17:00 | RVSM Task Force
54 | Develop a Pacific RVSM informational campaign | 1998-11-18 08:00 | 1999-03-01 | OPS/AIR/WG, RVSM Task Force
54a | Distribute operational approval checklist and references | 1999-05-15 | 1999-06-15 | OPS/AIR/WG, RVSM Task Force
55 | Prepare a Working Paper for ATS/AIS/SAR/SG/9 | 1999-02-08 08:00 | 1999-07-12 17:00 | RVSM Task Force Chair
56 | Process Doc 7030 amendment (including /W) | 1999-02-08 08:00 | 2000-01-22 | ICAO Regional Office
57 | Publish Pacific RVSM Guidance Material (1st Edition) | 1999-01-29 08:00 | 1999-01-29 17:00 | ICAO Regional Office
58 | Develop Amendment No. 1 to Pacific RVSM Guidance Material | 1999-01-29 | 1999-05-12 | RVSM Task Force
59 | Publish Pacific RVSM Guidance Material (Amendment No. 1) | 1999-05-24 08:00 | 2000-01-22 | ICAO Regional Office
60 | Publish advance NOTAM and/or AIC Supplements | 1999-02-08 08:00 | 1999-12-15 | Tahiti
60a | Review inter-facility coordination procedures | 1999-05-10 | 1999-11-05 | States
61 | Approval of Aircraft & Operators | 1999-02-24 08:00 | 2000-01-01
62 | Revise 91-RVSM, Appendix 5, for Pacific operations | 1999-02-05 | 1999-06-01 | FAA
63 | Assess readiness | 1999-02-05 | 1999-03-31 | IATA, OPS/AIR/WG
64 | Attain 6 month approved operations readiness target of 70% | 1999-08-24 08:00 | 1999-11-05 | IATA, OPS/AIR/WG, SAM/WG
65 | Attain 1 Jan 00 approved operations readiness target of 90% | 1999-11-24 08:00 | 2000-01-01 | IATA, OPS/AIR/WG, SAM/WG
65a | Evaluate impact of 90% approval on track loading for ATC | 1999-08-10 | 1999-08-12 | ATC/WG
65b | Establish a process for determining the progress of major Pacific operators in obtaining approval | 1999-08-12 | 2000-01-22 | SAM/WG, APARMO
66 | Seminar/2 (Singapore) | 1999-03-16 08:00 | 1999-03-17 17:00 | RVSM Seminar
67 | Develop Pilot & ATC Procedures | 1998-11-18 08:00 | 2000-01-22
68 | Develop procedures for handling non-compliant aircraft (inc ferry & mntce) in ATS documentation | 1998-11-18 08:00 | 1999-05-12
68a | Draft Procedures for Aircraft Found to be Non-Compliant through GMS Monitoring | 1999-08-12 | 1999-11-05 | OPS/AIR/WG
68b | Publish Procedures for Aircraft Found to be Non-Compliant through GMS Monitoring in GM | 1999-11-05 | 2000-01-22 | RVSM Task Force
69 | Adopt a tactical offset procedure to mitigate the effects of wake turbulence | 1998-11-18 08:00 | 1999-05-12 17:00 | ATC/WG, RVSM Task Force
70 | Develop procedures to mitigate multiple TCAS traffic alerts | 1998-11-18 08:00 | 1999-05-12 | OPS/AIR/WG, RVSM Task Force
71 | Review weather and contingency procedures for applicability under RVSM | 1998-11-18 08:00 | 1999-03-01 | OPS/AIR/WG, ATC/WG, RVSM Task Force
71a | Process Doc 7030 revisions to weather and contingency procedures | 1999-05-12 | 2000-01-12 | ICAO Regional Office
72 | Publish appropriate ATC policy & procedures on RVSM website | 1999-02-05 | Ongoing | RVSM Task Force
72a | Draft sample panel for charting addressing RVSM | 1999-08-12 | 1999-12-31 | OPS/AIR/WG
73 | Review text in GM re suspension of RVSM where acft experience greater than moderate turbulence | 1999-02-05 | 1999-05-12 | ATC/WG, RVSM Task Force
74 | Identify transition areas and procedures | 1998-11-18 08:00 | 2000-01-22 | States
75 | Conduct simulations | 1998-11-18 08:00 | 2000-01-22 | States
75a | Report on simulation activity | 1999-05-10 | Ongoing | ATC/WG, RVSM Task Force
76 | Distribute letter to States and operators advocating that RVSM operators adopt TCAS V.7 | 1999-05-10 08:00 | 1999-10-01 | OPS/AIR/WG, RVSM Task Force
77 | Evaluate policy and procedures to mitigate the problem of pilots levelling at the wrong FL | 1998-11-18 08:00 | 1999-05-11 17:00 | RVSM Task Force
78 | Develop mutually acceptable ATC procedures for non-approved military acft to transit RVSM airspace | 1998-11-18 08:00 | 1999-05-12 | ATC/WG, RVSM Task Force
79 | Publish on web-site ATC procedures for non-approved military acft to transit RVSM airspace | 1999-05-12 | 1999-08-15 | OPS/AIR/WG, ATC/WG, RVSM Task Force
79a | Develop contingency procedures for dispatchers | 1999-08-12 | 1999-12-31 | OPS/AIR/WG Chair, Delta Airlines
80 | Pilot & ATC Training | 1998-11-18 08:00 | 2000-02-24
81 | Update and distribute the pilot training package for TCAS | 1998-11-18 08:00 | 1999-06-01 | OPS/AIR/WG, RVSM Task Force
81a | Conduct local RVSM training for air traffic controllers | 1999-11-05 | 2000-02-24 | States
82 | Task Force/3 Meeting (Honolulu) | 1999-05-10 08:00 | 1999-05-12 17:00 | RVSM Task Force
83 | IPACG/13 (Anchorage) | 1999-06-22 | 1999-06-25 | IPACG
84 | ATS/AIS/SAR/SG/9 (Bangkok) | 1999-07-12 08:00 | 1999-07-16 17:00
85 | Task Force/4 Meeting (Brisbane) | 1999-08-10 | 1999-08-12 | RVSM Task Force
86 | ISPACG/14 (Brisbane) | 1999-12-06 | 1999-12-10 | ISPACG
86a | IPACG/14 (Honolulu) | 2000-01-23 | 2000-01-27 | IPACG
87 | APANPIRG/10 (Bangkok) | 1999-08-30 | 1999-09-03 | APANPIRG
88 | Perform System Verificiation | 1999-06-01 08:00 | 2000-01-22
89 | Height keeping performance monitoring needed to undertake initial safety analysis | 1999-06-01 08:00 | 2000-01-22 | PARMO and SAM/WG, RVSM Task Force
89a | Provide representative traffic movement data to APARMO | 1999-05-12 | 1999-08-12 | States (other than US)
90 | Undertake initial safety analysis | 1999-09-01 | 2000-01-22 | SAM/WG, RVSM Task Force
90a | Identify means of ongoing review of gross navigational errors | 1999-05-12 | 1999-08-12 | OPS/AIR/WG, SAM/WG, RVSM Task Force
90b | Prepare/maintain regional status report detailing RVSM implementation plans | 1999-08-10 | Ongoing | RVSM Task Force
91 | Task Force/5 Meeting (Tokyo) | 1999-11-04 | 1999-11-05 | RVSM Task Force
91a | Final Implementation Decision | 1999-08-10 | 2000-01-22 | RVSM Task Force
91b | Review aircraft altitude-keeping performance and operational errors | 1999-08-10 | 2000-01-22 | SAM/WG, OPS/AIR/WG
91c | ATS State documentation complete | 1999-08-10 | 2000-01-01 | States
92 | Publish NOTAM/AIP Supplement | 1999-11-22 08:00 | 1999-11-22 | States
93 | Complete safety analysis | 1999-11-09 | 1999-12-31 | RVSM Task Force
94 | Declare Initial Operational Capability | 2000-02-24 08:00 | 2000-02-24 17:00 | APARMO and SAM/WG, RVSM Task Force
94a | Post-Implementation Follow Up Meeting (RVSM/TF/7) | 2000-04-17 | 2000-04-18 | RVSM Task Force
94b | Review application and use of wake turbulence offset procedures | 2000-02-24 | 2000-04-18 | OPS/AIR/WG
95 | Monitor System Performance | 2000-02-24 08:00 | 2001-02-23 17:00
95a | Draft Policy for Follow-On Monitoring | 1999-08-12 | 2000-04-14 | OPS/AIR/WG
96 | Declare Full Operational Capability | 2001-02-23 08:00 | 2001-02-23 17:00
96a | Task Force/5A (Honolulu) | 2000-01-20 | 2000-01-22 | RVSM Task Force
97 | RVSM Seminar/3 (Manila) - Western Pacific/South China Sea Focus | 2000-03-16 | 2000-03-17 | RVSM Task Force
98 | Task Force/6 (Location TBD) - Western Pacific/South China Sea Focus | 2000-04-10 | 2000-04-14 | RVSM Task Force
99 | Task Force/8 (Location TBD) - Western Pacific/South China Sea Focus | 2000-08-01 | 2000-08-02 | RVSM Task Force
100 | Task Force/9 (Location TBD) - Western Pacific/South China Sea Focus | 2001-01-01 | 2001-01-02 | RVSM Task Force
101 | Task Force/10 (Auckland) - Pacific Review | 2001-02-01 | 2001-02-02 | RVSM Task Force
102 | RVSM Seminar/4 (Location TBD) - Western Pacific/South China Sea Focus | 2001-02-02 | 2001-02-03 | RVSM Task Force
103 | Task Force/11 (Location TBD) - Western Pacific/South China Sea Focus | 2001-05-01 | 2001-05-02 | RVSM Task Force
104 | Task Force/12 (Location TBD) - Western Pacific/South China Sea Focus | 2001-08-01 | 2001-08-02 | RVSM Task Force
105 | Task Force/13 (Location TBD) - Western Pacific/South China Sea Focus | 2001-12-01 | 2001-12-02 | RVSM Task Force
106 | Declare Initial Operational Capability - Western Pacific/South China Sea | 2002-02-01 | 2002-02-02 | RVSM Task Force