## Sheet1
UF-TRANSITION CERTIFICATION
Checklist
Source: SUS Transition Plan Checklist as of 03/11/2002 (www.icofa.org)
Item | Trans. Plan Ref. | Status (Completed as of, Pending) | Responsible Party | Issues/Concerns | Completion Initials/Date | Review Initials/Date
ACCOUNTING AND FINANCIAL REPORTING
University Accounting and Financial Reporting System
1. Provide a letter from the University Inspector General that the system being implemented contains adequate internal controls, the implementation methodology provides adequate separation of duties and will be able to prove BOE with the data required by the Legislature. |  |  | Inspector General
Accounting Transactions
2. Provide a date certain on which the university will cease entering or accepting Journal Transger transactions within FLAIR. |  |  | Haskew/Tillett/ERP Team Member
3. Provide a date certain on which all deposits by universities to State CFO accounts will cease. |  |  | UFS-Harris/IS/Moudgil
4. Provide estimated dollar amounts for new items to be financed through the Consolidated Equipment Financing Plan of the CFO. |  |  | Purch.-Hamby
5. Establish Direct Deposit with Comerica. Provide the CFO, CEFP Section with a fax or electronic transmission that is the equivalent of a remittance advice for each payment made directly to Comerica. The information must include the payment effective date, amount and the CEFP Financing Contract Number. |  |  | Hamby/Haskew
Direct Deposit of Funds
6. Provide the CFO with appropriate direct deposit authorization forms to establish deposit for the periodic distribution of appropriated funds from BOE. |  |  | Harris/Tillett/Moudgil
7. Assumption – legislation will be adopted that allows the CFO to provide each university with Direct Deposit Authorization data for its employees and vendors at the appropriate time in the Transition Plan. |  |  | Sauls/Hamby/Burch/ERP Team Member
8. Provide the CFO with a date certain by which the University will have designated a custodian to receive and secure the electronic data to be provided by the CFO, Direct Deposit Section. |  |  | Sauls/Hamby/Burch/ERP Team Member
9. Direct Deposit disbursement transactions returned to the CFO after a university has left FLAIR in July or payroll in January will be disbursed to the payee by a check drawn on the DFS Returns Account. Only a transaction which was disbursed to the wrong party or which should not have been disbursed will be cancelled. A university will be responsible for designating by June 30, 2003 a contact in the event that an expense payment is returned. |  |  | Haskew/Sauls
TREASURY ISSUES
10. Address the action the University wants taken on investments in the Treasurer’s Investment Pool and cash in the State Treasury. Provide the University’s timeline and procedures for the liquidation of investments and cash from the State Treasury. The plan needs to address where the funds will be located after they are disbursed from the Treasury, i.e., the Treasurer’s Special Purpose Investment Account (SPIA), local bank accounts, etc. |  |  | Tillett/Kruczek
11. If the University needs to establish new SPIA accounts with the Treasury, this must be accomplished at least one month prior to the movement of funds to the SPIA account. Please address this issue in the timeline mentioned above. |  |  | Tillett/Kruczek
12. Provide a date(s) certain on which all further deposits by Universities (other than deposits to cover payrolls after the devolution) to the State Treasury will cease including clearing account transfers and letter of credit draws. |  |  | Harris/Tillett/Moudgil
13. Address the action the University wants taken on EFT transactions sent to the Treasury in error after the University has devolved. The recommended action is to credit the deposit to the University’s devolution clearing fund and then disburse the funds to the University. |  |  | Tillett/Harris
Liquidation of Investments
14. Provide a date certain by which the University will have notified the Chief Financial Officer (CFO) of the State which accounts will be remitted to the University local funds and which will be transferred to SPIA accounts. |  |  | Acct. Contr-Tillett/Ellison
ACCOUNTS PAYABLE
Voucher Processing
15. Identify a date certain to transition off of FLAIR for voucher and journal transfer processing. |  |  | Haskew/ERP Team Member
16. Identify procedures for processing IRS levies. |  |  | Haskew/ERP Team Member
17. Identify procedures for processing DOR levies. |  |  | Haskew/ERP Team Member
18. Identify the last date travel advances are to be processed by FLAIR. (It is recommended that no travel advances be processed within three months of transitioning off of FLAIR in order to allow adequate time for settling the advance.) |  |  | Haskew/ERP Team Member
19. Identify prompt payment procedures. |  |  | Haskew/ERP Team Member
20. Certify documentation that ensures the University Inspector General has reviewed the Accounts Payable functions testing of the new ERP system. |  |  | Inspector General
21. Confirm whether your ERP system can set up multiple EFTs to alleviate the problem of travel payments made during the six months after the University devolves from FLAIR but prior to devolving from payroll. |  |  | Haskew/Sauls/ERP
EDI
22. Identify whether your university processes vendor payments through invoice tracking (EDI). If your agency processes EDI invoices, answer #22, #23, and #24. |  |  | Haskew
23. Identify the last date that vendors participating in EDI invoicing will transmit invoices electronically. (This date should be at least three months prior to transition off of FLAIR to allow adequate time to process outstanding invoices.) |  |  | Haskew
24. Identify last date that all invoices will be cleared from the approval queues. (This date should be at least one month prior to transition off of FLAIR.) |  |  | Haskew/Hamby
25. Identify a date certain that all trade account records will be placed in a “D” status. (This date should be at least one month prior to transition off of FLAIR.) |  |  | Haskew/IS
Purchasing Card
26. Identify how the University plans to devolve from the State of Florida Purchasing Card (PCard) Program by indicating which option you have chosen (1, 2 or 3). The options are detailed in the Accounts Payable Devolution Team document. |  |  | Hamby/Haskew/Kruczek/ERP Team Member
27. If option 2 or 3 is chosen, provide a date certain by which the University will start a “local government/participating entity” program using the State of Florida PCard Program contract. |  |  | Hamby/Haskew/Kruczek/ERP Team Member
28. If option 2 or 3 is chosen, address whether state funds will be necessary for the University’s local account, and identify when the funds will be needed and the amount. |  |  | Haskew/Mckee/Kruczek/ERP Team Member
29. If option 2 or 3 is chosen, address whether the University intends to use the optional batch process (tape or upload) to record PCard transactions back into FLAIR and, if applicable, provide the University’s procedure for using the optional batch process. |  |  | Haskew/IS/ERP Team Member
30. The devolution from the State of Florida PCard Program requires the University PCard Administrator to close all cardholder accounts and the University corporate account in the Purchasing Card Module (PCM) by 3/31/03, for devolution fiscal year 02-03. Provide the University’s procedures and timeline for accomplishing this requirement by the specified deadline. |  |  | Hamby/Haskew/Gray
31. All PCard transactions (debits, credits, whether disapproved or disputed) must be processed for payment through the PCM by 6/19/03, for devolution fiscal year 02-03. Provide the University’s procedures and timeline for accomplishing this requirement by the specified deadline. |  |  | Haskew/Edmands
32. If you do not process and pay in full all outstanding PCard transactions by 6/19/03, for devolution fiscal year 02-03, the Comptroller’s Office will exercise its authority to settle and approve these transactions, pursuant to Section 17.03, Florida Statutes. This would involve overriding any transactions that result in a negative status. The transactions will be processed using the default account referenced on the card record. Provide the University’s procedures for avoiding negative status transactions from occurring. |  |  | Haskew/Edmands
33. Prior to the liquidation process to remove University funds from the Treasury, all PCard transactions must be paid and settled if overridden. Provide the University’s procedures and timeline for settling any applicable negative PCard transactions. |  |  | Haskew/Edmands
34. The University PCard Administrator must close all PCM records (such as: processing groups, merchant category code groups, approvers, administrative units, persons, etc) by 6/30/03, for devolution fiscal year 02-03. There is a specific sequence of events for closing these records to avoid system errors. Provide the University’s procedures and timeline for accomplishing this requirement by the specified deadline. |  |  | Hamby/Haskew/Segura
35. PCard reports in the Report Distribution System (RDS) must be stopped by 7/31/03, for devolution fiscal year 02-03. Provide the date certain by which the University will stop the PCard RDS reports. |  |  | Edmands/Segura
36. Access control to the PCM (the system function “CD”) must be removed by 6/30/03, for devolution fiscal year 02-03. Provide the University’s procedures and timeline for removing access control to CD from all applicable University users. |  |  | Edmands/Segura
PAYROLL
Payroll Processing
37. Major milestones should be identified with target dates for completion. |  |  | Miller/ERP/Sauls/IS
38. Address intent to transition employee benefits, including but not limited to Section 125 benefits. |  |  | Sauls/Miller/Meeks/Burch/Dice
39. Plan should include plans to replace or provide alternate processes for existing interfaces, including but not limited to: Deferred Comp Authorizations, Tax Shelter Authorizations, Retirement Authorizations, and Insurance Authorizations. |  |  | Sauls/Miller/Meeks/Burch/Dice
40. Identify training needs of: Information Systems Staff, tax reporting Staff, Personnel/Payroll Staff, Managers and Employees. |  |  | HR/PR/ERP/Gentry
41. Provide a statement of supported pay cycles. |  |  | PR/ERP/Miller/Sauls/IS
42. Plan should provide for staffing and implementing Tax Reporting. |  |  | PR/Sauls/Miller/ERP/IS
43. Plan should provide for staffing and implementing Collections, Garnishments, and Court Order processing. |  |  | PR/Gen Counsel/Harris/Sauls/Miller
44. Statement from university Inspector General of their intent to ensure or verify that system and processes being implemented contain adequate internal controls to provide reasonable assurance that transactions are reported accurately and have appropriate authorization. |  |  | Inspector General
45. Plan should include target dates and data sources for loading and/or inputting production data into new system, including but not limited to W-4, Collections/Garnishments, EFT, employee master data, etc. |  |  | ERP/IS/PR/HR
46. Address intent to establish contigency plans for Payroll Software, Payroll Hardware, and Fulfillment of Contract Requirements (implementation slippage). |  |  | IS/PR/ERP
47. Plans should provide for staffing and implementing Limit Montioring: Section 125, Deferred Compensation 457, and 403(b). |  |  | PR/IS/ERP/Dice/Meeks
Reporting
48. State plan or approval for independent plans must be in place for Section 125. |  |  | F&A/HR/Gen Coun
49. Address intent to provide interfaces and data feeds to vendors and agencies that currently receive reports and data from State. |  |  | ERP/IS/Miller/Willets
50. Provide target dates for testing reports and data feeds. |  |  | ERP/ISMiller/Willets
51. Plan should provide for staffing and implementing reporting and remittance of taxes. |  |  | P/R-Sauls/Miller/IS/ERP
52. Plan should provide for staffing and impementing reporting and remittance of deducted wages to recipeints of garnished/court ordered deduction of wages. |  |  | P/R-Sauls/Miller/IS/ERP/UFS
53. Address intent to establish contingency plans for reports. |  |  | ERP/IS/Sauls/Miller/Willets
Interim Payroll Processing
54. Identify the interim payroll process and any special enhancements or assistance needed from the State Payroll Office. |  |  | ERP/IS/PR/HR/Miller/Sauls
55. Address intent to handle salary adjustments and cancellations for the period after Payroll isno longer processed by BOSP but before the IRS stattute of limitations is reached. |  |  | PR/IS/ERP/Miller/Sauls
56. Identify Post-Devolution needs from BOSP, I.e., RDS reports, etc. |  |  | PR/IS/ERP/Miller/Sauls
57. Address intent to maintain clearing accounts and cash. |  |  | UAS/PR/Miller/Sauls/IS
DATE OF BOARD OF TRUSTEES’ APPROVAL
59. Provide the date of the Board of Trustees’ meeting at which it is expected final approval of the transition plan will be obtained. |  |  | Kruczek/Poppell