## Areas
| Areas |  | Sub-areas | Abbreviation
1 | Injectors
|  | 1 | Production electron injector - 2 GeV | EINJ
|  | 2 | Positron drive electron injector - 6 GeV | DINJ
|  | 3 | Positron target & capture section | PTGT
|  | 4 | Positron booster linac - 2 GeV | PBL
2 | Damping Rings
|  | 1 | Positron Pre-DR | PPDR
|  | 2 | Positron Pre- DR transfer lines | PPDRX
|  | 3 | Positron Main DR | PMDR
|  | 4 | Positron Main DR transfer lines | PMDRX
|  | 5 | Electron Main DR | EMDR
|  | 6 | Electron Main DR transfer lines | EMDRX
3 | Pre-linacs, Bunch Compression & Pre-collimation
|  | 1 | Electron BC1 | EBC1
|  | 2 | Positron BC1 | PBC1
|  | 3 | Electron Pre-linac - 10 GeV | EPL
|  | 4 | Positron Pre-linac - 10 GeV | PPL
|  | 5 | Electron BC2 | EBC2
|  | 6 | Positron BC2 | PBC2
|  | 7 | Electron Pre-collimation | EPCOL
|  | 8 | Positron Pre-collimation | PPCOL
4 | Main Linacs
|  | 1 | Electron Main Linac | EML
|  | 2 | Positron Main Linac | PML
5 | Collimation and Switches
|  | 1 | Electron Collimation | ECOL
|  | 2 | Positron Collimation | PCOL
|  | 3 | Electron Switch | ESW
|  | 4 | Positron Switch | PSW
6 | Beam Delivery to IR1
|  | 1 | Electron Big Bend | EBB1
|  | 2 | Positron Big Bend | PBB1
|  | 3 | Electron Final Focus | EFF1
|  | 4 | Positron Final Focus | PFF1
7 | Beam Delivery to IR2
|  | 1 | Electron Big Bend | EBB2
|  | 2 | Positron Big Bend | PBB2
|  | 3 | Electron Final Focus | EFF2
|  | 4 | Positron Final Focus | PFF2
8 | IR Halls
|  | 1 | Interaction Region 1 | IR1
|  | 2 | Interaction Region 2 | IR2
9 | Dump Lines
|  | 1 | Electron IR1 Dump Line | EIR1D
|  | 2 | Positron IR1 Dump Line | PIR1D
|  | 3 | Electron IR2 Dump Line | EIR2D
|  | 4 | Positron IR2 Dump Line | PIR2D

## WBS
L | E | V | E | L | [6 empty] | Index No. | Hierarchy | [10 empty] | Content Notes | Format Notes
0 | [11 empty] | Project
| 1 | [11 empty] | Categories
|  | 2 | [11 empty] | Areas
|  |  | 3 | [11 empty] | Sub-areas
|  |  |  | 4 | [11 empty] | Systems
[5 empty] | 5 | [11 empty] | Generic Subsystems
[6 empty] | 6 | [11 empty] | Specific Subsystems
[7 empty] | 7 | [11 empty] | Major components |  |  |  |  | Incl. assembly.
[8 empty] | 8 | [11 empty] | Components |  |  |  | Incl. assembly.
[9 empty] | 9 | [11 empty] | Subcomponents |  |  | Incl. ass'y and indirect mat'ls.
[10 empty] | 10 | [11 empty] | Processes (dsgn, doc, coord, reliab, proto, fab, procure, QA, assemble, install, checkout, etc.) |  | The level of work; separate labor, overhead, materials, and factory burdens.
0 | [10 empty] | - | Project
| 1 | [9 empty] | 1 |  | Beam Lines
|  | 2 | [8 empty] | 1A |  |  | Area A
|  |  | 3 | [7 empty] | 1AB |  |  |  | Sub-area B
|  |  |  | 4 | [6 empty] | 1AB1 |  |  |  |  | Vacuum chamber systems
[5 empty] | 5 | [5 empty] | 1AB11 | [5 empty] | Drift tube systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB111 | [6 empty] | Drift tube system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB1111 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB1112 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Vacuum chambers
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Chambers
[8 empty] | 8 | [11 empty] | Flanges
[8 empty] | 8 | [11 empty] | Water cooling & connections
[7 empty] | 7 | [11 empty] | Vacuum hardware
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Manifolds
[8 empty] | 8 | [11 empty] | Pumps
[8 empty] | 8 | [11 empty] | HV stingers
[8 empty] | 8 | [11 empty] | HV cables & connectors
[8 empty] | 8 | [11 empty] | Analog read-out cables & connectors
[8 empty] | 8 | [11 empty] | HV controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[7 empty] | 7 | [11 empty] | Mechanical supports
[5 empty] | 5 | [5 empty] | 1AB12 | [5 empty] | Bend chamber systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB121 | [6 empty] | Bend chamber system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB1211 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB1212 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Vacuum chambers
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Chambers
[8 empty] | 8 | [11 empty] | Flanges
[8 empty] | 8 | [11 empty] | Water cooling & connections
[7 empty] | 7 | [11 empty] | Vacuum hardware
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Manifolds
[8 empty] | 8 | [11 empty] | Pumps
[8 empty] | 8 | [11 empty] | HV stingers
[8 empty] | 8 | [11 empty] | HV cables & connectors
[8 empty] | 8 | [11 empty] | Analog read-out cables & connectors
[8 empty] | 8 | [11 empty] | HV controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[7 empty] | 7 | [11 empty] | Mechanical supports
[5 empty] | 5 | [5 empty] | 1AB13 | [5 empty] | Other vacuum chamber systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB131 | [6 empty] | Other vacuum chamber system | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 1AB2 |  |  |  |  | Magnet systems
[5 empty] | 5 | [5 empty] | 1AB21 | [5 empty] | Quadrupole systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB211 | [6 empty] | Quadrupole system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB2111 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB2112 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Magnets
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Coils
[8 empty] | 8 | [11 empty] | Cores
[8 empty] | 8 | [11 empty] | Klixons
[8 empty] | 8 | [11 empty] | Flags
[8 empty] | 8 | [11 empty] | Water cooling & connections
[7 empty] | 7 | [11 empty] | DC power
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Power supplies |  |  | Sets of N+1
[8 empty] | 8 | [11 empty] | PS Controllers
[8 empty] | 8 | [11 empty] | Transductors
[8 empty] | 8 | [11 empty] | DC connection to magnet
[8 empty] | 8 | [11 empty] | Control system interface
[8 empty] | 8 | [11 empty] | AC cables & connections
[8 empty] | 8 | [11 empty] | Water cooling & connections
[7 empty] | 7 | [11 empty] | Movers
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cams
[8 empty] | 8 | [11 empty] | Motors
[8 empty] | 8 | [11 empty] | DC cables & connections
[8 empty] | 8 | [11 empty] | Control system interface
[8 empty] | 8 | [11 empty] | AC cables & connections
[7 empty] | 7 | [11 empty] | Mechanical supports
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Stationary pedestals
[8 empty] | 8 | [11 empty] | Moveable cradles
[5 empty] | 5 | [5 empty] | 1AB22 | [5 empty] | Sextupole systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB221 | [6 empty] | Sextupole system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 1AB23 | [5 empty] | Dipole systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB231 | [6 empty] | Dipole system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 1AB24 | [5 empty] | Corrector systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB241 | [6 empty] | Corrector system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 1AB25 | [5 empty] | Solenoid systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB251 | [6 empty] | Solenoid system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 1AB26 | [5 empty] | Kicker systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB261 | [6 empty] | Kicker system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 1AB27 | [5 empty] | Other magnet systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB271 | [6 empty] | Other magnet system | [5 empty] | One type per entry; bkdn as Quads
|  |  |  | 4 | [6 empty] | 1AB3 |  |  |  |  | RF systems
[5 empty] | 5 | [5 empty] | 1AB31 | [5 empty] | Beam-RF structure systems (all types) | [5 empty] | Feeds to loads | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB311 | [6 empty] | Beam-RF structure system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB3111 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB3112 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | RF sections/cavities
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Standard cells
[8 empty] | 8 | [11 empty] | Special cells
[8 empty] | 8 | [11 empty] | Input couplers
[8 empty] | 8 | [11 empty] | High-power loads
[8 empty] | 8 | [11 empty] | Water cooling & connections
[8 empty] | 8 | [11 empty] | Attachments to strongback
[7 empty] | 7 | [11 empty] | Vacuum hardware
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Manifolds
[8 empty] | 8 | [11 empty] | Pumps
[8 empty] | 8 | [11 empty] | HV stingers
[8 empty] | 8 | [11 empty] | HV cables & connectors
[8 empty] | 8 | [11 empty] | Analog read-out cables & connectors
[8 empty] | 8 | [11 empty] | HV controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[7 empty] | 7 | [11 empty] | Mechanical supports
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Strongbacks
[7 empty] | 7 | [11 empty] | Movers
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cams
[8 empty] | 8 | [11 empty] | Motors
[8 empty] | 8 | [11 empty] | DC cables & connections
[8 empty] | 8 | [11 empty] | Control system interface
[8 empty] | 8 | [11 empty] | AC cables & connections
[5 empty] | 5 | [5 empty] | 1AB32 | [5 empty] | Waveguide systems (all types) | [5 empty] | WG valve to girder | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB321 | [6 empty] | Waveguide system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB3211 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB3212 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Microwave waveguides or components
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Waveguides
[8 empty] | 8 | [11 empty] | Microwave components
[8 empty] | 8 | [11 empty] | Water cooling & connections
[7 empty] | 7 | [11 empty] | Vacuum hardware
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Manifolds
[8 empty] | 8 | [11 empty] | Pumps
[8 empty] | 8 | [11 empty] | HV stingers
[8 empty] | 8 | [11 empty] | HV cables & connectors
[8 empty] | 8 | [11 empty] | Analog read-out cables & connectors
[8 empty] | 8 | [11 empty] | HV controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[7 empty] | 7 | [11 empty] | Mechanical supports
[5 empty] | 5 | [5 empty] | 1AB33 | [5 empty] | High Power RF Sources (all types) | [5 empty] | LLRF to combiner | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB331 | [6 empty] | High Power RF Source | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB3311 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB3312 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Klystrons
[7 empty] | 7 | [11 empty] | Klystron carriage
[7 empty] | 7 | [11 empty] | Modulators
[7 empty] | 7 | [11 empty] | Modulator high voltage
[7 empty] | 7 | [11 empty] | RF combiner
[7 empty] | 7 | [11 empty] | RF driver assembly
[7 empty] | 7 | [11 empty] | Controls & interface
[7 empty] | 7 | [11 empty] | Vacuum hardware
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Manifolds
[8 empty] | 8 | [11 empty] | Pumps
[8 empty] | 8 | [11 empty] | HV stingers
[8 empty] | 8 | [11 empty] | HV cables & connectors
[8 empty] | 8 | [11 empty] | Analog read-out cables & connectors
[8 empty] | 8 | [11 empty] | HV controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[7 empty] | 7 | [11 empty] | Modulator power supply support
[7 empty] | 7 | [11 empty] | Klystron rf support & protection
[7 empty] | 7 | [11 empty] | Modulator mounting & containment
[5 empty] | 5 | [5 empty] | 1AB34 | [5 empty] | Other RF subsystems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB341 | [6 empty] | Other RF subsystem | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB3411 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB3412 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Major components |  |  |  |  | One per entry
|  |  |  | 4 | [6 empty] | 1AB4 |  |  |  |  | Beam instrumentation systems
[5 empty] | 5 | [5 empty] | 1AB41 | [5 empty] | BPM systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB411 | [6 empty] | BPM system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4111 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4112 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | BPM devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB42 | [5 empty] | Moveable collimator systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB421 | [6 empty] | Moveable collimator system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4211 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4212 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Moveable collimator devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB43 | [5 empty] | Profile monitor systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB431 | [6 empty] | Profile monitor system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4311 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4312 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Profile monitor devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB44 | [5 empty] | Stopper or dump systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB441 | [6 empty] | Stopper or dump system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4411 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4412 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Stopper or dump devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB45 | [5 empty] | SR monitor systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB451 | [6 empty] | SR monitor system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4511 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4512 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | SR monitor devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB46 | [5 empty] | Toroid systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB461 | [6 empty] | Toroid system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4611 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4612 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Toroid devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB47 | [5 empty] | Laser wire systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB471 | [6 empty] | Laser wire system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4711 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4712 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Laser wire devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB48 | [5 empty] | RF BPM systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB481 | [6 empty] | RF BPM system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4811 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4812 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | RF BPM devices
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB49 | [5 empty] | Other instrumentation systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB491 | [6 empty] | Other instrumentation system | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB4911 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB4912 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
|  |  |  | 4 | [6 empty] | 1AB5 |  |  |  |  | Safety systems
[5 empty] | 5 | [5 empty] | 1AB51 | [5 empty] | PPS systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB511 | [6 empty] | PPS subsystem | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB5111 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB5112 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB52 | [5 empty] | BCS systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB521 | [6 empty] | BCS subsystem | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB5211 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB5212 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB53 | [5 empty] | MPS systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB531 | [6 empty] | MPS subsystem | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB5311 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB5312 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB54 | [5 empty] | Other safety systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB541 | [6 empty] | Other safety subsystem | [5 empty] | One type per entry
[7 empty] | 7 |  |  |  | 1AB5411 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB5412 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
|  |  |  | 4 | [6 empty] | 1AB6 |  |  |  |  | Particle source systems
[5 empty] | 5 | [5 empty] | 1AB61 | [5 empty] | Gun systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB611 | [6 empty] | Gun system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6111 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6112 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB62 | [5 empty] | Gun pulser systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB621 | [6 empty] | Gun pulser system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6211 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6212 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB63 | [5 empty] | Gun high voltage systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB631 | [6 empty] | Gun high voltage system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6311 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6332 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB64 | [5 empty] | Laser systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB641 | [6 empty] | Laser system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6411 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6412 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB65 | [5 empty] | Laser optical systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB651 | [6 empty] | Laser optical system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6511 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6512 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB66 | [5 empty] | Cryogenic systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB661 | [6 empty] | Cryogenic system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6611 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6612 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB67 | [5 empty] | Secondary target systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB671 | [6 empty] | Secondary target system |  |  |  |  | Positron target sys. | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6711 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6712 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
[5 empty] | 5 | [5 empty] | 1AB68 | [5 empty] | Other source systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 1AB681 | [6 empty] | Other source system | [5 empty] | One type per entry, where applicable
[7 empty] | 7 |  |  |  | 1AB6811 | [7 empty] | Inventory |  |  |  |  | 1st entry at its level
[7 empty] | 7 |  |  |  | 1AB6812 | [7 empty] | Pre-installation |  |  |  |  | 2nd entry at its level
[7 empty] | 7 | [11 empty] | Devices |  |  |  |  | One type per entry
[7 empty] | 7 | [11 empty] | Mechanical supports
[7 empty] | 7 | [11 empty] | Control & read-out
[8 empty] | 8 | [11 empty] | Inventory |  |  |  | 1st entry at its level
[8 empty] | 8 | [11 empty] | Assembly |  |  |  | 2nd entry at its level
[8 empty] | 8 | [11 empty] | Cables & connectors
[8 empty] | 8 | [11 empty] | Controllers
[8 empty] | 8 | [11 empty] | Analog read-out electronics
| 1 | [9 empty] | 2 |  | Beam-line Installation | [9 empty] | Beware-this may change!
|  | 2 | [8 empty] | 2A |  |  | Area A
|  |  | 3 | [7 empty] | 2AB |  |  |  | Sub-area B
|  |  |  | 4 | [6 empty] | 2AB1 |  |  |  |  | Vacuum chamber systems
[5 empty] | 5 | [5 empty] | 2AB11 | [5 empty] | Drift tube systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB111 | [6 empty] | Drift tube system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB12 | [5 empty] | Bend chamber systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB121 | [6 empty] | Bend chamber system | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 2AB2 |  |  |  |  | Magnet systems
[5 empty] | 5 | [5 empty] | 2AB21 | [5 empty] | Quadrupole systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB211 | [6 empty] | Quadrupole system | [5 empty] | One type per entry
[7 empty] | 7 | [11 empty] | Installation major components
[8 empty] | 8 | [11 empty] | Installation components
[9 empty] | 9 | [11 empty] | Installation subcomponents
[10 empty] | 10 | [11 empty] | Installation processes
[5 empty] | 5 | [5 empty] | 2AB22 | [5 empty] | Sextupole systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB221 | [6 empty] | Sextupole system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 2AB23 | [5 empty] | Dipole systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB231 | [6 empty] | Dipole system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 2AB24 | [5 empty] | Corrector systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB241 | [6 empty] | Corrector system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 2AB25 | [5 empty] | Solenoid systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB251 | [6 empty] | Solenoid system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 2AB26 | [5 empty] | Kicker systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB261 | [6 empty] | Kicker system | [5 empty] | One type per entry; bkdn as Quads
[5 empty] | 5 | [5 empty] | 2AB27 | [5 empty] | Other magnet systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB271 | [6 empty] | Other magnet system | [5 empty] | One type per entry; bkdn as Quads
|  |  |  | 4 | [6 empty] | 2AB3 |  |  |  |  | RF systems
[5 empty] | 5 | [5 empty] | 2AB31 | [5 empty] | Beam-RF structure systems (all types) | [5 empty] | Feeds to loads | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB311 | [6 empty] | Beam-RF structure system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB32 | [5 empty] | Waveguide systems (all types) | [5 empty] | WG valve to girder | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB321 | [6 empty] | Waveguide system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB33 | [5 empty] | High Power RF Sources (all types) | [5 empty] | LLRF to combiner | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB331 | [6 empty] | High Power RF Source | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB34 | [5 empty] | Other RF subsystems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB341 | [6 empty] | Other RF subsystem | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 2AB4 |  |  |  |  | Beam instrumentation systems
[5 empty] | 5 | [5 empty] | 2AB41 | [5 empty] | BPM systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB411 | [6 empty] | BPM system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB42 | [5 empty] | Moveable collimator systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB421 | [6 empty] | Moveable collimator system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB43 | [5 empty] | Profile monitor systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB431 | [6 empty] | Profile monitor system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB44 | [5 empty] | Stopper or dump systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB441 | [6 empty] | Stopper or dump system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB45 | [5 empty] | SR monitor systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB451 | [6 empty] | SR monitor system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB46 | [5 empty] | Toroid systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB461 | [6 empty] | Toroid system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB47 | [5 empty] | Laser wire scanner systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB471 | [6 empty] | Laser wire system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB48 | [5 empty] | RF BPM systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB481 | [6 empty] | RF BPM system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB49 | [5 empty] | Other instrumentation systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB491 | [6 empty] | Other instrumentation system | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 2AB5 |  |  |  |  | Safety systems
[5 empty] | 5 | [5 empty] | 2AB51 | [5 empty] | PPS systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB511 | [6 empty] | PPS subsystem | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB52 | [5 empty] | BCS systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB521 | [6 empty] | BCS subsystem | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB53 | [5 empty] | MPS systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB531 | [6 empty] | MPS subsystem | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 2AB54 | [5 empty] | Other safety systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB541 | [6 empty] | Other safety subsystem | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 2AB6 |  |  |  |  | Particle source systems
[5 empty] | 5 | [5 empty] | 2AB61 | [5 empty] | Gun systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB611 | [6 empty] | Gun system | [5 empty] | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB62 | [5 empty] | Gun pulser systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB621 | [6 empty] | Gun pulser system | [5 empty] | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB63 | [5 empty] | Gun high voltage systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB631 | [6 empty] | Gun high voltage system | [5 empty] | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB64 | [5 empty] | Laser systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB641 | [6 empty] | Laser system | [5 empty] | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB65 | [5 empty] | Laser optical systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB651 | [6 empty] | Laser optical system | [5 empty] | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB66 | [5 empty] | Cryogenic systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB661 | [6 empty] | Cryogenic system | [5 empty] | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB67 | [5 empty] | Secondary target systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB671 | [6 empty] | Secondary target system |  |  |  |  | Positron target sys. | One type per entry, where applicable
[5 empty] | 5 | [5 empty] | 2AB68 | [5 empty] | Other particle source systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 2AB681 | [6 empty] | Other particle source system | [5 empty] | One type per entry, where applicable
|  |  |  | 4 | [6 empty] | 2AB69 |  |  |  |  | Other beam line systems
| 1 | [9 empty] | 3 |  | Global Control System | [9 empty] | Beware-this will change!
|  | 2 | [8 empty] | 31 |  |  | - | [9 empty] | Independent of Area
|  |  | 3 | [7 empty] | 311 |  |  |  | - | [8 empty] | Independent of Sub-area
|  |  |  | 4 | [6 empty] | 3111 |  |  |  |  | Computing
|  |  |  | 4 | [6 empty] | 3112 |  |  |  |  | Communications
|  |  |  | 4 | [6 empty] | 3113 |  |  |  |  | Timing & Broadcast
|  |  |  | 4 | [6 empty] | 3114 |  |  |  |  | System Software
[11 empty] | 3115 |  |  |  |  | High-level Applications software
|  |  |  | 4 | [6 empty] | 3116 |  |  |  |  | Non-recurring Engineering
[5 empty] | 5 | [5 empty] | 31161 | [5 empty] | Support systems
[6 empty] | 6 |  |  |  |  | 311611 | [6 empty] | Vacuum systems
[7 empty] | 7 |  |  |  | 3116111 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116112 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116113 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311612 | [6 empty] | Power supply systems
[7 empty] | 7 |  |  |  | 3116111 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116112 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116113 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311613 | [6 empty] | Mover systems
[7 empty] | 7 |  |  |  | 3116131 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116132 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116133 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311614 | [6 empty] | Other support systems
[7 empty] | 7 |  |  |  | 3116141 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116142 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116143 | [7 empty] | Applications software
[5 empty] | 5 | [5 empty] | 31162 | [5 empty] | Magnet systems
[6 empty] | 6 |  |  |  |  | 311621 | [6 empty] | - | [5 empty] | Independent of specific subsystem
[7 empty] | 7 |  |  |  | 3116211 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116212 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116213 | [7 empty] | Applications software
[5 empty] | 5 | [5 empty] | 31163 | [5 empty] | RF systems
[6 empty] | 6 |  |  |  |  | 311631 | [6 empty] | - | [5 empty] | Independent of specific subsystem
[7 empty] | 7 |  |  |  | 3116311 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116312 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116313 | [7 empty] | Applications software
[5 empty] | 5 | [5 empty] | 31164 | [5 empty] | Beam instrumentation systems
[6 empty] | 6 |  |  |  |  | 311641 | [6 empty] | BPM systems
[7 empty] | 7 |  |  |  | 3116411 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116412 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116413 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311642 | [6 empty] | Moveable collimator systems
[7 empty] | 7 |  |  |  | 3116421 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116422 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116423 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311643 | [6 empty] | Profile monitor systems
[7 empty] | 7 |  |  |  | 3116431 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116432 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116433 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311644 | [6 empty] | Stopper or dump systems
[7 empty] | 7 |  |  |  | 3116441 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116442 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116443 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311645 | [6 empty] | SR monitor systems
[7 empty] | 7 |  |  |  | 3116451 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116452 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116453 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311646 | [6 empty] | Toroid systems
[7 empty] | 7 |  |  |  | 3116461 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116462 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116463 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311647 | [6 empty] | Laser wire systems
[7 empty] | 7 |  |  |  | 3116471 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116472 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116473 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311648 | [6 empty] | RF BPM systems
[7 empty] | 7 |  |  |  | 3116481 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116482 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116483 | [7 empty] | Applications software
[6 empty] | 6 |  |  |  |  | 311649 | [6 empty] | Other instrumentation systems
[7 empty] | 7 |  |  |  | 3116491 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116492 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116493 | [7 empty] | Applications software
[5 empty] | 5 | [5 empty] | 31165 | [5 empty] | Other systems
[6 empty] | 6 |  |  |  |  | 311651 | [6 empty] | -
[7 empty] | 7 |  |  |  | 3116511 | [7 empty] | Control hardware
[7 empty] | 7 |  |  |  | 3116512 | [7 empty] | Control software
[7 empty] | 7 |  |  |  | 3116513 | [7 empty] | Applications software
| 1 | [9 empty] | 4 |  | Global Safety System | [9 empty] | Beware-this will change!
|  | 2 | [8 empty] | 41 |  |  | - | [9 empty] | Independent of Area
|  |  | 3 | [7 empty] | 411 |  |  |  | - | [8 empty] | Independent of Sub-area
|  |  |  | 4 | [6 empty] | 4111 |  |  |  |  | PPS
|  |  |  | 4 | [6 empty] | 4112 |  |  |  |  | BCS
|  |  |  | 4 | [6 empty] | 4113 |  |  |  |  | MPS
|  |  |  | 4 | [6 empty] | 4114 |  |  |  |  | Other Safety Backbone Systems
| 1 | [9 empty] | 5 |  | Conventional Facilities | [9 empty] | Beware-this will change!
|  | 2 | [8 empty] | 5A |  |  | Area A
|  |  | 3 | [7 empty] | 5AB |  |  |  | Sub-area B
|  |  |  | 4 | [6 empty] | 5AB1 |  |  |  |  | Buildings
[5 empty] | 5 | [5 empty] | 5AB11 | [5 empty] | Shop buildings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB111 | [6 empty] | Shop building | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB12 | [5 empty] | Office buildings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB121 | [6 empty] | Office building | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB13 | [5 empty] | Other buildings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB131 | [6 empty] | Other building | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 5AB2 |  |  |  |  | Housings
[5 empty] | 5 | [5 empty] | 5AB21 | [5 empty] | Beam housings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB211 | [6 empty] | Beam housing | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB22 | [5 empty] | RF housings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB221 | [6 empty] | RF housing | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB23 | [5 empty] | Instrumentation housings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB231 | [6 empty] | Instrumentation housing | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB24 | [5 empty] | Electrical housings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB241 | [6 empty] | Electrical housing | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB25 | [5 empty] | Other housings (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB251 | [6 empty] | Other housing | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 5AB3 |  |  |  |  | Electrical systems
[5 empty] | 5 | [5 empty] | 5AB31 | [5 empty] | 230-kV systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB311 | [6 empty] | 230-kV system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB32 | [5 empty] | 34.5-kV systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB321 | [6 empty] | 34.5-kV system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB33 | [5 empty] | 480-V systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB331 | [6 empty] | 480-V system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB34 | [5 empty] | 240-V systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB341 | [6 empty] | 240 V system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB35 | [5 empty] | 120-V systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB351 | [6 empty] | 120 V system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB36 | [5 empty] | Other electrical systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB361 | [6 empty] | Other electrical system | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 5AB4 |  |  |  |  | Water systems
[5 empty] | 5 | [5 empty] | 5AB41 | [5 empty] | LCW systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB411 | [6 empty] | LCW system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB42 | [5 empty] | Domestic water systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB421 | [6 empty] | Domestic water system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB43 | [5 empty] | Drain systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB431 | [6 empty] | Drain system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB44 | [5 empty] | Sewage systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB441 | [6 empty] | Sewage system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB45 | [5 empty] | Irrigation systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB451 | [6 empty] | Irrigation system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB46 | [5 empty] | Other water systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB461 | [6 empty] | Other water system | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 5AB5 |  |  |  |  | Ways | [6 empty] | Roads, rails, canals, etc.
[5 empty] | 5 | [5 empty] | 5AB51 | [5 empty] | Road systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB511 | [6 empty] | Road system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB52 | [5 empty] | Rail systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB521 | [6 empty] | Rail system | [5 empty] | One type per entry
[5 empty] | 5 | [5 empty] | 5AB53 | [5 empty] | Other way systems (all types) | [6 empty] | Sum of all specific types
[6 empty] | 6 |  |  |  |  | 5AB531 | [6 empty] | Other way system | [5 empty] | One type per entry
|  |  |  | 4 | [6 empty] | 5AB6 |  |  |  |  | Other conventional systems
| 1 | [9 empty] | 6 |  | Commissioning & Pre-ops
|  | 2 | [8 empty] | 61 |  |  | Injectors | [9 empty] | See area names index
|  | 2 | [8 empty] | 62 |  |  | Damping Rings
|  | 2 | [8 empty] | 63 |  |  | Pre-linacs, Bunch Compression & Pre-collimation
|  | 2 | [8 empty] | 64 |  |  | Main Linacs
|  | 2 | [8 empty] | 65 |  |  | Collimaiton & Switches
|  | 2 | [8 empty] | 66 |  |  | Beam Delivery to IR1
|  | 2 | [8 empty] | 67 |  |  | Beam Delivery to IR2
|  | 2 | [8 empty] | 68 |  |  | IR Halls
|  | 2 | [8 empty] | 69 |  |  | Dump Lines
| 1 | [9 empty] | 7 |  | Systems Management, Engineering & Integration
|  | 2 | [8 empty] | 71 |  |  | - | [9 empty] | Independent of Area
|  |  | 3 | [7 empty] | 711 |  |  |  | - | [8 empty] | Independent of Sub-area
|  |  |  | 4 | [6 empty] | 7111 |  |  |  |  | Beam line systems
[5 empty] | 5 | [5 empty] | 71111 | [5 empty] | Vacuum chamber systems
[5 empty] | 5 | [5 empty] | 71112 | [5 empty] | Magnet systems
[5 empty] | 5 | [5 empty] | 71113 | [5 empty] | RF systems
[5 empty] | 5 | [5 empty] | 71114 | [5 empty] | Beam instrumentation systems
[5 empty] | 5 | [5 empty] | 71115 | [5 empty] | Safety systems
[5 empty] | 5 | [5 empty] | 71116 | [5 empty] | Particle source systems
[5 empty] | 5 | [5 empty] | 71117 | [5 empty] | Other beam line systems
|  |  |  | 4 | [6 empty] | 7112 |  |  |  |  | Beam-line installation systems
[5 empty] | 5 | [5 empty] | 71121 | [5 empty] | Inventory systems
[5 empty] | 5 | [5 empty] | 71122 | [5 empty] | Warehouse systems
[5 empty] | 5 | [5 empty] | 71123 | [5 empty] | Other installation systems
|  |  |  | 4 | [6 empty] | 7113 |  |  |  |  | Control system backbone systems
[5 empty] | 5 | [5 empty] | 71131 | [5 empty] | Computing
[5 empty] | 5 | [5 empty] | 71132 | [5 empty] | Communications
[5 empty] | 5 | [5 empty] | 71133 | [5 empty] | Timing & Broadcast
[5 empty] | 5 | [5 empty] | 71134 | [5 empty] | System Software
[5 empty] | 5 | [5 empty] | 71135 | [5 empty] | High-level Applications Software
[5 empty] | 5 | [5 empty] | 71136 | [5 empty] | Device Software
[5 empty] | 5 | [5 empty] | 71137 | [5 empty] | Other controls systems
|  |  |  | 4 | [6 empty] | 7114 |  |  |  |  | Safety system backbone systems
[5 empty] | 5 | [5 empty] | 71141 | [5 empty] | PPS
[5 empty] | 5 | [5 empty] | 71142 | [5 empty] | BCS
[5 empty] | 5 | [5 empty] | 71143 | [5 empty] | MPS
[5 empty] | 5 | [5 empty] | 71144 | [5 empty] | Other safety system backbone systems
|  |  |  | 4 | [6 empty] | 7115 |  |  |  |  | Conventional facilities systems
[5 empty] | 5 | [5 empty] | 71151 | [5 empty] | Buildings
[5 empty] | 5 | [5 empty] | 71152 | [5 empty] | Housings
[5 empty] | 5 | [5 empty] | 71153 | [5 empty] | Electrical Systems
[5 empty] | 5 | [5 empty] | 71154 | [5 empty] | Water Systems
[5 empty] | 5 | [5 empty] | 71155 | [5 empty] | Other conventional systems
|  |  |  | 4 | [6 empty] | 7116 |  |  |  |  | Commissioning systems
|  |  |  | 4 | [6 empty] | 7117 |  |  |  |  | Other systems
| 1 | [9 empty] | 8 |  | Area Management
|  | 2 | [8 empty] | 81 |  |  | Injectors | [9 empty] | See area names index
|  | 2 | [8 empty] | 82 |  |  | Damping Rings
|  | 2 | [8 empty] | 83 |  |  | Pre-linacs, Bunch Compression & Pre-collimation
|  | 2 | [8 empty] | 84 |  |  | Main Linacs
|  | 2 | [8 empty] | 85 |  |  | Collimaiton & Switches
|  | 2 | [8 empty] | 86 |  |  | Beam Delivery to IR1
|  | 2 | [8 empty] | 87 |  |  | Beam Delivery to IR2
|  | 2 | [8 empty] | 88 |  |  | IR Halls
|  | 2 | [8 empty] | 89 |  |  | Dump Lines
| 1 | [9 empty] | 9 |  | Project Management