## Sheet1
Action Owners
L = Lead S = Support
Sec. |  | Description | Action | Timing | AMPD | AMSR | AMO | AMIC | CO | AMSQ | OSR | BMA | OCC | ORP MGR | RL PRO | DCAA
B.1 |  | Type of Contract - Items Being Acquired | No DOE Management Actions Required
B.2 |  | Obligation and Availability of Funds | Modify contract to update obligated funds | As Required | S | S |  |  | S |  |  | L
B.3 |  | Allowability of Subcontractor Fee | Determine allowability of subcontractor fee during incurred cost audits | Annually |  |  |  |  | S |  |  | L | S |  |  | S
B.4 |  | Target Costs and Fees | Modify Table 5.1as required by equitable adjustments | As Required |  |  |  |  | L
B.5 |  | Fee Descriptions and Calculations | Determine Operational Performance Fee Criteria | TBD | L | S | S |  | S |  |  | S |  | S
B.6 |  | Changes to Target Cost, Schedule, and Fee | Negotiate and Determine Equitable Adjustments to TC, Sch. And Fee | As Required | S | S | S | S | L | S | S | S | S | S |  | S
B.7 |  | Provisional Payment of Cost Performance Fee | Determine provisional fee payments based on contractor’s Quarterly Critical Analysis Report | Quarterly | S | S | S | S | L | S | S | S | S | S
B.8 |  | Conditional Payment of Fee, Profit, or Incentives | AM's Determine Compliance with ISMS Approval Requirements and Identify Catastrophic Events. AM's provide notice to CO, who ensures CO or FDO reduces fee payments per B.8. | As Required | S | S | S | S | S | L | L | S | S | S | S
B.9 |  | Final Fee Determination | Determine Final Fee Earned | At Contract Completion | S | S | S | S | L | S | S | S | S | S |  | S
C.1 |  | Introduction | No DOE Management Actions Required
C.2 |  | Contract Approach | No DOE Management Actions Required
C.3 |  | Interactions with Waste Treatment & Immob Plant Contractor | Support Partnering process | Ongoing | L | S | S | S | S |  |  | S |  | S
C.4 |  | ESQ&H | Non-radiological Worker Safety and Health | Ongoing | [5 empty] | L | S
|  |  | Radiological, Nuclear and Process Safety | Ongoing | [5 empty] | S | L
|  |  | Quality Assurance - 830.120 | Ongoing | [5 empty] | S | L
|  |  | Product Quality Assurance - OCRWM/DOE/RW-0333P | Ongoing | S |  |  |  |  | L | S
|  |  | Environmental Protection | Ongoing | [5 empty] | L | S
C.5 | Deliverable No. | Deliverables | Action Requirements Further Described in Appendix B of This Plan
| C.5.1 | Select a Commissioning Contractor | Approval | 2001-04-15 | S | S | L | S | S | S | S | S | S | S
| 1.1 | Plan for Transition | Concurrence | 2001-02-15 | L | S | S | S | S | S | S | S | S | S
| 1.2 | Project Execution Plan | Concurrence | 4/15/2001 and update annually thereafter | L | S | S | S
| 1.3 | Project Control System Description | Concurrence | 4/15/2001 with updates as required | S | S | S | L |  |  |  | S
| 1.4 | Interface Management Procedure | Concurrence | 5/15/2001 with updates as required | S | L | S | S
| 1.5 | WTP Project Baseline | Concurrence | 4/15/2001 with annual update on 4/15 | L | S | S | S | S |  |  | S
| 1.6 | WTP Risk Assessment | Concurrence | 7/1/2001 with quarterly update | S | S | S | L | S |  |  | S
| 1.7 | Monthly Status Report | Information | 15th day of each calendar month | L | S | S | S | S | S | S | S | S | S
| 1.8 | Occurrence Reporting | Concurrence | as required | S |  |  |  |  | S | L
| 1.9 | ES&H Reporting | Concurrence | as required | S |  |  |  |  | L | S
| 1.10 | Quarterly Critical Analysis | Concurrence | quarterly | L | S | S | S | S | S | S | S | S | S
| 2.1 | Updated Research and Technology Program Plan | Concurrence | 4/15/2001 and update annually thereafter | S | L |  | S
| 2.2 | R&T Test Plans | Information | as required | S | L |  | S
| 2.3 | R&T Test Reports | Review & Comment | as required | S | L |  | S
| 2.4 | Regulatory Data Quality Objective (DQO) | Concurrence | as negotiated | S | L | S |  |  | S
| 2.5 | Operational Research Assessment | Review & Comment | 8/15/2001 and update annually thereafter | S | L | S
| 2.6 | WTP Tank Utilization Assessment | Review & Comment | 8/15/2001 and update annually thereafter | S | L | S | S
| 2.7 | Material Balance and Process Flowsheet | Review & Comment | 8/15/2001 and update annually thereafter | S | L | S | S |  | S | S
| 3.1 | Design Process | Review & Comment | 2001-02-15 | L | S | S | S |  | S | S
| 3.2 | Functional Specification | Concurrence | 5/15/2001 and update as required | S | L | L |  |  | S | S
| 3.3 | Basis of Design/Design Criteria Database | Concurrence | 5/15/2001 and update as required | L | S | S |  |  | S | S
| 3.4 | Operations Requirements Document | Concurrence | 2001-07-15 | S | S | L |  |  | S | S
| 3.5 (a) | Design Products - Subpara c (1)-(4) & (8)-(11) | Monitor | ongoing | S | L | S |  |  | S | S
| 3.5 (b) | Design Products - Subpara c (5)-(7), (12)-(17), (20) | Monitor | ongoing | L | S | S |  |  | S | S
| 3.6 | Analytical Laboratory Design Requirements | Review & Comment | 2001-09-15 | S | L | L |  |  | S | S
| 3.7 | Site Layout Drawings | Concurrence | 2001-04-15 | L | S | S |  |  | S | S
| 3.8 | Optimization Study | Concurrence | 2001-03-15 | S | L | S | S |  | S | S | S |  | S
| 3.9 | Design Overviews | Monitor | ongoing | L | S | S |  |  | S | S
| 3.1 | Design Overviews | Review & Comment | quarterly | L | S | S |  |  | S | S
| 4.1 | Construction, Procurement, and Acceptance Testing Plan | Concurrence | 5/15/2001 and update annually thereafter | L | S | S |  |  | S | S
| 4.2 | Purchasing System | Approval | as required | S |  |  |  | L
| 4.3 | Construction Bid and Work Packages | Information | as required | L | S | S |  | S | S | S
| 4.4 | Construction and Acceptance Testing Program | Concurrence | prior to start of construction | L | S | S |  |  | S | S
| 4.5 | Construction Overviews | Monitor | ongoing | L | S | S |  |  | S | S
| 5.1 | Commissioning Plan | Concurrence | 24 months prior to start of commissioning, annually thereafter | S | S | L |  |  | S | S
| 5.2 | Commissioning Review | Monitor | ongoing | S | S | L |  |  | S | S
| 5.3 | Waste Form Qualification Tests | Product Acceptance — As defined in Specification 13 | during cold commissioning | S | L | S |  |  | S | S
| 5.4 | Design Capacity Performance Tests | Concurrence | during cold commissioning | S | S | L |  |  | S | S
| 5.5 | Off-standard Operational Testing | Review & Comment | during cold commissioning | S | S | L |  |  | S | S
| 5.6 | Resultant Products from Cold Commissioning | Product Acceptance — As defined in Specification 13 | during cold commissioning |  | S | L |  |  | S | S
| 5.7 | Environmental Performance Test | Concurrence | during cold commissioning |  | S | S |  |  | L
| 5.8 | Cold Commissioning Results | Concurrence | prior to hot commissioning |  | S | L |  |  | S | S
| 5.9 | Certification of Completion of Cold Commissioning | Concurrence | when complete |  | S | L |  | S | S | S |  |  | S
| 5.1 | Certification of Readiness for Hot Operations | Concurrence | 3 months prior to hot commissioning |  | S | L |  | S | S | S |  |  | S
| 5.11 | Certification of Hot Commissioning Start | Concurrence | when complete |  | S | S |  | S | S | S |  |  | L
| 5.12 | Hot Commissioning Performance Tests | Concurrence | during hot commissioning |  | S | L |  |  | S | S
| 5.13 | Resultant Products from Hot Commissioning | Product Acceptance — As defined in Specification 13 | during hot commissioning |  | L | S |  |  | S | S
| 5.14 | Hot Commissioning Results | Concurrence | upon completion of hot commissioning |  | S | L |  |  | S | S
| 5.15 | Certification of Completion of Hot Commissioning | Concurrence | when complete |  | S | S |  | S | S | S |  |  | L
| 5.16 | Facility Turnover | Concurrence | after successful commissioning |  | S | S |  | S | S | S |  |  | L
| 6.1 | Products and Secondary Wastes Plan | Concurrence | 4/15/2001 and update annually thereafter |  | L | S
| 6.2 | Waste Form Compliance Plan | Concurrence | 7/15/2001 and update annually thereafter |  | L | S |  |  | S
| 6.3 | IHLW Qualification Documentation | Review & Comment/Concurrence | 8/1/2002 and update annually |  | L | S |  |  | S
| 6.4 | Waste Form Qualification Report | Review & Comment/Concurrence | 9/1/2002 and update annually thereafter |  | L | S |  |  | S
| 6.5 | IHLW Production Documentation | Concurrence | at time of production |  | S | L
| 6.6 | ILAW Qualification Documentation | Review & Comment/Concurrence | 2/1/2002 and update annually thereafter |  | L | S
| 6.7 | ILAW Production Documentation | Review & Comment/Concurrence | at time of production |  | S | L
| 6.8 | Entrained Solids Qualifications Documentation | Review & Comment/Concurrence | 10/1/2002 and update annually thereafter |  | L | S
| 6.9 | Entrained Solids Production Documentation | Review & Comment/Concurrence | at time of production |  | S | L
| 6.1 | Secondary Wastes Production Documentation | Review & Comment/Concurrence | at time of production |  | S | L
| 6.11 | QA Provisions Document | Concurrence | 3/1/2001 and update annually thereafter |  | S | S |  |  | L
| 7.0 | Non-radiological Worker Safety and Health | Regulatory Deliverable Approval Per Std 7 | per Standard 7.a(1) | [5 empty] | L | S
| 7.1 | Radiological, Nuclear and Process Safety | Regulatory Deliverable Approval Per Std 7 | per Table S7-1 | [6 empty] | L
| 7.2 | Quality Assurance | Approval/Regulatory Deliverable Approval Per Std 7 | 2001-04-15 | [5 empty] | L
| 7.3 | Environmental Plan | Concurrence | 3/15/2001 and update annually thereafter | S | S | S |  |  | L |  |  | S
| 7.4 | Dangerous Waste Permit Application Implementation Plan | Concurrence | 2001-03-15 | S | S | S |  |  | L |  |  | S
| 7.5 | Dangerous Waste Permit Application | Concurrence | as required | S | S | S |  |  | L |  |  | S
| 7.6 | Risk Assessment Work Plan | Concurrence | as required | S | S | S | L
| 7.7 | Notice(s) of Construction | Concurrence | 150 days prior to submission to the regulators | L |  |  |  |  | S
| 7.8 | Prevention of Significant Deterioration (PSD) Permit Application | Concurrence | 150 days prior to submission to the regulators | L |  |  |  |  | S
| 7.9 | Petition for Exemption or Exclusion for IHLW | Concurrence | 2003-12-01 |  | S |  |  |  | L
| 7.1 | Petition for a New Treatment Standard | Concurrence | 2003-08-01 |  | S |  |  |  | L
| 8.0 | Safeguards and Security | Concurrence | see Table S8-1 | [5 empty] | L
| C.9.1 | Interface Control Documents | Jointly Developed | every 6 months | S | L | S | S |  | S | S | S
| H.1 | Environmental Permit Applications | Concurrence | ongoing | [5 empty] | L
| H.2 | Litigation Management Plan | Approval | 2001-04-15 | [8 empty] | L
| H.3 | Plan for Transition to Operations | Concurrence | start of commissioning | S | S | L | S
C.6 | Standards | Standard 1 - Management Products & Controls | Manage Project Transition | Ongoing | L | S | S
|  |  | Manage LCAM critical decision process | As Required | L | S | S
|  |  | Manage Project Execution | Ongoing | L | S | S
|  |  | Ensure implementation of RPP PMP | Ongoing | L | S | S
|  |  | Provide for Compliance Reviews | As Required | S | S | S | S | L |  |  | S
|  |  | Support ICD development process and interface management | Ongoing | S | L | S | S | S |  |  | S
|  |  | Integrate WTP and TF contractors with respect to scope and schedule | Ongoing | S | S | S | L
|  |  | Develop WTP funding need projections | Ongoing | S | S | S | S | S |  |  | L
|  |  | Disposition contractor requests for contingency expenditures above the cumulative contingency utilization profile | Ongoing | L | S | S |  | S |  |  | S
|  |  | Monitor WTP contractor’s risk management activities, actions | Ongoing | S | L | S
|  |  | Manage and Disposition contractor proposed changes to WTP project baseline (scope, schedule, and/or cost) | Upon approval request by Contractor | L | S | S | S | S |  | S | S
|  |  | Review contractor status information (provided in monthly reports and quarterly critical analysis reports) and identify any potential problem areas | Monthly/ Quarterly | L | S | S | S | S |  |  | S
|  |  | Manage Occurrences and Accident Investigations | As Required | S |  | S |  |  | L
C.6 | Standards | Standard 2 - Research, Technology, and Modeling | Review, track, and/or approve contractor’s R&T program to ensure activities, test results, and application meet ORP mission, project baseline, and risk assement requirements. | Ongoing | S | L | S |  |  | S | S
|  |  | Review for acceptability proposed R&T test methodology. | Upon approval request by Contractor | S | L
|  |  | Review, track, and/or approve, as required, contractor’s characterization activities (i.e., tests, results, and proposed changes). | Upon approval request by Contractor | S | L | S |  |  | S | S
|  |  | Review, track, and/or approve, as required, contractor’s waste processing testing activities (i.e., tests, results, and proposed changes). | Upon approval request by Contractor | S | L | S |  |  | S | S
|  |  | Review, track, and/or approve, as required, contractor’s waste qualification testing activities (i.e., tests, results, and proposed changes). | Upon approval request by Contractor | S | L | S |  |  | S | S
|  |  | Review, track, and/or approve, as required, contractor’s WTP Process and Facility Modeling for operations research, utilization, and material balance and process flow and ensure configuration control on models is maintained. |  | S | L | S
|  |  | Process contractor requests for waste samples for testing | Upon request by Contractor | S | L | S
C.6 | Standards | Standard 3 - Design | Disposition contractor proposed changes to design process | Upon approval request by Contractor | L | S |  |  | S
|  |  | Disposition contractor proposed changes to design, design layout, and WTP and associated processes | Upon approval request by Contractor | L | S |  |  | S
|  |  | Disposition recommendations from optimization studies completed by contractor | Upon approval request by Contractor | S | L |  |  | S
C.6 | Standards | Standard 4 - Construction, Procurement, and Acceptance Testing | Manage Construction, Procurement, and Acceptance Testing |  | L | S | S
|  |  | Disposition contractor proposal regarding ILAW glass composition ranges |  | S | L | S |  | S
|  |  | Coordinate commissioning-related reviews by DOE oversight groups, official review teams and audit organizations |  | S | S | L |  | S | S | S
|  |  | Verify resolution of commissioning-related deficiencies identified by and recommendations made by DOE oversight groups, official review teams and audit organizations |  | S | S | L |  | S | S | S
C.6 | Standards | Standard 5 - Commissioning | Review Commssioning Plan | Upon Submittal | L | S | S |  |  |  | S
|  |  | Participate in Commissioning Review Board | When Convened | S | S | L
|  |  | Review Cold Commissioning Test Reports | Upon Submittal | L | S | S
|  |  | Reivew Hot Comissioning Test Reports | Upon Submittal | S | S | L
|  |  | Confirm Completion of Hot Commissioning | Jan. 2011 | S | S | S |  | L |  |  | S | S | S |  | S
C.6 | Standards | Standard 6 - Product Qualification, Characterization, and Certification | See |  | S | L |  |  |  | S
C.6 | Standards | Standard 7 - ESQ&H | Non-radiological Worker Safety and Health | Ongoing | [5 empty] | L | S
|  |  | Radiological, Nuclear and Process Safety | Ongoing | [5 empty] | S | L
|  |  | Quality Assurance - 830.120 | Ongoing | [5 empty] | S | L
|  |  | Product Quality Assurance - OCRWM/DOE/RW-0333P, NQA-1 | Ongoing |  | S |  |  |  | L
|  |  | Environmental Protection | Ongoing | [5 empty] | L | S
C.6 | Standards | Standard 8 - Safeguards and Security | Verify SAS Program implementation and review Standard 8 Table S8-1 deliverables | Upon Submittal | [5 empty] | L
C.7 |  | Facility Specification | Disposition contractor proposed changes to Facility Specification | Upon proposed changes by Contractor | S | L | S | S | S | S | S | S | S | S |  | S
|  |  | Disposition contractor requests to add, during aqueous washing, more than four grams of sodium per kilogram of insoluble solids received in the HLW slurry | Upon approval request by Contractor | S | L | S | S | S | S | S | S | S | S |  | S
C.8 | Operational Specs | Spec 1 - Immobilized High-Level Waste | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 2 - Immobilized Low-Activity Waste | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 3 - Entrained Solids | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 4 - Reserved | No DOE Management Actions Required
|  | Spec 5 - Reserved | No DOE Management Actions Required
|  | Spec 6 - Reserved | No DOE Management Actions Required
|  | Spec 7 - Low-Activity Waste Envelopes Definition | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 8 - High-Level Waste Envelope Definition | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 9 - Liquids or Slurries Transferred to DOE Tanks by Pipeline | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 10 - Reserved | No DOE Management Actions Required
|  | Spec 11 - Reserved | No DOE Management Actions Required
|  | Spec 12 - Number of High-Level Waste Canisters Per Batch of Waste Envelope D | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
|  | Spec 13 - Waste Product Inspection and Acceptance | Determine design specification compliance and disposition Contractor-proposed changes | Ongoing | S | L | S | S | S | S | S | S | S | S
D |  | Marking and Packaging | No DOE Management Actions Required
E |  | Inspection and Acceptance | DOE inspection and test before acceptance to ensure compliance with the terms of the contract | 2011-07-31 | L | S | S |  | S | S | S
|  |  | DOE verification of contractor’s performance of inspection and acceptance | Ongoing | L | S | S |  | S | S | S
|  |  | DOE determination of final acceptance | 2011-07-31 | S | S | S |  | S | S | S |  |  | L
F.1 |  | Period of Performance and Delivery Dates | Verify milestone compliance | At Sec F Milestone Dates | L | S | S |  | S | S | S
F.2 |  | Principal Place of Performance | No DOE Management Actions Required
F.3 | FAR 52.242-15 | Stop-Work Order (AUG 1989) - ALT I (APR 1984) | Issue and cancel Stop-Work Orders, as appropriate | As Required | S |  |  |  | L | S | S
G.4 |  | Billing Instructions | Process bi-weekly payment invoices & review prior invoice per established invoice review procedure | Bi-weekly per procedure | S |  |  |  | L |  |  | S
H.1 |  | Technical Direction | Issue COR designation letters | 2001-01-15 |  |  |  |  | L
|  |  | Perform COR Duties per authority designation letter | Ongoing | L | S | S
H.2 |  | Modification Authority | No DOE Management Actions Required
H.3 |  | Key Personnel | Enforce fee reductions and approval of key personnel replacements | As Required | S | S | S | S | L | S | S | S | S | S
H.4 |  | Small Business Subcontracting Plan | Verify compliance with Plan via SF-294 and SF-295 reporting reviews | Annually by March 31 |  |  |  |  | L
H.5 |  | Representations, Certifications, and Other Statements of the Offeror | No DOE Management Actions Required
H.6 |  | Displaced Employee Hiring Preference | Verify compliance and flowdown to subcontractors | TBD |  |  |  |  | L |  |  | S |  |  | S
H.7 |  | Implementation of Section 3161 Policy on Work Force Restructuring and Preference in Hiring | Verify compliance | TBD |  |  |  |  | L |  |  | S |  |  | S
H.8 |  | Labor Relations | Verify compliance | TBD | S |  |  |  | L |  |  | S |  |  | S
H.9 |  | Implementation of the Hanford Site Stabilization Agreement | Verify compliance and flowdown to subcontractors | TBD | S |  |  |  | L |  |  | S |  |  | S
H.10 |  | Determination of Appropriate Labor Standards | Verify compliance | TBD |  |  |  |  | L |  |  | S |  |  | S
H.11 |  | Age Discrimination in Employment | Verify compliance | TBD |  |  |  |  | L |  |  | S |  |  | S
H.12 |  | Operations and Engineering Contract Multiple Employer Pension Plan | Verify compliance | TBD |  |  |  |  | L |  |  | S |  |  | S
H.13 |  | Self-Performed Work | Verify compliance | Ongoing | S |  |  |  | L |  |  | S |  |  |  | S
H.14 |  | Payment Bonds and Performance Bonds | Verify compliance | During BMOP Review |  |  |  |  | L |  |  | S |  |  |  | S
H.15 |  | Guarantee of Performance | Verify compliance at time of award and verify financial condition of guarantor throughout the life of the contract | Annual Review Cycle Established by DCAA |  |  |  |  | L |  |  | S | S
H.16 |  | DOE Access to Contractor Management and Contract Documentation | Assure required PM functions are located in the Tri-Cities and that all major design reviews are held in the Tri-Cities | Ongoing | L |  |  |  | S
H.17 |  | Waste Treatment and Immobilization Plant Conceptual Design and Supporting Information | Assure timely and complete conceptual design transition from TFC to WTC in accordance with ORP Transition Plan | By date estalished in Deliverable 1.1 | L | S | S | S | S | S | S | S
H.18 |  | Responsible Corporate Official | No DOE Management Actions Required
H.19 |  | Assignment of Subcontracts | Direct subcontract assignments as deemed in the best interests of DOE | As Required | S |  |  |  | S |  |  |  |  | L
H.20 |  | Other Government Contractors | Verify compliance. Notify Contractor if interference occurs | As Required | L |  |  |  | S
H.21 |  | Assignment | Verify compliance and approve assignments | When requested by Contractor | S |  |  |  | L |  |  |  | S
H.22 |  | Subcontractor Environment, Safety, Quality, and Health Requirements | Verify compliance and ensure flowdown to subcontractors | TBD | L |  | S |  | S | S | S |  |  |  | S
H.23 |  | Tri-Party Agreement | Verify compliance with current and future TPA milestones | Ongoing | S | S | S |  | S | S |  |  | S | L
H.24 |  | Emergency Clause | Direct Contractor & subcontractors during declared Hanford site emergency | As Required | [9 empty] | L
H.25 |  | Shutdown Authorization | Direct shutdown or initiation of emergency response as required due to imminent hazard | As Required | L |  | L |  | S | L | L |  |  | S
H.26 |  | Environmental Permits | (a) Environmental permits - assure transfer of existing permits | TBD | L |  |  |  |  | L |  |  | S
|  |  | (b) DOE sign with Contractor as co-permittees | TBD | L |  |  |  |  | L |  |  | S
|  |  | (c) DOE sign with Contractor as co-permittees | TBD | L |  |  |  |  | L |  |  | S
|  |  | (d) Review and comment on permit applications | TBD | L |  |  |  |  | L |  |  | S
|  |  | (e) Determine cost allowability of bonds, insurance & fees | TBD | S |  |  |  | L |  |  | S |  |  |  | S
|  |  | (f) Provide copies of technical information to Contractor | TBD | L
|  |  | (g) Provide DOE certification statement to Contractor | TBD | L | [7 empty] | L
|  |  | (h) Authorize Contractor to conduct negotiations with regulatory agencies | TBD | S |  |  |  | S | S |  |  | S | L
|  |  | (I) Assume responsibility for assigned permits at contract termination or expiration | TBD | S |  |  |  | L | S |  |  | S | S
H.27 |  | Contractor Acceptance of Notices of Violation or Alleged Violations, Fines, and Penalties | Determine allowability of cost and penalties and verify compliance with reporting requirements | As Required | L |  |  |  | S | S |  | S | S | S |  | S
H.28 |  | Allocation of Responsibilities for Contractor Environmental Compliance Activities | Ensure proper allocation of fines | As Required | L |  |  |  | S | S |  | S | S | S |  | S
H.29 |  | Hazardous Materials | Verify submittal of MSDS | Ongoing | L |  | S |  |  | S
H.30 |  | Preservation of Antiquities and Land Areas | No DOE Management Actions Required
H.31 |  | Information | Verify compliance | Ongoing |  |  |  |  | L
H.32 |  | Costs Associated with Whistleblower Actions | Determine allowability of cost | Annual Review Cycle Established by DCAA | S |  |  |  | S |  |  | L | S |  |  | S
H.33 |  | Litigation Management Plan | Review Plan | 2001-03-11 | [8 empty] | L
H.34 |  | Alternative Dispute Resolution | (a)(1) Participate in partnering workshop | 2001-02-11 | S | S | S | S | L | S | S | S | S | S
|  |  | (a)(2) Agree to "standing neutral" | 2001-02-11 | S |  |  |  | L |  |  |  | S | S
|  |  | (b) Resolve disputes | As Required | S |  |  |  | L |  |  |  | S | S
H.35 |  | Lobbying Restriction (Energy and Water Development Appropriation Act, 2000) | No DOE Management Actions Required
H.36 |  | Cooperation During Transition to Operations | Review Contractor Transition Plan and determine compliance with Clause requirements | After Commissioning | S |  | L |  | S
H.37 |  | Advance Understanding on Costs | Negotiated Advance Understanding on Particular Items of Cost | 2001-02-11 | S | S | S | S | L |  |  | S | S
H.38 |  | Additional Rights in Inventions and Technical Data | Assure Contractor assignment of permits, authorizations, leases, and any licenses in any third party intellectual property. | As Required | S |  |  |  | S |  |  |  | L
H.39 |  | Patent Indemnity - Subcontracts | Verify compliance during Contractor purchasing system review | As Required | S |  |  |  | S |  |  |  | L
H.40 |  | Government-Furnished Property and Government-Furnished Equipment | No DOE Management Actions Required
H.41 |  | Third Parties | No DOE Management Actions Required
I.1 | FAR 52.202-1 | Definitions (OCT 1995) | No DOE Management Actions Required
I.2 | FAR 52.203-3 | Gratuities (APR 1984) | No DOE Management Actions Required
I.3 | FAR 52.203-5 | Covenant Against Contingent Fees (APR 1984) | No DOE Management Actions Required
I.4 | FAR 52.203-6 | Restrictions on Subcontractor Sales to the Government (JUL 1995) | No DOE Management Actions Required
I.5 | FAR 52.203-7 | Anti-Kickback Procedures (JUL 1995) | No DOE Management Actions Required
I.6 | FAR 52.203-8 | Cancellation, Rescission, and Recovery of Funds for Illegal or Improper Activity (JAN 1997) | No DOE Management Actions Required
I.7 | FAR 52.203-10 | Price or Fee Adjustment for Illegal or Improper Activity (JAN 1997) | No DOE Management Actions Required
I.8 | FAR 52.203-12 | Limitations on Payments to Influence Certain Federal Transactions (JUN 1997) | No DOE Management Actions Required
I.9 | FAR 52.204-4 | Printing/Copying Double-Sided on Recycled Paper (JUN 1996) | No DOE Management Actions Required
I.10 | FAR 52.209-6 | Protecting the Government’s Interest When Subcontracting with Contractors Debarred, Suspended or Proposed for Debarment (JUL 1995) | No DOE Management Actions Required
I.11 | FAR 52.215-2 | Audit and Records – Negotiation (JUN 1999) | No DOE Management Actions Required
I.12 | FAR 52.215-8 | Order of Precedence – Uniform Contract Format (OCT 1997) | No DOE Management Actions Required
I.13 | FAR 52.215-11 | Price Reduction for Defective Cost or Pricing Data–Modifications (OCT 1997) | Perform Cost/Price Analysis on Contractor modification proposals and determine Defective Pricing Compliance | As Required | S |  |  |  | L |  |  | S | S |  |  | S
I.14 | FAR 52.215-13 | Subcontractor Cost or Pricing Data–Modifications (OCT 1997) | Perform Cost/Price Analysis on Contractor modification proposals and determine Defective Pricing Compliance | As Required | S |  |  |  | L |  |  | S | S |  |  | S
I.15 | FAR 52.215-15 | Pension Adjustments and Asset Reversions (DEC 1998) | Ensure flowdown to subcontractors during Contractor purchasing system review | As Required |  |  |  |  | L |  |  | S | S |  |  | S
I.16 | FAR 52.215-17 | Waiver of Facilities Capital Cost of Money (OCT 1997) | Action completed by deleting this clause in Modification No. M019 | As Required |  |  |  |  | L |  |  | S | S |  |  | S
I.17 | FAR 52.215-18 | Reversion or Adjustment of Plans for Postretirement Benefits (PRB) Other Than Pensions (OCT 1997) | Ensure receipt of credit for pension fund asset reversions and ensure flowdown to subcontractors during Contractor purchasing system review | As Required |  |  |  |  | L |  |  | S | S |  |  | S
I.18 | FAR 52.215-19 | Notification of Ownership Changes (OCT 1997) | Verify compliance | As Required |  |  |  |  | L |  |  |  | S |  |  | S
I.19 | FAR 52.216-7 | Allowable Cost and Payment (MAR 2000) | Execute payment, establish billing rates, and perform audits as required | As Required | S |  |  |  | L |  |  | S | S |  |  | S
| FAR 52.215-20 | Requirements for Cost or Pricing Data or Information Other Than Cost or Pricing Data (OCT 1997) | Perform Cost/Price Analysis on Contractor modification proposals and determine Defective Pricing Compliance | As Required | S |  |  |  | L |  |  | S | S |  |  | S
I.20 | FAR 52.216-10 | Incentive Fee (MAR 1997) | Make final fee earnings determination | At Contract Completion | S | S |  | S | L | S | S | S | S | S |  | S
I.21 | FAR 52-219-4 | Notice of Price Evaluation Preference for HUBZone Small Business Concerns (JAN 1999) | No DOE Management Actions Required
I.22 | FAR 52.219-8 | Utilization of Small Business Concerns (OCT 1999) | Requirement compliance determined through Subcontracting Plan review and reporting under FAR 52.219-9. | Semiannually by April 30 and Oct 31 |  |  |  |  | L
I.23 | FAR 52.219-9 | Small Business Subcontracting Plan (OCT 1999) – Alternate II (JAN 1999) | Approve revisions Small Business Subcontracting Plan and review SF-294 and SF-295 submittals | Semiannually by April 30 and Oct 31 |  |  |  |  | L
I.24 | FAR 52.219-10 | Incentive Subcontracting Program (FEB 2000) | Determine incentive percentage for exceeded approved small business goals | 2000-04-30 |  |  |  |  | L
I.25 | FAR 52.219-16 | Liquidated Damages – Subcontracting Plan (JAN 1999) | Assess Liquidated Damages for specified Small Business Subcontracting Plan failures | As Required |  |  |  |  | L
I.26 | FAR 52.219-23 | Notice of Price Evaluation Adjustment for Small Disadvantaged Business Concerns (OCT 1999) | No DOE Management Actions Required
I.27 | FAR 52.219-25 | Small Disadvantaged Business Participation Program – Disadvantaged Status and Reporting (OCT 1999) | Obtain Optional Form 312 | At Contract Completion |  |  |  |  | L
I.28 | FAR 52.219-26 | Small Disadvantaged Business Participation Program – Incentive Subcontracting (FEB 2000) | Determine incentive percentage for exceeded approved small disadvantaged business targets | 2000-04-30 |  |  |  |  | L
I.29 | FAR 52.222-1 | Notice to the Government of Labor Disputes (FEB 1997) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.30 | FAR 52.222-3 | Convict Labor (AUG 1996) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.31 | FAR 52.222-4 | Contract Work Hours and Safety Standards Act – Overtime Compensation (JUL 1995) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.32 | FAR 52.222-6 | Davis-Bacon Act (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.33 | FAR 52.222-7 | Withholding of Funds (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.34 | FAR 52.222-8 | Payrolls and Basic Records (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.35 | FAR 52.222-9 | Apprentices and Trainees (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.36 | FAR 52.222-10 | Compliance with Copeland Act Requirements (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.37 | FAR 52.222-11 | Subcontracts (Labor Standards) (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.38 | FAR 52.222-12 | Contract Termination – Debarment (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.39 | FAR 52.222-13 | Compliance with Davis-Bacon and Related Act Regulations (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.40 | FAR 52.222-14 | Disputes Concerning Labor Standards (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.41 | FAR 52.222-15 | Certification of Eligibility (FEB 1988) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.42 | FAR 52.222-21 | Prohibition of Segregated Facilities (FEB 1999) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.43 | FAR 52.222-26 | Equal Opportunity (FEB 1999) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.44 | FAR 52.222-27 | Affirmative Action Compliance Requirements for Construction (FEB 1999) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.45 | FAR 52.222-35 | Affirmative Action for Disabled Veterans and Veterans of the Vietnam Era (APR 1998) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.46 | FAR 52.222-36 | Affirmative Action for Workers with Disabilities (JUN 1998) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.47 | FAR 52.222-37 | Employment Reports on Disabled Veterans and Veterans of the Vietnam Era (JAN 1995) | Labor Compliance | Ongoing |  |  |  |  | S |  |  | S | S |  | L
I.48 | FAR 52.223-3 | Hazardous Material Identification and Material Safety Data (JAN 1997) – Alternate I (JUL 1995) | Verify compliance with MSDS requirements of this clause | As Required | S |  |  |  | S | L
I.49 | FAR 52.223-5 | Pollution Prevention and Right-to-Know Information (APR 1998) | Verify compliance with notice and MSDS requirements of this clause | As Required | S |  |  |  | S | L
I.50 | FAR 52.223-6 | Drug-Free Workplace (JAN 1997) | Verify Compliance | Ongoing |  |  |  |  | L
I.51 | FAR 52.223-14 | Toxic Chemical Release Reporting (OCT 1996) | Verify compliance with annual report filing requirement | Annually on July 1 | L |  |  |  | S | S | S
I.52 | FAR 52.224-1 | Privacy Act Notification (APR 1984) | Verify Compliance | Ongoing |  |  |  |  | S |  |  |  | L
I.53 | FAR 52.224-2 | Privacy Act (APR 1984) | Verify Compliance | Ongoing |  |  |  |  | S |  |  |  | L
I.54 | FAR 52.225-5 | Trade Agreements (APR 2000) | Verify Compliance | Ongoing |  |  |  |  | S |  |  |  | L
I.55 | FAR 52.225-11 | Buy American Act – Balance of Payments Program-Construction Materials under Trade Agreements (FEB 2000) | Verify Compliance | Ongoing |  |  |  |  | L
I.56 | FAR 52.225-13 | Restrictions on Certain Foreign Purchase (JUL 2000) | Verify Compliance | Ongoing |  |  |  |  | L
I.57 | FAR 52.226-1 | Utilization of Indian Organizations and Indian-Owned Economic Enterprises (FEB 2000) | Determine equitable adjustment amount to the target cost and make the appropriate incentive fee payment to the Contractor upon subcontract award to Indian-owned enterprise | As Required |  |  |  |  | L |  |  | S
I.58 | FAR 52.227-1 | Authorization and Consent (JUL 1995) | No DOE Management Actions Required
I.59 | FAR 52.227-2 | Notice and Assistance Concerning Patent and Copyright Infringement (AUG 1996) | Address patent infringement claims by Contractor | As Required |  |  |  |  | S |  |  |  | L
I.60 | FAR 52.227-3 | Patent Indemnity (APR 1984) | Notify Contractor of and patent infringement suit and afford the Contractor the opportunity to participate in its defense | As Required |  |  |  |  | S |  |  |  | L
I.61 | FAR 52.227-6 | Royalty Information (APR 1984) | Delete this clause from contract. It is a Section K Representation. | 2001-02-15 |  |  |  |  | L
I.62 | FAR 52.227-23 | Rights to Proposal Data (Technical) (JUN 1987) | Compliance | [5 empty] | S |  |  |  | L
I.63 | FAR 52.230-2 | Cost Accounting Standards (APR 1998) | Obtain and Review CAS Disclosure Statement; monitor compliance; approve accounting system changes; make appropriate equitable adjustments to Target Cost | 03/31/01 for DS and Ongoing |  |  |  |  | S |  |  | L | S |  |  | S
I.64 | FAR 52.230-6 | Administration of Cost Accounting Standards (NOV 1999) | Approve Cost Accounting Practice Changes and Disclosure Statement | As Required |  |  |  |  | S |  |  | L | S |  |  | S
I.65 | FAR 52.232-17 | Interest (JUN 1996) | Calculate interest on Contractor payments due DOE | As Required |  |  |  |  | S |  |  | L | S |  |  | S
I.66 | FAR 52.232-22 | Limitation of Funds (APR 1984) | Verify compliance with notification requirements | As Required |  |  |  |  | S |  |  | L |  | S
I.67 | FAR 52.232-23 | Assignment of Claims (JAN 1986) | No DOE Management Actions Required
I.68 | FAR 52.232-25 | Prompt Payment (JUN 1997) | Process semimonthly payment invoices & review prior invoice per established invoice review procedure | Semimonthly per procedure | S |  |  |  | S |  |  | L
I.69 | FAR 52.232-34 | Payment of Electronic Funds Transfer – Other than Central Contractor Registration (MAY 1999) | Obtain Contractor electronic payment information | 2001-02-01 |  |  |  |  | S |  |  | L
I.70 | FAR 52.233-1 | Disputes (DEC 1998) Alternate I (DEC 1991) | Obtain Claim Certification, legal analysis, technical analysis, cost analysis and audit as appropriate and issue a timely Contracting Officer's Final Decision. Ensure that ADR process in H.34 has been exhausted. | As Required | S | S | S | S | L | S | S | S | S | S | S | S
I.71 | FAR 52.233-3 | Protest After Award (AUG 1996) – Alternate I (JUN 1985) | Make determination to stay performance | As Required |  |  |  |  | L |  |  |  | S | S
I.72 | FAR 52.236-5 | Material and Workmanship (APR 1984) | Verify that all equip, materials, and articles incorporated in work is suitable for purpose intended | As Required | L |  |  |  | S
|  |  | Provide CO approval of machinery and mechanical and other equip to be incorporated into the work | As Required | S |  |  |  | L
I.73 | FAR 52.236-7 | Permits and Responsibilities (NOV 1991) | No DOE Management Actions Required
I.74 | FAR 52.236-8 | Other Contracts (APR 1984) | Verify compliance |  | L |  |  |  | S
I.75 | FAR 52.236-18 | Work Oversight in Cost-Reimbursement Construction Contracts (APR 1984) | Provide extent and character of work to be done | Ongoing through contract | S |  |  |  | L
I.76 | FAR 52.236-19 | Organization and Direction of the Work (APR 1984) | Obtain Contractor submittal of chart showing the general executive and administrative organization, the personnel to be employed in connection with the work under this contract, and their respective duties. | 2001-02-01 | L |  |  |  | S
I.77 | FAR 52.236-25 | Requirements for Registration of Designers (APR 1984) | No DOE Management Actions Required
I.78 | FAR 52.242-1 | Notice of Intent to Disallow Costs (APR 1984) | Issue notice and address Contractor response within 60 days | As Required | S |  |  |  | L |  |  | S
I.79 | FAR 52.242-3 | Penalties for Unallowable Costs (OCT 1995) | Determine and assess penalties for proposing expressly unallowable costs | As Required | S |  |  |  | L |  |  | S | S
I.80 | FAR 52.242-4 | Certification of Final Indirect Costs (JAN 1997) | Obtain certification | At time of final indirect cost submittal |  |  |  |  | L |  |  | S
I.81 | FAR 52-242-13 | Bankruptcy (JUL 1995) | No DOE Management Actions Required
I.82 | FAR 52.243-2 | Changes – Cost Reimbursement (AUG 1987) – Alternate III (APR 1984) | Changes Directed Only by Contracting Officer and Determination of Equitable Adjustment Amount | When Directed by CO | S | S |  | S | L |  |  | S | S | S |  | S
I.83 | FAR 52.243-6 | Change Order Accounting (APR 1984) | Changes Directed Only by Contracting Officer and Determination of Equitable Adjustment Amount | When Directed by CO | S | S |  | S | L |  |  | S | S | S |  | S
I.84 | FAR 52.243-7 | Notification of Changes (APR 1984) | Respond within 30 days of receiving notice from the Contractor | As Required | S | S |  | S | L |  |  | S | S | S |  | S
I.85 | FAR 52.244-2 | Subcontracts (AUG 1998) | Approve Contractor Purchasing System and provide subcontract approvals | Upon approval request by Contractor | S |  |  |  | L
I.86 | FAR 52-244-5 | Competition in Subcontracting (DEC 1996) | Verify compliance during Contractor purchasing system review | When system approval request submitted by Contractor | S |  |  |  | L
I.87 | FAR 52-244-6 | Subcontracts for Commercial Items and Commercial Components (OCT 1998) | Verify compliance during Contractor purchasing system review | When system approval request submitted by Contractor | S |  |  |  | L
I.88 | FAR 52-245-5 | Government Property (Cost Reimbursement, Time-and-Material, or Labor-Hour Contracts) (JAN 1986) | Provide GFP as Identified in C.9 Interface Control Documents | As Required by C.9 | S | L |  |  | S
I.89 | FAR 52.247-1 | Commercial Bill of Lading Notations (APR 1984) | Verify compliance | Ongoing |  |  |  |  | L
I.90 | FAR 52.247-63 | Preference for U.S.-Flag Air Carriers (JUN 1997) | Verify compliance | Ongoing |  |  |  |  | L
I.91 | FAR 52.247-64 | Preference for Privately Owned U.S.-Flag Commercial Vessel (JUN 1997) | Verify compliance | Ongoing |  |  |  |  | L
I.92 | FAR 52.249-6 | Termination (Cost Reimbursement) Alternate I (SEP 1996) | Authorized Only by Contracting Officer | If terminated | S | S | S | S | S | S | S | S | S | L | S | S
I.93 | FAR 52.249-14 | Excusable Delays (APR 1984) | Determination by Contracting Officer based on facts and extent of delivery failure. Revise delivery schedule, if appropriate. | When requested by Contractor | S |  |  |  | L |  |  | S | S | S
I.94 | FAR 52.251-1 | Government Supply Sources (APR 1984) | CO issue authorization to Contractor to use Government Supply Sources | When requested by Contractor |  |  |  |  | L
I.95 | FAR 52.251-2 | Interagency Fleet Management System Vehicles and Related Services (JAN 1991) | CO may issue authorization to Contractor to use interagency fleet management system vehicles | When requested by Contractor |  |  |  |  | L
I.96 | FAR 52.252-2 | Clauses Incorporated by Reference (FEB 1998) | No DOE Management Actions Required
I.97 | FAR 52.252-6 | Authorized Deviations in Clauses (APR 1984) | No DOE Management Actions Required
I.98 | FAR 52.253-1 | Computer Generated Forms (JAN 1991) | No DOE Management Actions Required
I.99 | DEAR 952.202-1 | Definitions (JAN 1997) | No DOE Management Actions Required
I.100 | DEAR 952.208-7 | Tagging of Leased Vehicles (APR 1984) | Obtain vehicle information from Contractor necessary to acquire Government vehicle tags | As required |  |  |  |  | L
I.101 | DEAR 952.208-70 | Printing (APR 1984) | Ensure Contractor obtains required printing through GPO sources | As required |  |  |  |  | L
I.102 | DEAR 952-216-7 | Allowable Cost and Payment (JAN 1997) | Execute payment, establish billing rates, and perform audits as required | As required | S |  |  |  | L |  |  | S | S |  |  | S
I.103 | DEAR 952.217-70 | Acquisition of Real Property (APR 1984) | Provide CO approval of real property purchases and leases | When requested by Contractor | S |  |  |  | L |  |  | S
I.104 | DEAR 952.222-70 | Whistleblower Protection for Contractor Employees (APR 1999) | Ensure whisteblower protection for Contractor employees | Ongoing | S |  |  |  | S | S | S | L | S |  | S
I.105 | DEAR 952.223-71 | Integration of Environment, Safety, and Health into Work Planning and Execution (JUN 1997) | CO establish date for submittal, discussions, and revisions to system. | Post Award | S |  |  |  | S | S | L |  | S
|  |  | Review and approve ISM System. Dates for submittal, discussions, and revisions to the System will be established by the contracting officer. Guidance on the preparation, content, review, and approval of the System will be provided by the contracting officer. | TBE | S |  |  |  | S | S | L |  | S
|  |  | On an annual basis, the contractor shall review and update, for DOE approval, its safety performance objectives, performance measures, and commitments consistent with and in response to DOE's program and budget execution guidance and direction. | Annually | L |  |  |  | S | S | S |  | S
I.106 | DEAR 952.223-75 | Preservation of Individual Occupational Radiation Exposure Records (APR 1984) | Verify compliance | Ongoing |  |  |  |  | S | S | L |  | S
I.107 | DEAR 952.224-70 | Paperwork Reduction Act (APR 1994) | No DOE Management Actions Required
I.108 | DEAR 952.245-5 | Government Property (Cost Reimbursement, Time-and-Material, or Labor-Hour Contracts | Provide GFP as Identified in C.9 Interface Control Documents | As Required by C.9 | S | L |  |  | S
I.109 | DEAR 952.247-70 | Foreign Travel (MAR 2000) | CO approval of all foreign travel | As requested by Contractor | S |  |  |  | L |  |  |  | S
I.110 | DEAR 952.250-70 | Nuclear Hazards Indemnity Agreement (JUN 1996) | No DOE Management Actions Required
I.111 | DEAR 952.251-70 | Contractor Employee Travel Discounts (JUN 1995) | Provide CO letter to Contractor entitling travels to federal travel discounts | 2001-01-15 |  |  |  |  | L
I.112 | DEAR 970.5204-9 | Accounts, Records, and Inspection (MAY 2000) | Verify that a separate set of accounts and records are maintained and inspection is made available at all reasonable times. | During periodic incurred cost audits | S |  |  |  | L |  |  | S | S |  |  | S
I.113 | DEAR 970.5204-31 | Insurance -- Litigation and Claims (JUN 1997) | CO direct Contractor to initiate third party litigation; ensure required bonds and insurance are obtained; and determine allowability of costs for Contractor liability to third parties | As required |  |  |  |  | S |  |  | S | L
I.114 | DEAR 970.5204-58 | Workplace Substance Abuse Programs at DOE Sites (AUG 1992) | Verify compliance and determine remedy for instances of non-compliance | Ongoing |  |  |  |  | S | L |  |  | S
I.115 | DEAR 970.5204-72 | Patent Rights Acquisition by the Government (SEP 1997) | Secure Government rights to intellectual property conceived or first actually reduced to practice in the course of or under this contract. | Ongoing |  |  |  |  | S |  |  |  | L
I.116 | DEAR 970.5204-77 | Workforce Restructuring Under Section 3161 of the National Defense Authorization Act for Fiscal Year 1993 (JUN 1997) | Verify Contractor compliance with workforce restructuring and accomplishment of restructuring to mitigate social and economic impacts | As required |  |  |  |  | L |  |  |  | S |  | S
I.117 | DEAR 970.5204-78 | Laws, Regulations, and DOE Directives (JUN 1997) | Compliance, Update Order Requirements As Necessary | As necessary | S | S | S | S | L | S | S | S | S | S | S | S
I.118 | DEAR 970.5204-79 | Access to and Ownership of Records (JUN 1997) | No DOE Management Actions Required
J | Attachment A | List of Acronyms | Update as necessary | As necessary |  |  |  |  | L
J | Attachment B | Reserved | No DOE Management Actions Required
J | Attachment C | Government-Furnished Property & GF Equipment | No DOE Management Actions Required
J | Attachment D | Small Business Subcontracting Plan | Approved at time of Contract Award and Approve Updates, Verify Compliance | As Required |  |  |  |  | L
J | Attachment E | List of Applicable Directives - List B | Update as necessary | As Required | S | S |  | S | L | S | S | S | S | S
J | Attachment F | Key Personnel | Verify Compliance, Approve Substitutions, Enforce H.3 | As Required | S |  |  |  | L |  |  |  | S
J | Attachment G | Performance Guarantee Agreement | Review Financial Condition of Guarantor | Annually |  |  |  |  | L |  |  | S | S |  |  | S
J | Attachment H | Tank Farm Contractor Staff and Subcontractors Employed on the WTP Project | No DOE Management Actions Required
J | Attachment I | Advance Understanding on Costs | Document Negotiated Agreements | 2001-02-11 | S | S |  | S | L |  |  | S | S |  |  | S
J | Attachment J | Small Disadvantaged Business Participation Program Targets | Verfiy Compliance During Performance and At Contract Closeout via OF-312 Reporting | At Contract Completion |  |  |  |  | L