## Equipment with Embedded Logic
Directions: | Equipment goes onto this sheet if there is any risk at all of date problems causing malfunction. This spreadsheet documents the first 4 steps:
1) Inventory and Initial Risk Assessment- Fill out Inventory information and how important this problem could be (columns 1-9);
2) Assessment- Research the problem, determine exactly what needs to be done, and note what fix and testing is required (Columns 10 & 14);
3) Correct- If a fix is required, note when the problem is actually corrected (Column 12);
4) Test- If test or verification is required, note what needs to be done. Note the date that the test or verification was done, and who did it.
Please review the Y2K Toolkit at http://www.ucsf.edu/y2k/toolkit/toolkit.html before filling out this form.
Dep't/Div/PI: |  |  |  |  | Contact Name:
Date: |  |  |  |  | Phone #:
1.Inventory and Initial Risk Assessment | [8 empty] | 2.Assessment |  | 3. Correct | 4.Test
(1) Inventory # or UC # (if Applicable) | (2) Equip. Location (Site & Room#) | (3) Serial Number (If no serial number, approximate date of manu- facture.) | (4) Manu-facturer | (5) Type of Equipment | (6) Model # | (7) Risk Level (C=Critical, I=Important, N=Not Important) | (8) Risk Assess-ment Date | (9) Risk Assess-ment By (initials) | (10) Correction Required? (Y/N). If Yes,explain in Notes, along with testing rq'd. | (11) Est. Cost of Compliance | (12) Date of Cor- rection | (13) Notes: State Correction and Testing/verification required. Sign off here when testing is done and note the date. You may also provide detail on actions taken or required, assigned resources, risks, etc.
745-97542 | 4.368S | TY19BHH72 | Beckman | defibrillator | LX-700 | C | 1997-12-19 | clh |  |  |  | The spreadsheet will expand to allow as much information to be put in here as necessary. It also will put the above header at the top of every page for clarity.

## Desktop Computer Hardware
Directions: | To take inventory and make an initial assessment, fill out columns 1-6 (7 if you can). Fill out other columns as problems are found, fixed and tested.
Please review the Y2K Toolkit at http://www.ucsf.edu/y2k/toolkit/toolkit.html before filling out this form.
Macintosh computers (HARDWARE ONLY) are compliant and need NOT be included.
Dep't/Div/PI: | [5 empty] | Contact Name:
Date: | [5 empty] | Phone #:
1.Inventory and Initial Risk Assessment | [7 empty] | 2.Assessment |  | 3. Correct | 4.Test
(1) Inventory # (if available) | (2) Equip. Location (Site & Room#) | (3) Serial Number (If no serial number, approximate date of manu- facture.) | (3) Manu- facturer | (6) Model # | (4) Risk Level (C=Critical, I=Important, N=Not Important) | (5) Risk Assess- ment date | (6) Risk Assess-ment By (initials) | (7)Correction Required? (Y/N). If Yes,explain in Notes, along with testing rq'd. | (8) Est. Cost of Correction | (9) Date of Compliance | (13) Notes: State Correction and Testing/verification required. Sign off here when testing is done and note the date. You may also provide detail on actions taken or required, assigned resources, risks, etc.
EXAMPLE:
745-93369 | 464.L MED |  | DELL |  | N | 1997-12-19 | clh | Y |  |  | Flash the BIOS as a last resort; want to do it ~April 15 after we have verified that we can't do a upgrade via software. This is one of 4 like this, should do them all at once w/School of Pharmacy machines. -jspw 1/21/99.

## Licensed Computer Software
Directions: | To take inventory and make an initial risk assessment, fill out columns 1-9 (10 if you can). Fill out other columns as problems are fixed and tested.
This spreadsheet asks for SUMMARY information only about software in your department. If you would like a form to help collect this information, see the web site.
Include: Macintosh software, Windows Operating System software, and software running on departmental servers.
Please review the Y2K Toolkit at http://www.ucsf.edu/y2k/toolkit/toolkit.html before filling out this form.
Dep't/Div: |  |  |  | Contact Name:
Date: |  |  |  | Phone #:
1.Inventory and Initial Risk Assessment | [8 empty] | 2.Assessment |  | 3. Correct | 4.Test
(1) Manu- facturer (or custom) | (2) Software Name | (3) Software Version | (4) Total QTY -- Risk Level Critical | (5) Total QTY -- Risk Level Important | (6) Total QTY -- Risk Level Not Important | (7) Total QTY (sum columns 4,5 &6) | (8) Risk Assessment Date | (9) Risk Assessment By (initials) | (10)Correc- tion Required? (Y/N). If Yes,explain in Notes, along with testing rq'd. | (11) TOTAL Est. Cost of Correction | (12) Date of Compli-ance | (13) Notes: State Correction and Testing/verification required. Sign off here when testing is done and note the date. You may also provide detail on actions taken or required, assigned resources, risks, etc.
EXAMPLE:
Borland | Paradox | 7 | 1 | 1 | 3 | 5 | 1997-12-19 | clh |  |  |  | This version of Paradox requires minor patch, but we built two apps that need date formattikng chages on the input, sinced it only lets us enter two digits. Need to allocate resources to check the rest of the databases for simlar issues. -jsw 1/21/98

## Vendor Dependence
Directions: | This spreadsheet is designed to address our dependence on vendors that could be affected by Year 2000 problems This exposure could
be to completely non-technical products or services. Enter items that are critical or important for which you may need backup inventory or services that could be
delayed that you depend on. Do not include power systems and other systems shared by many or all departments unless there is special risks for you.
To take inventory and make an initial risk assessment, fill out columns 1-9 (10 if you can). Fill out the rest as issues are found and resolved.
This spreadsheet asks for SUMMARY information only about dependence on vendors. If you would like a form to help collect this information, see the web site.
Please review the Y2K Toolkit at http://www.ucsf.edu/y2k/toolkit/toolkit.html before filling out this form.
Dep't/Div: |  |  |  | Contact Name:
Date: |  |  |  | Phone #:
1.Inventory and Initial Risk Assessment | [8 empty] | 2.Assessment | 3. Correct | 4.Verification
(1) Manu- facturer (or custom) | (2) Product Name | (3) Model #/ Version/ Type/ Size | (4) Total QTY -- Risk Level Critical | (5) Total QTY -- Risk Level Important | (6) Total QTY -- Risk Level Not Important | (7) Total QTY (sum columns 4,5 &6) | (8) Risk Assessment Date | (9) Risk Assessment By (initials) | (10)Action Required? (Y/N). If Yes,explain in Notes. | (11) Date adequate vendor Assurance or inventory increase, etc. | (12) Notes: State intentions and any verification required. Sign off here when verification is done, point of contact, related dependencies, etc. and note the date.
EXAMPLE:
Solutions-r-us | Solution1 | Thick1/32 oz. | 4 | 2 | 21 | 27 | 1997-12-19 | clh |  |  | We only keep 2 weeks of solution around- this is a highly technical product to put out, vendor is highly automated- can we increase the inventory to 4-6 weeks, or do we want to talk to the vendor about it? JS 1/21