## Sheet1
ACTIVITIES AND TASKS | DELIVERABLES | INFORMATION SOURCE | RESPONSIBLE PARTY | DURATION
ORIENTATION
Review Steps to Getting Started | Agency Understanding | Info on ePay Website | Agency
Review Roles and Responsibilities | Agency Understanding | Info on ePay Website | Agency
Review US Bank FAQ Document | Agency Understanding | Info on ePay Website | Agency
Review eLearning Tutorial | Agency Understanding | http://www.payconnexion.com/E-Learning/ | Agency
Review Technical Documentation | Agency Understanding | Info on ePay Website | Agency
Review Sample State Application Pages | Agency Understanding | http://www.doa.state.wi.us/docs_view2.asp?docid=1703 | Agency
Review Sample Statement of Work | Agency Understanding | Info on ePay Website | Agency
INITIATION
Submit Business Overview, Current Payment Method | Brief High Level Overview/Charter | Email ePay Product Manager | Agency
Agency Objectives | Agency Objectives Document | Agency | Agency
Agency Submits Request for ePay Services | Completed Form to ePay Product Manager | Form from ePay Website | Agency ePayment Lead
ePayment Services Kickoff Meeting | Forward Minutes to ePay Product Manager | Agency ePayment Lead | Agency ePayment Lead
Decision to Move Ahead with Planning | Notifiy ePay Product Manager | Agency ePay Team Lead | Agency ePayment Lead
PLANNING
Review of US Bank Contract |  | Info on DOA Website | Agency
Determine Cost-Effective Payment Method | Calculation Form | Calculator on DOA Website | Agency Financial Lead
Create Project Plan | Project Plan Approved by Agency | Create MS Project template from this document | Agency Project Lead
Submit Implementation Questionnaire | Agency Contact Information | Form from ePay Website | Agency ePayment Lead
Develop a Statement of Work | SOW Signed by Agency/DOA/USB | Example on ePay Website | US Bank/DOA-DET
Customer Help Desk/Support | SLA - Approved by Agency/DOA/USB | Info on ePay Website | Agency/DOA-DET
IMPLEMENTATION
Financial - DOA/SCO
ePayment Bank Accounts Established |  | DOA Financial Lead | DOA-SCO | 2 days
Financial - Agency
Custody Appropriation Established (if necessary) |  | Agency Financial Staff | Agency Financial Staff
Financial Mngr Signs Reconciliation Agreement | Reconciliation Agreement | Agency Financial Manager | Agency Financial Manager
Agency Request for Merchant ID | Merchant ID Form | Available on ePay Website | Agency/DOA-SCO
Technical - Agency
Develop Web Application Redirect to USB | Application Post to USB | Agency Technical Lead | Agency Technical Lead | 0.5 day
Develop RTPC Listener (if required) | Application Listener for RTPC | Agency Technical Lead | Agency Technical Lead | 0.5 day
Develop Paid Transaction Processing | Application Processing for Paid Transactions | Agency Technical Lead | Agency Technical Lead | Agency Project Dependent
Integration Testing w/ USB & DET | Confirm Agency / DET / USB Functionality | Joint Agency/DET/USB Technical | Joint Agency/DET/Technical | Agency Project Dependent
Technical - DOA/DET
Configure E-Pay Proxy Server for Agency RTPC | DET Proxy Support for Agency RTPC | DET Implementation Lead | Agency Technical Staff | 0.25 day
Coordinate Integration Testing w/ Agency & USB | Confirm Redirect & RTPC Proxy Services | DET Implementation Lead | Agency Technical Staff | 5 days
US Bank / Anexsys
Implement Agency Product per Questionairre | Payment Pages for Agency We b Application | Anexsys Contact | Joint /Agency/DET/USB
Integration Testing w/ Agency & DET | Test Plan/Scripts, Acceptance | Joint Agency/DET Technical | Joint /Agency/DET/USB | 5 days
QA / Acceptance Testing | Acceptance Document-Agency/DET | Agency and DET QA Staff | Agency and DET QA Staff | 5 days
USB = US Bank
Anexsys = Credit Card Processor (owned by US Bank)
DOA = Department of Administration
SCO = State Controller's Office
DET = Division of Enterprise Technology
SLA = Service Level Agreement
QA = Quality Assurance
Note on B7: Pam Hujanen: User ID = eLearner Password= Payconn22
Note on B13: Pam Hujanen: Provide a brief overview of the business or program area with current fees/payment methods -- or provide agency project charter.