## Triennium
DOC. FINANCE SG-4
Status of Projects Managed by the Convention Bureau
Triennium Report for the years 1999, 2000, 2001 and up to 31 August 2002
Project Number | Project Title / Description |  | Income |  |  | Total Expenditures | Project Balance
|  |  | 1 Jan. 1999 to 31 Aug 2002 |  |  | 1999-2002 | as of 31 August 2002
|  |  | Balance Carried Forward at 01.01.99 | CHF |  | CHF | CHF
7002-000 | Ramsar Advisory Missions (RAMs) |  | Balance Carried Forward | 103913.48 |  | 79164.6 | 54662.88
Technical missions, at the request of the countries concerned, to Ramsar sites included in the Montreux Record in order to prepare recommendations on how to address the problems involved.
|  |  | UK - RSPB 1999 | 9600
|  |  | UK - RSPB 2000 | 10476
| Activities in 2000: |  | UK - RSPB 2001 | 9838
RAM No. 41 to Ichkeul, Tunisia (on Montreux record) was undertaken in March 2000 by a consultant
and the RC for Africa.
RAM No. 42 to Djoudj, Senegal and Diawling, Mauritania was undertaken in September 2000.
RAM No. 43 to the Ebro Delta, Spain, took place in September 2000.
Activities in 2001:
Two experts visited the Schinias wetlands in Greece.
RAM No. 44 to the Sumava Peatlands in the Czech Republic took place in June 2001
The RC for Africa undertook RAM No. 45 to the Parc national de la Keran site in Togo in August 2001.
RAM No. 46 was made to the Mühlenberger Loch in Germany (24-26 September 2001).
RAM No. 47, a joint World Heritage/IUCN mission for the Srebarna site in Bulgaria was undertaken in October 2001.
RAM No. 48 was undertaken at the Llancanelo Site in Mendoza, Argentina in October 2001.
RAM No. 49 was undertaken at the Ouse Washes Ramsar Site, UK on 5-8 November 2001.
RAM No. 50 to Chilika Lake, India, for removal of this site from the Montreux Record took place 11-13 December 2001.
7051-000 | Wetland Database / Directory Expertise |  | Balance Carried Forward | 3617 |  | 3617.45 | Closed
| Support for the development of the Ramsar expert database. A consultant was appointed to set up and compile a database of wetland experts, particularly from developing countries and countries whose economy is in transition. The database was launched on World Wetlands Day, 2 February 1998 and currently has entries on over 300 experts from 68 countries. The Bureau is looking for ways to continue to maintain the database. | [5 empty] | 28.01.00
USA
7056-000 | Wetlands for the Future. An initiative to promote training in the management of wetlands |  | Balance Carried Forward | 239560.1 |  | 1474611.1 | 731125
7056-030 | in Latin America and the Caribbean
| Support for wetland training and education in the Neotropics in the context of the agreement between the Government of the United States and the Bureau concerning the partnership for effective implementation of the Convention in the Western Hemisphere in honour of the Convention's 25th Anniversary. Projects are jointly approved by the US Department of State, US Fish and Wildlife Service, and the Bureau. Expenditure to date has funded 149 projects in the Neotropics in the field of training and capacity building. |  | USA - Dep't of State - 1999 | 445380
|  |  | USA - Dep't of State - 2000 | 442098
|  |  | USA - Dep't of State - 2001 | 539730
|  |  | USA - Dep't of State - 2002 | 538968
Funding has also been provided to support four specialized workshops in Colombia, Mexico, the CARIBWA
Conference and the Turtle workshop in Belize. The project also provided 8 specialists the chance to attend the
Millenium 2000 Wetland Event in Quebec City, Canada in August 2000.
* Funds in the amount of CHF 119,364 are committed for previous years' contracts.
In 2001, 42 proposals were submitted, and approval for funding was given to 23 projects and two workshops.
In 2002, 34 proposals were submitted and 21 were approved.
7056-041 | Conservacion Altoandinos - Chile |  | Minera Escondida Ltda | 49227.65 |  | 37800.9 | 11426.75
In 2002, Minera Escondida Ltda generously gave US$30,800 towards a project in Chile entitled:
"Action plan for the conservation and development of the High Andean wetlands".
7063-000 | Wetland Biodiversity Publication |  | Balance Carried Forward | 7971 |  | 7971.15 | Closed
| Publication of Wetland Biodiversity in connection with the celebration of the Convention's 25th Anniversary; the printing of the publication was donated by India. The remaining funds were used for its dissemination. | [5 empty] | 31.12.00
|  |  | India | Printing
7066-000 | 25th Anniversary Pledges |  | Balance Carried Forward | 126470.33 |  | 109185 | 17285.35
In honour of the Convention's 25th Anniversary, pledges from a number of Contracting Parties have been earmarked for support of goals listed in the Ramsar Strategic Plan 1997-2002. Certain Contracting Parties pledged funds to be used in their own countries. A donation of non-earmarked funds from Switzerland (CHF 500,000) continues to sustain this project.
Switzerland
A paper was prepared for the UNFCCC COP5.
Wetlands International prepared a Global Review Study.
A River Basin Study was prepared in 2000, which led to the implementation of the River Basin Initiative.
Workshops on Inland Water Ecosystems were held in Zimbabwe in July 2000, Colombia in September 2000, and
Malaysia in November 2000.
Field equipment was furnished to the Hamukungu Ramsar Site Management Association in Uganda.
Five scientists were sponsored to attend the Asian Wetland Symposium in Penang, Malaysia in August 2001.
7070-000 | Special Requests Project |  | Balance Carried Forward | 2786 |  | 38925.28 | 29997.34
The funds in this project are designed to be made available at short notice to governments, NGOs, and other bodies (normally within Ramsar Contracting Party States, though exceptionally in non-Party countries) for activities related to the Convention and Strategic Plan which only require limited funds. Expenditure to date has funded sixteen projects.
|  |  | Project transfers | 55206
|  |  | Belgium, Wallonne Region | 10930.62
Examples:
A contract with the Kenya Wildlife Service funded the preparation of Lake Bogoria as a Ramsar site.
The project supported an expert to travel to the ISEH meeting in Brisbane.
A translation of the Ramsar Toolkit into Chinese was funded in 2001.
The fund helped pay for the printing of the WCMC Seagrass Atlas.
200 Video copies were made for EcoCienca in Ecuador.
Belgium provided funding for the airfare of a participant from Senegal to the RIZA course in the Netherlands.
7071-000 | Swiss Grant for Africa 1997 |  | Balance Carried Forward | 37109.43 |  | 29109.43 | 8000
The 1997 grant for work in Africa was used for the assessment of potential Ramsar sites in The Gambia; for initial studies on populations of water birds in a Ramsar site in Gabon; for the preparation of a management plan for a national park in Niger; for an emergency rehabilitation plan in a biosphere reserve in Senegal; for Wetlands International's 1997 African Waterfowl Census Report; and for seed funding for a project to evaluate wetland systems in the Southern African Development Community (SADC).
Switzerland
7072-000 | MedWet 2 Co-ordination |  | Balance Carried Forward | -105026.64 |  | 260670 | 79330.08
| WWF's Mediterranean Programme provided funds to cover the MedWet Co-ordinator's part-time salary and travel and office expenses in 1997 and 1998. For 1999 and 2000 the contributions came from the MAVA Foundation. |  | WWF - International - 1999 | 105000
|  |  | MAVA Foundation - 1999 | 160000
|  |  | MAVA Foundation - 2000 | 180000
| The Greek Government contributed funds to help establish and support the MedWet Unit in Greece. |  | Greece - Min.of Environment 2001 | 160000 | €
|  |  | Greece - Min.of Environment 2002 | 160000 | €
7073-000 | Seventh Meeting of the Conference of the Parties |  | Registration Fees | 90563 |  | 856240 | Closed
| Expenditures relating to the 7th Conference of the Parties in San José, Costa Rica in 1999. |  | Hotel Commissions | 83382.64 |  |  | 10.10.00
|  |  | Bal PanAm meeting | 2111
|  |  | Greece | 8000
|  |  | USA Dep't of State 97-99 | 179973
|  |  | Core Budget 98+99 | 170000
|  |  | Reserve Fund | 158614.36
|  |  | Sweden, Sida | 50224
|  |  | Switzerland | 50000
|  |  | Transfer to cover deficit | 63372
|  |  | Total | 856240
|  | * | US FWS | 100000 | $
| * These amounts were paid directly to the | * | Netherlands,Embassy | 50000 | $
| COP7 Trust Fund opened in Costa Rica. | * | Spanish Int'l
|  |  | Cooperation Agency | 45000 | $
7074-000 | African Intern |  | Balance Carried Forward | -13383 |  | 17017.1 | Closed
| Financial support from the USA in 1999 provided training of an intern from Africa and to expose him/her to the workings of the Convention as an instrument for international co-operation for the conservation and wise use of wetlands. The intern gives technical assistance to the Bureau's Regional Co-ordinator for Africa. | [5 empty] | 31.12.00
|  |  | USA - Fish & Wildlife Service | 30400
Now funded through the Core budget.
7076-000 | Austrian-Kenyan Twinning Project on Studies on White Stork in their Wintering Grounds |  | Austria 1999 | 3420.75 |  | 6619.75 | 3175.72
| Support from the Austrian Federal Ministry for Environment for Ramsar to coordinate with the Ministry of Tourism and Wildlife of the Kenya Wildlife Service to start on Phase II of the project on the European White Stork in their wintering grounds. Sub-projects include a mini-poster on the distribution and ecology of the White Stork, a twinning programme between schools, communities & national park administrators and providing equipment for site managers. |  | Austria, Arge Natuursch. 2001 | 3175.75
|  |  | Austria, Umwelt - 2001 | 3198.97
7079-000 | Evian Project (1998-2000) |  | Balance Carried Forward | 1680.4 |  | 1134709 | Closed
| The Evian project, known formally as the 'Caring for Water Resources and Water Quality Initiative', is a portfolio of activities in support of the Convention, funded by the Groupe Danone (which includes the Evian mineral water company) and the French Global Environment Facility (FFEM), and developed with the support of the Government of France, the town of Evian, and in particular the Conservatoire du Littoral. | [5 empty] | 03.2002
|  |  | Danone Evian | 698152.15
|  |  | Conservatoire Littorale | 35732.15
|  |  | France, FFEM | 399144.91
A brochure describing this project will be distributed at COP8.
7079- | Evian Project 2001 - 2002 |  | Danone Evian - 2001 | 232271.32 |  | 443504.88 | 11998.98
010 to 080 | Danone has committed to continuing the Evian project and has provided funding for a total of FFR 2,000,000 over a period of two years. |  | Danone Evian - 2002 | 223232.54
The 2001 programme included: A symposium on Mountain Living Waters; an Evian Encounter for Arab Countries, a Workshop through EACN China, various Communications projects and the Evian Exhibition.
During 2002 an additional three projects were added:
A Workshop through EACN Japan; The Evian Award 2002 (to be presented at COP8 Valencie);
and an Evaluation Report of the whole project will be prepared by a consultant.
7081-000 | Swiss Grant for Africa 1998 |  | Balance Carried Forward | 74680.53 |  | 86780.52 | 7900.01
The 1998 grant for work in Africa covered the balance of seed funding for a project to evaluate wetland systems in the Southern African Development Community (SADC); development of an integrated management plan at a Ramsar site in Botswana; support for the development of a common approach to shared water catchment areas in Benin, Burkina Faso, Niger, and Togo; support for a public awareness campaign on invasive species in wetlands; completion of the national wetland policy in Zambia; and Wetland International's 1998 African Waterfowl Census Report.
|  |  | Switzerland, additional funds | 20000
7083-000 | Costa Rica Conference of the Parties - Delegate Support |  | Australia | 9680 |  | 775416 | Closed
| Support for 181 delegates and observers from developing countries and countries whose economies are undergoing transition to attend the 1999 Conference of the Parties. |  | Austria | 4603 |  |  | 10.10.00
|  |  | Belgium | 21140
|  |  | Canada, CIDA | 16877
| In total 181 delegates were funded, from 85 Contracting Parties and 17 Observer States. |  | Denmark | 30000
|  |  | Finland | 40421
|  |  | France, Min. Foreign Affairs | 17428
|  |  | France, Min. of Environment | 24394
|  |  | Germany | 40809
|  |  | Hungary | 29700
|  |  | Italy | 49682
|  |  | Japan | 100000
|  |  | Netherlands | 73800
|  |  | Norway | 18850
|  |  | Portugal | 1600
|  |  | Sweden, SIDA | 146457
|  |  | Switzerland | 50000
|  |  | United Kingdom | 21105
|  |  | From 7061 | 15321
|  |  | UNESCO | 28500
|  |  | WWF Int'l | 10000
|  |  | WWF-Australia | 6088
|  |  | WWf-UK | 14616
|  |  | Honorarium WRP | 4345
|  |  | Total | 775416
7084-000 | Asian Regional Meeting |  | Sweden, Sida | 175125.11 |  | 175125 | Closed
| Preparatory meeting for the 1999 Conference of the Parties, covering the cost of the meeting facilities and materials, travel and subsistence costs of sponsored participants and staff, and hospitality provided during the meeting which was held in Manila, The Philippines, in February 1999. | [5 empty] | 28.01.00
** SIDA donated the balance to 7073 COP7 preparations.
7086-000 | Ramsar Promotional Book |  | Switzerland | 50000 |  | 44687.07 | 90312.93
| This book will depict significant Ramsar sites around the world. |  | Spain, Min. of Env. | 85000
A consultant co-ordinated the call for photographs to all Parties, the production of a CD-Rom and the final
printing of the book. The book wil be ready for distribution at COP8.
7087-000 | Japan Voluntary Additional Contribution |  | Balance Carried Forward | 211677 |  | 424000 | 206040
Voluntary contributions from Japan in the years 1997, 1998 and 1999 specifically targetted for projects in the Asian region. Funds have been donated to COP7 Sponsored Delegate travel, the Small Grants Fund for 1999, and two Small Grants Projects in Nepal in 1999 and 2000.
|  |  | Japan, Min. of Foreign Affairs | 418363
In 2001 CHF 100,000 was approved to support the Asian Regional Meetings in 2001 and 2002.
In 2002 CHF 100,000 was approved to support COP8 delegates.
7088-000 | Swiss Grant for Africa 1999 |  | Switzerland | 154444 |  | 148436.38 | 6007.62
Six projects were funded in Botswana, Burkina Faso, Cameroon and Nigeria.
A combined implementation of environment-related conventions in CAR, Benin, Cameroon and Tanzania
was established. A wetlands Inventory Training program was initiated in Cameroon and Kenya.
7089-000 | Publication of COP7 Proceedings |  | Spain - Biodiversity Foundation | 240675.3 |  | 240683.65 | Closed
| Approximately 600 copies of the COP7 Proceedings (Resolutions and Recommendations, List of Participants and |  | Ministry of Environment |  |  |  | 07.06.01
the Conference Report) were mailed to participants of the COP.
The grant also paid for the production of the Ramsar "Toolkit" - a boxed set of 10 handbooks.
The Bureau has mailed out approximately 2,500 sets of this reference guide.
7090-000 | Convention Outreach Programme |  | Reserve Fund excess | 76839 |  | 97310.66 | 30412.06
| The 24th Standing Committee approved the use of the excess in the Reserve fund to initiate the |  | Transfers from projects | 50883.72
"Voluntary Fund for the Convention's Outreach Programme". A consultant has prepared a report on implementing
the Convention's Outreach Programme 1999-2002: Reviewing and Action Plannning for Wetland Communication,
Education and Public Awareness. The report has been translated into French and Spanish.
A consultant was engaged to prepare documents for World Wetland Day.
A contribution was made to the Ugandan Wetland Programme for preparations for WWD 2002.
A consultant was engaged to prepare an information document entitled 'Agenda 21 and the Ramsar Convention'
on Ramsar's activities, for the UN Department of Economic and Social Affairs, for the information of those involved
in the preparation of the 2002 World Summit on Sustainable Development.
7091-000 | GEF Iran |  | UNDP GEF | 148567 |  | 148567 | Closed
| The Bureau acted as International Service Provider under contract to the UNDP. | [5 empty] | 16.05.02
Five expert consultants were contracted to prepare studies on Wetland Appraisal; Legal and
Institutional work; and Management and Training. All final reports have been submitted.
7092-000 | MedWet Com3 |  | Portugal | 3867.5 |  | 19291.7 | Closed
| Provided the travel expenses for sponsored delegates to the MedWet Com3 meeting in Djerba, Tunisia in 2000. |  | Spain, Min. of Environment | 15424.18 |  |  | 31.12.00
7093-000 | Swiss Grant for Africa 2000 |  | Switzerland | 142744 |  | 132001.6 | 10742.4
The Swiss Grant has provided funding for six projects in:
Botswana: Development of a management plan for the Okavango Delta.
Guinea: Implementing the Convention. Sierra Leone: Assistance to ratify Ramsar sites.
Madagascar: Management plan for Manambolomaty site.
As well, a public awareness & education programme has been started in Ghana and Kenya, an emergency plan
against Salvinia molesta was funded in Senegal, and a workshop was held in Mauritius.
7094-000 | STRP Working Groups |  | UK - Dept of Environment | 12070 |  | 99834.7 | 18267.3
|  |  | USA - Dept of State | 65496
| In 2001 consultants prepared reports for COP8 on: |  | Reserve fund excess | 40536
> Development of Guidance on Climate Change and Wetlands
> Preparation of Guidelines for Water Allocations and Management
> Contribution to Guidelines for Water Allocations and Management
> Global Review of Wetland Resources - Wetland Inventory Meta-database
> Principles and guidelines for integrating wetlands into Integrated Coastal Zone Management.
7095-010 | COP8 - Valencia, Spain 2002 - Administration |  | Spain | 721000 |  | 257656 | 582199.08
| Expenditures relating to the Conference of the Parties to be held 18-26 November 2002. |  | Switzerland has pledged | 50000
The funding will cover the translation of documents before and during the COP; hiring of consultants and experts;
reproduction and distribution of documents; interpreters and translators; per diems and travel for Bureau staff &
printing of the COP8 Proceedings.
771000
7095-020 | COP8 - Sponsored Delegates |  | Austria, Fed. Min. of Agriculture, Forestry, Env & Water Mgmt | 13797 |  |  | 645127
| Additional fundraising has been initiated to achieve a total goal of CHF 1.4 million to support delegates and observers |  | Belgium, Ministere de la Region Wallonne | 18000
| from developing countries and countries whose economies are undergoing transition to attend the Conference |  | Finland, MoEnv. | 14704
| of the Parties in Valencia, Spain in November 2002. |  | Germany, Ministry for Umwelt, Naturschutz | 50725.5
|  |  | Hungary, Dept for Int'l Relations | 17099
|  |  | Hungary, Min for Euro Relations | 33378
|  |  | Japan, Mission | 100000
|  |  | Netherlands, Min. of Agriculture, Nature Mgmt & Fisheries | 23480
|  |  | Spain, Ministerio de Medio Ambiente | 100000
|  |  | Sweden, SIDA | 34910.05
|  |  | UK, DEFRA | 80513
|  |  | USA - Dep't of State | 158520
645126.55
Pledged:
|  |  | Denmark, Min. of Env.DANCEE | 29350
|  |  | France, Min. of Environment | 33085
|  |  | France, UNESCO | 29900
|  |  | Netherlands, Min. of Agriculture, Nature Mgmt & Fisheries | 6000
|  |  | Switzerland, Direction du Développement et de la Coopération DDC | 60000
158335
7095-030 | COP8 - Secondee |  | Spain, Ministry of Environment | 239333 |  | 179424.42 | 59908.58
Mr Carlos Villalba has been seconded from Spain as the Bureau's "COP8 Technical Support Officer" until
December 2002. Part of Mr Villalba's time will be devoted to working with the MedWet Coordination Unit in Athens.
7096-000 | European Regional Meeting - Bled, Slovenia 13-18 October 2001 |  | Austria | 14899 |  | 114932 | Closed
| The meeting was attended by 141 participants, representing 38 Contracting Parties in the European Region |  | Denmark, DANCEE | 29250 |  |  | 31.12.01
| (of a total of 44), nine international organisations, and a number of non-governmental organisations and invited experts. |  | France | 33138
| A total of 45 sponsored delegates were helped with funding to attend the meeting. |  | Netherlands | 17222
|  |  | Switzerland | 20000
| Note: Some contributions originally made to this meeting were transferred to other meetings, with the donors consent. |  | UK, DEFRA | 423
114932
7097-000 | Middle East Regional Meeting - Beirut, Lebanon, 5-10 October 2002 |  | Japan | 61330 |  | 17270 | 44060
The meeting will be attended by approximately 50 persons, comprising 7 from non-Contracting Parties, 7 Partner
organizations, 4 NGO's, plus observers. Thirteen sponsored delegates will be supported to attend the meeting.
7097-010 | West and Central Asian Regional Meeting - Islamic Republic of Iran, 3-5 February 2002 |  | Japan | 37318.44 |  | 48249.06 | Closed
| The meeting was attended by 38 participants, comprising 8 Contracting Parties, 3 non-Contracting Parties, 6 Partner |  | Belgium, Wallonne District | 10930.62 |  |  | 12.08.02
organizations, 9 International and regional organizations, plus observers. Sixteen sponsored delegates were
supported to attend the meeting.
7097-020 | East Asian Regional Meeting - Bangkok, Thailand, 1-3 October 2001 |  | Japan* | 1000 |  | 34399.48 | Closed
| The meeting was attended by 78 persons, comprising 9 Contracting Parties, 2 non-Contracting Parties, 7 organizations, |  | Sweden, SIDA | 33399.5 |  |  | 12.08.02
7 NGO's, plus observers. Eighteen sponsored delegates were supported to attend the meeting. * Japan offered
full funding, but Sida's contribution had to be used before 31.12.01. Thus Japan's funding had to be reserved.
7098-010 | Central and Northern Africa Regional Meeting - Algiers, Algeria 19-21 March 2002 |  | MAVA | 50000 |  | 71800 | Closed
| The meeting was attended by 38 persons, comprising 10 Contracting Parties, 7 non-Contracting Parties, |  | Sweden, SIDA | 718 |  |  | 26.08.02
| 3 organizations and 7 partner organizations. In total 25 delegates were sponsored to attend. |  | Norway, Dir. For Nature Mgmt | 10000
|  |  | Algeria, Min. of the Environment | 11229
7098-020 | Eastern & Southern Africa Regional Meeting - Lusaka, Zambia, 12-14 November 2001 |  | Sweden, SIDA | 66980.6 |  | 73890.79 | Closed | 1.6678
| The meeting was attended by 38 persons, comprising 10 Contracting Parties, 7 non-Contracting Parties, |  | Norway, Dir. For Nature Mgmt | 6910.12 |  |  | 31.12.01 | 51353
3 organizations and 7 partner organizations. In total 32 delegates were sponsored to attend.
7098-030 | West Africa and Island States Regional Meeting - Cotonou, Benin 5-7 June 2002 |  | Norway, Dir. For Nature Mgmt | 14524 |  | 95783.93 | Closed
| The meeting was attended by 38 persons, comprising 10 Contracting Parties, 7 non-Contracting Parties, |  | Sweden, SIDA (2002) | 41260 |  |  | 26.08.02
| 3 organizations and 7 partner organizations. In total 32 delegates were sponsored to attend. |  | Switzerland, Agency for Environ. | 40000
7098-040 | Summary meeting for the Africa Region - Gland, Switzerland October, 2002 |  | Norway, Min. of Environment | 14151 |  |  | 14151
A meeting will be held in Gland to summarize the key results of the regional meetings.
7099-000 | South America Regional Meeting - Buenos Aires, Argentina 10-12 September 2001 |  | Argentina | 87022.5 |  | 87023 | Closed
| A total of 58 delegates attended the first regional meeting. Of these 13 Contracting Parties and 4 | [5 empty] | 31.12.01
organizations were represented. A total of 26 delegates were sponsored to attend the meeting.
7099-010 | Central America and Caribbean Regional Meeting - Guayaquil, Ecuador 1-5 July 2002 |  | Canada | 9612.12 |  | 173107.19 | 38576.4
| Ninety participants attended the meeting, of which the following Contracting Parties were represented: |  | Spain | 43551.47
| 22 from the Neotropics, three from North America and 3 European observers. Five non-Contracting Parties participated. |  | USA | 158520
| Five Partner organizations and 13 NGOs were represented. A total of 41 delegates were sponsored to attend. |  |  | 211683.59
7099-020 | Americas Regional Meeting to non-CP States 15-22 September 2002 |  | USA | 72247 |  | 13780 | 58467
A delegation of representatives from the Bahamas, Trinidad & Tobago and the US Fish & Wildlife Service visited
Antigua & Barbuda, Barbados, Guyana, Grenada, St Vincent & the Grenadines, and Saint Lucia (CP) to ascertain.
the status of preparation for adherence to the Convention.
7099-030 | Central/North American & Caribbean Regional Meeting - San Pedro Sula, Honduras, |  | Canada | 5960 |  | 47882 | Closed
| 26-28 September 2001 |  | Norway, Dir. For Nature Mgmt | 14455 |  |  | 31.12.01
| Over 60 delegates representing 17 Contracting Parties and four organizations, as well as other non-governmental |  | Sweden, SIDA (2001) | 13686
| agencies attended the meeting. Fifteen delegates were sponsored to attend. |  | USA | 13781
7100-000 | Swiss Grant for Africa 2001 |  | Switzerland | 140000 |  | 158053.6 | Closed
| Six initiatives were undertaken in 2001. |  | OMPO - Oiseaux Migrateurs du | 18053.62 |  |  | 15.02.02
| An integrated management plan for the Okavango Delta in Botswana; an invasive species initiative for all African |  | Paléarctique Occidental
Contracting Parties; an African Waterfowl Census for all African CPs; Support for accession to the Convention
for Burundi, Mauritius and Sudan; Restoration of a new Ramsar site in Algeria; and Transboundary management
and Ramsar site designation in the Lake Malawi Basin for Malawi, Mozambique and Tanzania.
7100-010 | Swiss Grant for Africa 2002 |  | Switzerland | 140000 |  | 127061 | 89709
| Seven initiatives were undertaken for 2002 : |  | Swiss/WWF partnership | 30000
| Implementation of recommendations for a joint initiative on invasive species in Africa. |  | UNESCO | 31770
| Establishing the National Committee for the Niger Basin in Guinea. Encouraging non-pollutant energy through |  | WWF Living Waters | 15000
| the Center for African Wetlands. Setting up the institutional mechanism for the implementation of the Convention in |  |  | 216770
Angola, Mozambique, Djibouti, Rwanda, the Seychelles, and Lesotho. Technical assistance for implemtnation of
the Convention in the above six African countries. Strengthening communication for Nigeria. Designation of Lake
Malawi/Niassa/Nyasa as a Ramsar site.
7101-000 | Interpretation for Sub-Group on COP8, 15-17 May 2002 in Gland |  | Spain, Min. of Environment | 32852 |  | 12150 | 20702
Spain has offered to pay for English, French and Spanish interpretation for the meeting
of the Sub-Group on COP8.
7102-000 | Review and refine of the CBD programme of work on the biological diversity of inland water ecosystems. |  | Wetlands International | 117000 |  | 117000 | Closed
| A joint agreement funded by Wetlands International through their Conservation and Wise Use of Wetlands - Global | [5 empty] | 06.09.02
Programme, to review current knowledge of the status and trends of the biological diversity of inland water eco-
systems, its uses and threats; and to identify gaps in information. The projects objectives also included the
evaluation of progress in the iplementation of the current CBD PoW, and the review and refinement of the PoW.
7103-000 | Transboundary Management of Ramsar & World Heritage Site |  | Belgium, Wallonne Region | 20000 |  |  | 20000
Ramsar is supporting training for this five-year, 30 million Euro European Commision funded project involving 8
African countries surrounding the "W" area of the Niger River Basin. It comprises a wetland complex covering over
100,000 hectares, including two existing Ramsar sites (Burkina Faso & niger) and one potential site (in Benin).
7104-000 | High Altitude Wetlands/Lakes Workshop in Urumqi, China |  | WWF - Living Waters Progm. | 45861.85 |  | 9790.5 | 36071.35
A workshop was held in Urumqi in mid August 2002, to support the preparation, printing and publication of the
Country Report. Eight participants were sponsored. A second workshop will be held before the end of the year
7105-000 | Participatry management Network Service - PMNS |  | Sweden - SIDA | 76887 |  |  | 76887
SIDA has provided support since 2000 for the Participatry Management Clearinghouse on natural resources.
It is a joint service of IUCN, Ramsar and WWF. Its aim is to improve the flow of information and knowledge and
to share lessons on participatry management of natural resources. The present project is to consolidate the
global PMC website in English and SIMP in Spanish.
7500-000 | (SGF) Small Grants Fund for Wetland Conservation and Wise Use |  | Carried forward for previous years* | 304676 |  | 113939.52 | 190736.48
Assistance for wetland conservation and wise use initiatives in developing countries and countries with economies in transition. The Fund's resources are being directed to small-scale projects not traditionally covered by larger funding agencies. Some of the funds in the project reflect 25th Anniversary Pledges.
|  |  | 1999 Income Received | 634970 |  | 563109.84 | 71860.16
Austria, Belgium, Denmark, EHCSP, Japan, Monaco, United Kingdom, USA, WWF Int'l, and Core Budget.
* Funds from previous years are all committed for second payments to contracts.
7500-500 | 1999 Small Grants Fund
Fourteen projects were funded and Japan supported a project in Nepal and Switzerland (DEZA) funded a project in Armenia.
|  |  | 2000 Income Received | 400166 |  | 350808.7 | 49357.3
Austria, Denmark, Iceland, Ireland, Japan, Sweden-SIDA, United Kindom, USA and and the 1999 Core budget surplus.
7500-600 | 2000 Small Grants Fund
Eight projects were funded through the Grant, and OMPO co-funded a project in Niger-Togo.
7500 - 700 | 2001 Small Grants Fund |  | Austria | 12000
| Forty good quality proposals were submitted in response to the 2001 call for proposals. There were nine submitted from the African Region, 6 from the Americas, 8 from the Asian regional, 16 from the European region and one from Oceania. In total these projects amounted to CHF 1,325,121. The Standing Committee approved nine projects for a total of CHF 327,890 of available funds. |  | Germany, Fed. Min. for Environ. | 45216
|  |  | Japan - Min. of Foreign Affairs | 99678
|  |  | UK, DEFRA | 49590
USA - Dept of State + Dept of
| Belgium supports a separate project which tracks the Black Stork Flyways. |  | Interior, Fish & Wildlife Service | 126275
| WWF - Living Waters Programme is supporting a project in Mongolia. |  |  | 332759 |  | 270393.53 | 62365.47
| WWF International took over two projects in Morocco and Algeria. |  | SEPARATELY FUNDED PROJECT:
| DGIS and Wetlands International took over three projects in Bulgaria, Belarus and the Slovak Republic. |  | WWF - Living Waters | 7000
PROJECTS TAKEN OVER:
|  |  | WWF International | 80000
|  |  | DGIS / Wetlands International | 113979
7500-701 | SGF - Coral Reefs
| The USA provided separate funding to promote projects specifically involved in protecting Coral Reefs. |  | USA, Dept of State | 40000 |  | 32000 | 8000
7500-610 | SGF - Black Storks - Flyways Project |  | Belgium, Wallonne District | 40000 |  | 20000 | 20000
7500-710 | The Belgian Wallonne District is continuing to support a long-term study which tracks the flyways of the |  | 2000 & 2001
Black Stork between Europe and Africa.
7500-800 | 2002 Small Grants Fund |  | Austria - Min. Land, Forestry, Env. | 12206 |  |  | 277472.6
| To date we have received 56 proposals from 37 countries, requesting a total of 2,057,977 swiss francs in aid. |  | Sweden - SIDA | 153775
|  |  | USA - Dept of State & Dept of Int. | 111492
|  |  | TOTAL | 277473