## Sheet1
ID | Institution | Type | Requirement | Phase 1 Implementation | Plan Task ID | Implementation Complete
1 | NSC | Preparation | Will need to use either UNR or UNLV data (rules) to get started). | No. Not planning to use DARwin until after phase 1.
2 | NSC | Preparation | Need to know what prep work has to be done | No. Not planning to use DARwin until after phase 1.
3 | UNR, UNLV | Preparation | Data cleanup that needs to occur in SIS before loading to DARwin | Yes | 50
4 | CCSN | Preparation | Change suffix in class name from * to R or S (Or some other code) | Yes | 40
5 | ALL | Function | Retain current functionality available in DARS (The data will not be real time) | Yes | 104
6 | ALL | Function | Performance measurements | Yes | 104
7 | WNCC, GBC, UNLV | Function | Specify web features that will be included in first release | Yes(If we go with 3.0, all features will be available to DARS staff, advisors faculty)(Not available for students until after phase I) If 3.5 (Same as above except we may not include the 3rd party software) | 53
8 | WNCC, GBC, UNR, TMCC, UNLV | Function | Need the ability to view other institution's data and to clone that data | Yes (This is provided by the import and copy features of DARwin) | 104
9 | GBC, UNR, UNLV | Function | Ability to run a DARS for a student at one institution at another Nevada institution. | NO (DARwin does not support this)
10 | GBC | Function | Ability to print color reports | Yes (This is a feature of DARwin but it is necessary to encode the use of color intor your rules) | 104
11 | GBC | Function | Ensure batch loads of data work properly | yes | 104
12 | GBC | Function | Need to be able to do Title Matching | Yes | 104
13 | UNR, UNLV | Function | Would like students, faculty, and advisors to have what-if access to DARwin | Yes for Faculty and Advisors (Students will not have the functionality until after phase I) | 104
14 | UNLV | Function | Want students, Faculty , and advisors to be able to view articulation via the web (Transfer Articulation Database) | Yes (Faculty and Advisors can view via DARwin Web interface. Students will have access to XNET reports) | 104
15 | UNR, UNLV | Function | Would like to be able to do mass comparisons between catalogs. | Yes (This is something that can be done with DARwin but would be implemented by the DARwin encoders) | 104
16 | UNLV | Function | Ability to use/run DARwin as NCAA Eligibility, ABET Engineering & Veterans Certification Audits. | Yes (This is something that can be done with DARwin but would be implemented by the DARwin encoders) | 104
17 | UNLV | Function | DARwin needs to pull degree audits on a specific teaching field (Secondary Education BS & BA programs have 42 teaching fields to choose from). Currently, these are encoded as Marker Requirements & run/done via individual EXCeptions. | NO (Phase II This would be done via system exceptions)
18 | UNR, UNLV | Function | Need smooth and timely transfer of data for new admits (affects registration) | Yes | 104
19 | UNLV | Function | DARwin needs to be able to handle split credits & composite grades particularly when repeated/retaken. | Yes (If DARwin offers this feature or Miami will code) | 104
20 | UNLV | Function | DARwin should process in line w/UNLV repeat/retake policy & give priority to the most recent transfer grade, regardless if taken at 4 year or 2 year institution. | Yes (If DARwin offers this feature or Miami will code) UNLV will work with Miami on this | 45, 104
21 | UNLV | Function | DARwin to handle UNLV's INComplete policy particularly in the articulation of INComplete transfer course (e.g. I = F if not completed by end of following regular semester). | This has been put on hold. Probably a phase II item.
22 | UNLV | Function | DARwin needs to be able to handle UNLV's Repeat/Retake Policy. | Yes (If DARwin offers this feature or Miami will code) UNLV will work with Miami on this | 45, 104
23 | UNLV | Function | DARwin to handle UNLV's 'blank' grades, whether I/IP (in progress) 'blank' grades or 'zero' credit LAB blank grades. DARwin to accurately calculate GPA & total Credits. Currently, DARS inaccurately calculates GPA, assumes 'blank' grade as 'F' & arbitrarily adds or assigns credit (to what must remain 'zero' credit). | This has been put on hold. Probably a phase II item.
24 | UNLV | Function | DARwin to handle really old courses, particularly the ones that used to have credit/count & now have converted to remedial 'zero' credit courses. E.g. MAT 100 (= 3 credits: prior to 19921), MAT 112 (= 3 credits: 19922-19962) now equate to MAT 096 (= 'zero' credits: 19963-9999). Currently, if a student took MAT 100 or MAT 112 during those inclusive date ranges, SIS is correct giving them 3 credits, however DARS 'zeros' out credit. | Yes (If DARwin offers this feature or Miami will code) UNLV will work with Miami on this
25 | UNLV | Function | DARwin to handle retaken old courses (particularly combined with transfer courses). Currently, DARS will process the repeat once, then SIS will process it again, ending up with credit shortage. | Yes (If DARwin offers this feature or Miami will code) UNLV will work with Miami on this
26 | UNLV | Function | course title of transfer articulated courses needs to be in the degree audit reports | Yes. You will need to be setting COM.TEXTLIMIT to support reporting a course title, and COM.TEXTPNT2=Y. COM.SETCTITLE should be Y or R (either appropriate). If they enter the title with the source course, and use the defaults that we send out, the target course will get that source course title and report on the audit without difficulty. | 104
27 | UNLV | Function | Want to be able to load all transfer courses into DARwin. | Yes (will need to work out a way to archive these after a while) | 104
28 | UNR, UNLV | Function | Would like to use DARwin to show students what courses they need to graduate. | Yes (This is something that can be done with DARwin but would be implemented by the DARwin encoders) | 104
29 | UNLV | Interfaces | Need an interface between STARRS and DARwin | We will investigate what would be required.
30 | TMCC, WNCC, GBC, UNLV | Data | Need Nevada Only Electronic transcripts added to DARS | Yes | 81
31 | TMCC | Data | Will load the last three semesters of data. | Yes | 49, 71
32 | GBC, UNLV | Data | A process to check exception processing. Possibly reports in SIS and DARwin? | Yes (This will be a report that compares totals of records exported from SIS and imported to DARwin) | 68
33 | GBC, WNCC | Data | Load the 1998 students to the present | Yes | 49, 71
34 | UNLV | Data | Load from Spring 2002 plus new admits | Yes | 49, 71
35 | CCSN | Data | Load students that have a certain amount of credits, not older than 1997 and new students from the last three semesters | Yes | 49, 71
36 | UNR, UNLV | Data | Load STUD records and APPL records | Yes | 49, 71
37 | TMCC, WNCC, GBC, UNR, UNLV | Data | Need a way to flag students to be uploaded to DARS. | Yes | 72
38 | GBC, UNR, UNLV | Data | Pull additional data from SIS into DARwin (See infoman ticket) | NO (There is no place to put the additional data in the conversion programs)
39 | SCS | Data | List of customizations to be added after a base install of DARwin | Yes (The only customizations to DARS have been in increasing sizes in the COM table.) | 55
40 | UNR, UNLV | Data | Add Catalog year to DARwin for Minors | Yes (If DARwin offers this feature or Miami will code) | 104
41 | UNR, UNLV | Data | Need a way to handle courses that are so old they want to remove them from the catalog but leave them in DARwin | Yes (If DARwin offers this feature or Miami will code) | 104
42 | UNR, UNLV | Data | Would like SCS help to re-sort and convert Encoding data. | Yes | 51
43 | GBC, UNLV | Reporting | The current Focus reports must be available in DARwin. | Yes (If the data is still in SIS use Focus otherwise you must use an ODBC compliant reporting tool) | 104
44 | ALL | Reporting | Would like to be able to print directly to a PC printer of their choice. | Yes | 100, 104
45 | TMCC, UNLV | Format | The text on the top and bottom of the page should be different for graduated students vs. non-grads | Yes | 104
46 | TMCC, WNCC, GBC, UNR, UNLV | Format | Branding on Web Interface | Yes | 99
47 | GBC | Format | Change branded name form RAD to DARS | Yes | 99
48 | UNLV | Security | Would like to be able to set up their own security. | Yes (If UCCSN Auditors and Campus Agree) | 57
49 | ALL | Education/Training | Attend training offered by Miami | Yes (Contingent upon financing and availablilty) | 41, 42
50 | SCS | Education/Training | DARS person at SCS needs training for basic understanding | Yes | 41, 42
51 | UNR, UNLV | Education/Training | Does Exception processing in DARwin allow for catalog years (currently SIS does not) | Yes In a course sub, you can identify a particular occurrence of a course by year/term. In a course generation type of exception, you can create a course waiver or hours waiver with a date, and in requirement modifications, you can add courses with dates to a sub-requirement, or add or remove a date from an existing SELECT/NOT FROM course, or you can change a date range on a SELECT/NOT FROM course. | 104
52 | UNR, UNLV | Education/Training | Need to understand how the COM table will work | Yes | 114
53 | UNLV | Education/Training | Need to understand how GradeMaster Table & System Condition Codes work | Yes (Will ask Miami to cover this in training) | 114
54 | WNCC, GBC | Education/Training | Would like to see the Miami screen to screen comparison of DARS to DARwin | Yes | 21
55 | TMCC, GBC, WNCC, UNR, UNLV | Testing/Transition | Need a testing plan | Yes | 105, 106
56 | GBC, WNCC, UNLV | Testing/Transition | Some testing should occur away from their offices | Yes | 115
57 | UCCSN | Testing/Transition | Help with test scripts | Yes | 106
58 | TMCC, UNLV | Information/Communication | DARS reports emailed to students on some regular basis (email with link to DARS XNET) | Yes DARS reports for students will still be available via student web | 89
59 | GBC, UNLV | Information/Communication | Link from a Deficient class listing in DARwin to registration in SIS | No (Can not implement until J2K)
60 | UNR, UNLV | Information/Communication | Catalog comparisons available to students and advisors on the web | Yes for Advisors (Students will not have this functionality until after phase I) | 90, 104
61 | UNR, UNLV | Information/Communication | Direct Read only access to DARwin tables for IT staff | No (Will implement after phase1 when performance and server availablilty can be assesed)
62 | WNCC, GBC | Support | What needs to be funded by each institution | Yes