## upgradeDIAGRAM
NOTE: When PeopleTools are mentioned for purposes of end users we are referring to TREES, QUERIES, SECURITY
All other data is referred to as non-peopletools data.
Building of SF75GOLD on 9/28 after 8:00 p.m.
A copy of SFS is made and renamed SF75GOLD.
From this point all SFS PeopleTool changes are frozen. That doesn't mean you "can't" change
SFS PeopleTools, that means you must keep track of what you change, so when we go live you can "re-do"
all of the changes in the new 7.5 SFS. Another option is you can update SF75GOLD at the time you update
SFS. That's what we plan on doing with security requests. Please refer to the SFS IS FROZEN - CHECKLIST.doc
A copy of SFS is made and renamed SF75GOLD. The DBA performs all the upgrade steps to convert the dbase to version 7.5
BUILDING OF SF75GOLD
|  | Convert ALL the |  | Call the database
| SFS | SFS |  | SF75GOLD
| is copied on Sept. 28 | data and tools into
| PeopleTools are | version 7.5 |  | This will be the master copy of all
| frozen at this time |  |  | Peopletools. Treat this dbase like
| meaning dual main |  |  | you would treat SFS for Queries and trees.
If you change your password here, this
will be your password on GO LIVE.
Building of the new 7.5 SFS database the weekend of Thanksgiving
This database is created by merging the "non-peopletools" data from SFS with the PEOPLETOOL data in SF75GOLD,
giving you your upgraded 7.5 SFS database. See below for a more detailed list of what we are calling
accounting data vs peopletool data
BUILDING OF SFS version 7.5
| SFS |  |  |  | SF75GOLD
| as of Nov 21 |  |  |  | as of Sept 28
| Accounting data pulled from SFS: |  | PeopleTool data pulled from SF75GOLD:
| All transaction data |  |  |  | Trees
| All cfields - Orgs, Accts, Projects, etc.. |  |  |  | Queries
| nVision Report Requests and scope definitions |  |  |  | Security
| Combination edit rules |  |  |  | Cutom UW panels
| Allocations |  |  |  | Online customizations
Operator preferences
Locations
Vendors
Customers
Business Unit settings
such as "as of date",
closed acctg periods
active combo edit rules
MERGE SFS DATA WITH SF75GOLD AND YOU GET
UPGRADED 7.5
SFS