## Sheet1
Massachusetts Aquatic Invasive Species Management Plan Implementation Table
Tasks/Actions |  |  | Funding Source (current) |  |  | Implementing Entity | Cooperating Entity | Recent Efforts ($/FTEs) |  |  |  | Planned Efforts ($000/FTEs)
[8 empty] | FY '00 |  | FY '01 |  | FY '02 |  |  |  | FY '03 |  |  |  | Future Needs (beyond FY '03) | Budget Justification
Task # | Task Description | year | state | federal | other |  |  | $ (000) | FTE | $ (000) | FTE | dedicated |  | seeking |  | dedicated |  | seeking |  | $(000)/yr
[12 empty] | $ (000) | FTE | $ (000) | FTE | $ (000) | FTE | $ (000) | FTE
1A1 | Dedicate 2.65 full time (equivalent) AIS coordinators | 1 | DEM | NOAA/Sea Grant/EPA |  | DEM/CZM/MBP |  |  |  | 45 | 0.75 | 84 | 1.4 | 75 | 1.25 | 84 | 1.4 | 75 | 1.25 | 75 | Equivalent of 2.65 FTE will be dedicated to implementing the AIS plan
1A2 | Organize four AIS Working Group Meetings annually | OG |  |  |  | DEM/CZM/MBP
1A3 | Meet with member groups of the MA Council on Invasive Species annually | 1, OG |  |  |  | AIS Working Group/ MA Council on Invasive Species
1B1 | Co-Chair and staff Northeast Regional Panel | 1 |  | NOAA |  | CZM | MIT Sea Grant/GOMC/DEM/MBP |  |  |  |  | 25 | 0.25 |  |  | 25 | 0.25 |  |  |  | Funding will support travel and administrative costs for Panel Co-Chair and staff
1B2 | Participate in AIS workshops | OG | DEM | NOAA/EPA |  | DEM/CZM/MBP | [14 empty] | Task to be carried out by Coastal and Freshwater AIS Coordinators
1B3 | Share educational resources | 1,OG |  | NOAA |  | AIS Working Group/DEM/MIT Sea Grant/NIPGro |  |  |  | 60
1B4 | Sponsor Marine Bioinvasions Workshop | 1 |  |  |  | MBP | MIT Sea Grant/Northeast NEPs |  |  |  |  | 12 | [8 empty] | Workshop contingent on receipt of funding from EPA
1C1 | Participate in ANS Task Force Meetings | OG |  | NOAA |  | CZM | AIS Working Group |  |  | 1 |  | 3 |  |  |  | 3 |  |  |  |  | AIS Coordinators and AIS Working Group members will participate in ANS Task Force meetings: dedicated funding includes travel costs
2A1 | Report on results of MA Transport Vector Study | 1 |  | NOAA | Williams College/North-eastern University | Smith/Williams/MIT Sea Grant/Northeastern | [5 empty] | 270
2A2 | Report on results of New England Transport Vector Study | 1 |  | NOAA | Williams College/North-eastern University | Smith-Williams-MIT Sea Grant |  |  |  | 207
2A3 | Expand Transport Vector Study to include additional pathways of introduction | 2 |  | NOAA | Smith/MIT Sea Grant | Smith/Williams/MIT Sea Grant | [5 empty] | 60 |  |  |  | 60
2A4 | Assess need to expand task 2A1 to freshwater systems | 1 |  |  |  | AIS Working Group
2B1 | Establish transport vector focus groups | 1 |  | NOAA/EPA |  | Smith/Williams/MIT Sea Grant/Northeastern/MBP | [5 empty] | 10
2B2 | Establish transport vector working groups of task 2B1 | 2,OG |  |  |  | MBP/AIS Implementation Committee | [14 empty] | Coastal AIS Coordinators will take the lead in Working Group development
2C1 | Identify educational needs through working groups of Task 2B1 | 2 |  |  |  | AIS Working Group
2D1 | Develop a regional AIS database | 1 |  | NOAA/Sea Grant |  | CZM/NE Regional Panel | [5 empty] | 31 | 0.2
2D2 | Maintain a freshwater invasive species database | 1 |  |  |  | DFW/DEP/DEM
2E1 | Develop a ballast water database | 1,2 |  | NOAA |  | MIT Sea Grant/Massport |  | 3 |  | 4 |  | 4 |  | 5 | [6 empty] | Funding will support one student to assist with data management and steering committee meetings (task 2E2)
2E2 | Convene a ballast water steering committee | 1 |  | NOAA |  | MIT Sea Grant/Massport | [5 empty] | 25
2E3 | Assemble ballast water reporting information | og |  |  |  | Massport/USCG
2E4 | Develop a ballast water outreach plan | 2 |  |  |  | MIT Sea Grant/Massport
2E5 | Recommend additional ballast water management practices/legislation | 2 |  |  |  | CZM/MBP, MIT Sea Grant | [11 empty] | 10 |  |  | Funding will support one research assistant
2F1 | Update and post boating related AIS signage | 1,2 | LPI |  |  | DEM | [5 empty] | 13.5
2F2 | Distribute AIS outreach materials to lake and pond associations | OG | LPI |  |  | DEM |  |  |  | 8 |  |  |  | 12 | [6 empty] | Funding will support printing and distribution costs
2F3 | Distribute AIS education materials with boater registration forms | 2 |  |  |  | DEM/DEP/DFWELE | [11 empty] | 10 |  |  | Funding will support printing and distribution costs
2F4 | Distribute AIS education materials through Public Access Boards | 2 |  |  |  | DEM/CZM/MBP
2F5 | Install a pilot boat wash station | 2 | LPI |  |  | DEM | [5 empty] | 4.5 |  | 20 |  |  |  | 20 |  | 2 | Funding will support installation of a boat wash stations and staff time for maintenance and management
2F6 | Evaluate capacity for an AIS inspection program | 2 |  |  |  | DEP/DFW | [7 empty] | 15 | 0.2 |  |  | 15 | 0.2 |  | Funding will support staff time for scoping and development of inspection program
2G1 | Develop a seafood industry species list | 1 |  |  |  | Smith/Williams/MIT Sea Grant/CZM/MBP/DMF | [7 empty] | 5 | [6 empty] | Funding will support an intern to research seafood sales and imports
2G2 | Develop guidance on packing materials | 1 |  |  |  | CZM/DMF/MIT Sea Grant | [7 empty] | 5 | [6 empty] | Funding will support an intern to research use of live packing materials and develop/distribute educational materials
2H1 | Hire a shellfish pathologist | 1,OG |  |  |  | DMF | [7 empty] | 40 | 0.5 |  |  | 40 | 0.5 | 40 | Funding will support one half time shellfish pathologist
2H2 | Research proper shellfish disposal/disinfection | OG |  | NOAA |  | CZM | DMF |  |  | 7 | 0.1 | 7 | 0.1
2H3 | Evaluate nonindigneous fish stocking practices | 3 to 5 |  |  |  | AIS Working Group
2I1 | Encourage proper bait disposal | 1 | DMF |  |  | DFW/DMF | [5 empty] | 7 | 0.1 | 5 | [6 empty] | Funding will support printing and distribution costs
2J1 | Develop a pet store/water garden strategic plan | 1 |  |  |  | AIS Working Group
2J2 | Continue Noxious Weed List inspections | OG | DFA |  |  | DFA |  | 30 | 0.5 | 30 | 0.5 | 30 | 0.5 |  |  | 30 | 0.5
2J3 | Evaluate DFA authority to update the MA Noxious Weed List | 1 |  |  |  | DFA
2J4 | Annually update the MA Noxious Weed List | 2,OG |  |  |  | DFA/AIS Working Group/MIPG | MIPG/AIS Working Group
2J5 | Evaluate DFWELE authority to create lists of invasive plants in natural areas | 1 |  |  |  | DFWELE/DFW
2K1 | Develop reporting system for import of organisms for research | 2 |  |  |  | CZM/MBP/DMF | NEAMGLL
2K2 | Develop BMP's for discharge of wastewater from research facilities | 1 |  |  |  | AIS Working Group
2K3 | Encourage implementation of BMP's developed in task 2K2 | 3to5 |  |  |  | AIS Working Group
2L1 | Identify live organism supply companies | 1 |  |  |  | CZM | [7 empty] | 5 | [6 empty] | Funding will support an intern to research import of organisms through research supply companies
2L2 | Recommend controls for the Internet trade to the ANS Task Force | 2 |  |  |  | AIS Working Group
2L3 | Identify guidelines for shipping and disposal of nonindigenous organisms | 3to5 |  |  |  | AIS Working Group
3A1 | Continue Rapid Assessment Surveys | 3to5 |  | NOAA/EPA |  | MIT Sea Grant/MBP/CZM |  |  |  | 90 | 0.5
3A2 | Conduct an assessment of intertidal, benthic habitats | 1.2 |  | EPA |  | MBP/MIT Sea Grant/CZM | [5 empty] | 50 | [8 empty] | The Rapid Assessment Survey is contingent on funding of a current proposal to EPA
3A3 | Train volunteers to monitor for AIS | 2 |  |  |  | MBP/CZM | [11 empty] | 10 |  |  | Funding will support workshop development and training costs
3A4 | Develop an AIS monitoring strategy | 2 |  |  |  | AIS Working Group
3B1 | Continue lakes and ponds assessments | OG | DEP |  |  | DEP/DEM |  | 50 | 1 | 50 | 1 | 150 | 3 | 50 | 0.5 | 150 | 3 | 50 | 0.5 | 50 | Funding will support field staff time, equipment, and data management and reporting costs
3B2 | Establish a MA Weed Watcher Program | 1 |  |  |  | DEM
3B3 | Dedicate staff to the management of an aquatic plants database | 2,OG |  |  |  | DEP | [11 empty] | 90 | 1 | 45 | Funding will support staff time for data development and management
3B4 | Continue to monitor AIS infested sites containing rare species | OG |  |  |  | DFW
3C1 | Evaluate remote sensing technology for AIS monitoring | 2 |  |  |  | USGS | DEP/DEM
4B1 | Assemble a Lakes and Ponds Emergency Response Team | 1 | LPI |  |  | DEM/DEP | EOEA/DFW |  |  |  |  | 60 | 1 | 75 |  | 60 | 1 | 75 |  | 75 | Funding will support the acquisition of AIS control technologies and staff time to manage the Emergency Response Team
4B2 | Coordinate with Weed Watcher Groups to identify early infestations | 1 |  |  |  | DEM/DEP | EOEA/DFW
4B3 | Coordinate with DFW to identify AIS control/endangered species conflicts | 1 |  |  |  | DFW/DEM/DEP
4B4 | Train DMF field staff to identify AIS | 1 |  |  |  | DMF/CZM | [7 empty] | 10 | [6 empty] | Funding will support staff time and workshop costs
4B5 | Seek resource to develop a Coastal Emergency Response Team | 2 |  | NOAA |  | CZM/MIT Sea Grant/MBP | DMF | [8 empty] | 12 | 0.2
4C1 | Identify agency responsibilities for eradication | 2 |  |  |  | AIS Working Group
4C2 | Identify response protocols for priority invaders | 1 |  |  |  | AIS Working Group
4C3 | Generate a list of unregistered pesticides for AIS controls | 2,OG |  |  |  | AIS Working Group | DFA
4C4 | Develop an MOU for implementation of response protocols | 3to5 |  |  |  | AIS Working Group | MA Agencies
4C5 | Develop a facilitated permitting process through the Herbicide Licensing Program | 2 |  |  |  | DEP/DFA | [7 empty] | 45 | 0.5 |  |  | 45 | 0.5 | 22.5 | Funding will support staff time for technical assistance, review and oversight
4D1 | Conduct risk assessments of priority species introductions | 2 |  |  |  | AIS Working Group | [11 empty] | 30 |  |  | Funding will support a student researcher to conduct risk assessments
5B1 | Support research on the biological control of AIS | OG |  |  |  | AIS Working Group
5B2 | Continue biological control of purple loosestrife | 1,OG | WRP |  |  | WRP |  |  |  | 7 |  |  |  | 2 |  |  |  | 2 |  | 2 | Additional funds will purchase beetle rearing equipment and supplies
5C1 | Develop protocols for updating priority AIS species lists | 1 |  |  |  | AIS Working Group
5C2 | Develop protocols for identifying priority sites for management | 1 |  |  |  | AIS Working Group
5D1 | Compile available AIS control technologies | 1 | DEM |  |  | DEP/DEM |  |  |  | 25 |  | 25
5D2 | Implement lakes and ponds demonstration projects | 1 |  |  |  | DEM | EOEA |  |  |  |  | 440 |  |  |  | 440
5D3 | Train groups in use of AIS control technologies | 2 |  |  |  | DEM
5D4 | Include reintroduction of native plants in GEIR | 1,OG | DEM |  |  | DEM
5E1 | Make funds available for lakes and ponds restoration efforts | 2 |  |  |  | DEM | EOEA |  |  | 250 |  | 250 |  |  |  | 250
5F1 | Include a monitoring requirement in Herbicide Licensing Program | 2 |  |  |  | DEP | [7 empty] | 10 | 0.2 |  |  | 10 | 0.2 | 5 | Funding will support staff time for development of monitoring component and ongoing program management
5F2 | Monitor effectiveness of Lake and Pond AIS control techniques | 2 |  |  |  | DEM | EOEA | [6 empty] | 5 |  |  |  | 5 |  | 5 | Funding will support staff time for monitoring program development
5F3 | Include monitoring requirement with AIS control grants | 2 |  |  |  | DEM | [5 empty] | 6 | 0.1 |  |  | 6 | 0.1
5F4 | Monitor effectiveness of loosestrife biocontrol efforts | OG |  |  |  | WRP |  |  |  | 1 |  |  |  | 9 |  |  |  | 9 |  |  | Funding will support the purchase of two Global Positioning System for loosestrife population mapping
5G1 | Continue Water Chestnut Control Efforts | OG | NFWF |  |  | Silvio O. Conte Refuge |  | 56 |  | 44 |  |  |  | 65 |  |  |  | 65 |  | 30 | Funding will support staff time to coordinate harvesting efforts, and acquisition of mechanical harvesting tools
6A1 | Maintain the MIT Bioinvader Web Page | OG |  | NOAA |  | MIT Sea Grant |  |  |  | 5 |  | 5 |  |  |  | 5
6A2 | Develop a Northeast Regional Panel Web Page | 2 |  |  |  | NE Regional Panel
6A3 | Maintain the Lakes and Ponds Strategy web page | 1, OG |  |  |  | EOEA
6A4 | Develop an AIS slide presentation | 1 |  |  |  | AIS Working Group/CZM/DEM
6B1 | Distribute "Hitchhiker" ID cards | 1 |  | NOAA | Mass Audubon | MIT Sea Grant |  |  |  | 12.5 |  | 12.5
6B2 | Distribute "A Guide to Selected Invasive Non-Native Species in Massachusetts" | 1 | DEM |  |  | DEM |  |  |  | 18
6B3 | Distribute "A Guide to Aquatic Plants in Massachusetts" | OG |  |  |  | DEM/New England Aquarium
6B4 | Develop a portable invasive species exhibit | 1 | EOEA |  |  | EOEA | [5 empty] | 3.5
6C1 | Develop and distribute an aquarium AIS poster series | 1 |  |  |  | CZM/DFA | [7 empty] | 10 | [6 empty] | Funding will support development, printing, and distribution costs
6C2 | Develop a native species landscape model | 1 |  | NOAA |  | CZM | [5 empty] | 25 | [8 empty] | Funding will support development, printing, and distribution costs
6C3 | Distribute ballast water education materials | 2 |  |  |  | MIT Sea Grant/Massport | [11 empty] | 10 |  |  | Funding will support printing and distribution costs
6C4 | Distribute the "Stop the Spread of Invasive Species" poster | 1 | LPI |  |  | DEM | [5 empty] | 10
6C5 | Sponsor an AIS booth at gardening exhibitions | OG |  |  |  | AIS Working Group | EOEA | [6 empty] | 10 |  |  |  | 10 |  | 10 | Funding will support travel expenses, printing, and distribution costs
6C6 | Present AIS issues to the Coastal Caucus of Legislators | 3to5 |  |  |  | AIS Working Group
7A1 | Identify AIS research priorities | 2 |  |  |  | AIS Working Group | MIT Sea Grant
7A2 | Support an AIS graduate fellowship | 2 |  |  |  | AIS Working Group | [11 empty] | 20 |  | 20 | Funding will support one graduate fellowship annually
7A3 | Communicate AIS research needs to the scientific community | 1,OG |  |  |  | AIS Working Group
8A1 | Evaluate authority to prohibit invertebrate imports | 2 |  |  |  | CZM | AIS Working Group | [6 empty] | 10
8A2 | Develop a regulatory strategy to limit the introduction of priority species | 2,OG |  |  |  | AIS Working Group
8B1 | Biennially evaluate regulatory needs | 2,OG |  |  |  | AIS Working Group
| Totals | [6 empty] | 139 | 1.5 | 864.5 | 2.85 | 1623 | 6.65 | 488 | 3.15 | 1125 | 6.45 | 601 | 4.15 | 381.5
| total match (FY02-FY03) | $ | 2748000
| total sought (FY02-FY03) | $ | 1089000
Acronyms
AIS | Aquatic Invasive Species
ANS | Aquatic Nuisance Species
BMP | Best Management Practice
CZM | Massachusetts Office of Coastal Zone Management
DEM | Massachusetts Department of Environmental Management
DEP | Massachusetts Department of Environmental Protection
DFA | Massachusetts Department of Food and Agriculture
DFW | Massachusetts Division of Fish and Wildlife
DFWELE | Division of Fish Wildlife and Environmental Law Enforcement
DFWELE | Division of Fish and Wildlife
EOEA | Massachusetts Executive Office of Environmental Affairs
EPA | US Environmental Protection Agency
GOMC | Gulf of Maine Council
LPI | Massachusetts Lakes and Ponds Initiative
MBP | Massachusetts Bay National Estuary Program
MIPG | Massachusetts Invasive Plant Group
MOU | Memorandum of Understanding
NEAMGLL | Northeast Association of Marine and Great Lakes Labs
NEP | National Estuary Program
NIPGro | New England Invasive Plant Group
NFWF | National Fish and Wildlife Foundation
NOAA | National Oceanic and Atmospheric Administration
OG | Ongoing
USGS | US Geological Survey
WRP | Massachusetts Wetlands Restoration Program