## current_investments
Section 4: Current Projects/Investments
-- Last revised: March 27, 2000
The table below presents summary information for each current investment (approved/funded but not completed). Maintenance activities are not included. The status of each project is indicated by the green/yellow/red color coding for project objectives (Description/Purpose), budget (Cost Estimate and FTEs), and schedule. (NOTE: "Project Status" and "IT Goal Supported" are not included in this revision.)
Title | Description/ Purpose | Cost Estimate | FTEs | Schedule |  | Scope/ Risk* | Business Driver/ Strategy Supported | IT Goal Supported |  |  | Executive Sponsor | Project Manager
[8 empty] | Integration | Access | Efficiency
Desktop
Automated desktop hardware and software inventory system acquisition and Y2K inventory | Provide Ecology with inventory across the network and check hardware and software Y2K readiness. |  | 0.25 | Install SMS software , test and run inventory in February 2000 |  | Agency / Low risk | Provide accurate and timely inventory of all PC and the hardware and software across the agency. This software will also do a Y2K check and prove data on any risks. |  |  | X | Carol Fleskes, AS Mgr. 360-407-7012, cfle461@ecy.wa.gov | Mary Ellen Bradley, CCS Mgr. 360-407-6670, mbra461@ecy.wa.gov / Ginnie Schiendleman
Automated desktop software distribution system acquisition | Implement software distribution across the network. | 0 | 0.2 | Rollout of first product to the desktop is scheduled for March 2000. |  | Agency / Low risk | Increase efficiency of delivering agency software by pushing it to the desktop. |  |  | X | Carol Fleskes | Mary Ellen Bradley
Desktop hardware upgrades (See project plan) | Upgrade 25% of desktop computers per year / 50 % each biennium | $735,000/ year | 5 | Ongoing; 350 computers are scheduled to be replaced by June 30, 2000 and 250 more by June 30, 2001. | Replaces the low end desktop with current techonolgy. | Agency / Low risk | Improve desktop units, remove PCs that will not be Y2K compliant, move to a standard PC "look and feel" |  | X | X | Carol Fleskes | Mary Ellen Bradley (Lacey Bldg); Bob Monn (Regional offices)
Network printer upgrades (See project plan) | Replace old printers with new ones that provide enhanced capablities | $50,000/ year | 3 | 1999-2001 biennium | Upgrade old printers and provide more capabilities for printing . | Agency / Low risk | Improve printing capablities and the HQ building, reduce cost of repairing old printers. |  | X | X | Carol Fleskes | Mary Ellen Bradley (Lacey Bldg); Bob Monn (Regional offices)
Network
Remote Access Enhancement | Provide improved dial-in access to Ecology's network |  |  | Complete by April 2000 |  | Agency / Low risk | Support telecommuting and other out-of-office network access |  |  |  | Carol Fleskes | Gordon Brooks and Bob Monn
Install new server for Exchange System | Move approximately 300 users from the existing two servers at HQ. |  |  | Complete by March 2000 |  | Lacey Building (ie. HQ and SWRO) / Low risk | Lessen the impact of a mail server failure by spreading the users across three servers instead of two. |  |  |  | Carol Fleskes | Gordon Brooks
Network concentrator upgrades (See Proposed 1999-2001 IS Budget**) | Replace aging network backbone equipment on 6 year cycle |  |  | Complete by December 31, 2000 |  | Agency / Low risk | Maintain current network reliability |  |  |  | Carol Fleskes | Gordon Brooks and Bob Monn
Network performance enhancement - implement FR or ATM (See Proposed 1999-2001 IS Budget**) | Convert wide area network links to newer technology (I.e. Frame Relay or ATM) |  |  | Complete by December 31, 2001 |  | Agency / Low risk | Improve connectivity to remote offices, enhance flexibility, and reduce monthly line charges |  |  |  | Carol Fleskes | Gordon Brooks
Telecommunications
Lacey Building PBX (See Project Authorization Package) | Convert Lacey Building phones from Centrex service provided by US West to PBX service provided by DIS. | 193000 | 0.40 Ecy; DIS proj. team | 09/2000 - 07/2001 | Requires replacement of all desk phones and change of all phone numbers in Lacey Building | Lacey Building (ie. HQ and SWRO) / Low risk | Reduce costs, improve service (faster staff/line moves), and increase features in desk phones |  |  |  | Carol Fleskes | Jerry Bentley, IRSS/telecom , 360-407-7030, jben461@ecy.wa.gov
Replace Conveyant reception desk system | Review anqiuated reception equipment, recommend replacement. | $ 133,000; installation of PBX system for HQ will reduce total cost, aprox. $30,000 | 0.25 Ecy staff | 07/2000 - 07/2001 |  | HQ and Regional Offices / Low risk | Combine current desktop standard with intrigrated voice/data reception communication system. |  |  |  | Carol Fleskes | Diane Schenk 360-407-7017/Gwendolyn Campbell 360-407-7029
NWRO Re-Wiring | Voice/data rewire of the NWRO. Current patch work of wiring systems continues to cause communication problems and reduce efficiencies in server connections. | $ 187,000 - $212,000; | 0.5 Ecy staff | 03/2001 - 06/2002 |  |  | Bring office location up to agency standards, decrease the need for outside tech assistance, improvre response time on network troubleshooting |  |  |  |  | Jerry Bentley, IRSS/telecom , 360-407-7030, jben461@ecy.wa.gov
GIS
Support and maintain the Agency GIS technical environment including UNIX servers, workstations, printers, and plotters | Provide continued access to GIS users to the agency hardware, software and applications | (Project costs below do not include FTE costs) | 0.6 | Ongoing |  | Agency / Low risk | Keep the GIS infrastructure up and running to insure agency GIS users have access to the system in order to conduct program/agency business activities |  |  |  | Carol Fleskes | Joy Denkers, GIS Mgr, 360-407-7128, jden461@ecy.wa.gov
Agency GIS server & workstation hardware maintenance | Maintenance for hardware & operating system | 34500
Agency GIS data server (HP 9000 K210) maintenance & upgrades | Memory and disk array | 16000
GIS peripheral maintenance & upgrades | Replace 6 year old primary agency plotter | 11400
Agency GIS remote access enhancements | Improve dial-in access to GIS server and continue Map Server support & development efforts | 2700
Unix workstation hardware maintenance & upgrades | Upgrade 2 UNIX workstations, new disk array, DLT library backup system | 65000
Support and maintain the agency's GIS software environment | Provide maintenance and updates to the agency's GIS software | (Project costs below do not include FTE costs) | 0.6 | Ongoing |  | Agency / Low risk | Ensure agency GIS users have access and connection to agency software in order to conduct their program/agency business tasks |  |  |  | Carol Fleskes | Joy Denkers
Desktop software upgrades & additions | ArcView, ArcPress, Adobe Suite for desktop mapping | 15900
Agency GIS software maintenance & upgrades | ArcView, Exceed, Arc/Info, SDE, Solaris, MapObjects | 87300
Provide agency-level spatial data and database support. Maintain agency statewide data, metadata and GIS Intranet and Internet sites. | Provide access and updating of GIS agency data and data descriptions. Reduce data duplication by maintaining one point of distribution. | (Project costs below do not include FTE costs) | 0.8 | Ongoing |  | Agency / Low risk |  |  |  |  | Carol Fleskes | Joy Denkers
Digital orthophoto acquisition and spatial data improvements | Obtain photos from USGS & DNR and continue to improve and update existing data | 25000
Agency Applications
Year 2000 Project | Ensure Y2K compliance |  | 0.5 | Complete by March 30, 2000 |  | Agency / Low risk | Statewide Year 2000 Effort |  |  |  | Carol Fleskes | Debbie Stewart/Kevin Barbee
EPIC - Maintenance and Enhancements | Maintain and expand the current EPIC functionality to include other high priority items | 30000 | 0.25 | July 1, 1999 to Dec. 31, 2001 |  | Agency / Low risk | Improve the management of employee information and make it accessible to a wide audience. | X | X | X | Joy St. Germain | Lynn Singleton, IIP Mgr., 360-407-6610, lsin461@ecy.wa.gov
Facility/Site Identification System (F/S ID)
F/S ID maintenance | Maintain and make minor enhancements to F/S ID | 42500 | 1.5+ | Ongoing |  | Agency / Low risk | To keep enterprise-wide system functioning as needed by the agency |  |  |  | Carol Fleskes | Lynn Singleton
GIS Access to F/S ID Data | Link tabular and spatial data to the application | 15000 |  | Ongoing |  | Agency / Low risk | To make agency data accessible to both the tabular and geospatial sides of the system |  |  |  | Carol Fleskes | Lynn Singleton
Establish a multi-state partnership to redevelop F/S ID to a web browser | The F/S ID System is mature and ready to be deployed via the Inter/Intranet | TBD |  |  |  | Agency/Medium Risk | The partnership will allow Ecology to have our redevelopment costs covered and other partners states get a system for a fraction of the cost |  |  |  | Carol Fleskes | Lynn Singleton
Migrate Department of Health Drinking Water Systems data to F/S ID | Provide access to important Watershed data to our permit writers and the public via the web |  |  | Oct 1999- Jan 2000 |  | Agency / Medium risk | Provides DOH data to our staff and to the public--decreases the number of inquiries by phone and written requests and improves our decision-making information base. |  |  |  | Carol Fleskes | Lynn Singleton
Clean F/S Data | Send a mailing to all companies in the system |  |  | TBD |  | Agency/ Low Risk | Will improve the quality and completeness of the facility data we manage. |  |  |  | Carol Fleskes | Lynn Singleton
Migrate other agency data to F/S ID, e.g. EPCRA, Wells, Water rights, solid waste fac. | Clean and move high priority facility data to F/S |  |  | July 1, 1999--June 30, 2001 |  | Agency / Low risk | Will make data available to the agency and the public and lower data maintenance costs |  |  |  | Carol Fleskes | Lynn Singleton
Migrate Air Facilities data to F/S ID | Upload the Local Air Authority Facilities to F/S ID |  |  | TBD -- |  | Agency / Low risk | Provides our Facility data to the public and decreases the number of inquiries by phone and written requests |  |  |  | Mary Burg | Lynn Singleton
(See TCP's USTBase integration project)
Environmental Information Management (EIM) System
EIM maintenance | Maintain and make minor enhancements to EIM | 42500 | 1.5+ | Ongoing |  | Agency / Low risk | To keep enterprise-wide system functioning as needed by the agency |  |  |  | Carol Fleskes | Lynn Singleton
GIS Access to EIM Data | Link tabular and spatial data to the application | 15000 |  | Ongoing |  | Agency / Low risk | To make agency data accessible to both the tabular and geospatial sides of the system |  |  |  | Carol Fleskes | Lynn Singleton
Well Log Imaging Project | Convert paper records into an electronic medium and develop a searchable data base | 25000 |  | July 1, 1999-Dec.31, 1999 |  | Agency / Low risk | Once imaged, the 300,000 well logs will be available to the EIM system and the agency in general in a non paper form. Significant file cleanup will also result from the effort. |  |  |  | Keith Phillips | Chris Anderson, Debbie Stewart
Well Logs Integrated with EIM | Integrate Well Logs with the EIM system and develop an agency-wide solution for distributing images |  |  | Jan 1, 2000-June 30, 2000 |  | Agency / Medium risk | Images need to be available to the agency and the public in a consistent and efficient manner. |  |  |  | Keith Phillips/Carol Fleskes | Lynn Singleton, Debbie Stewart, Chris Anderson
EIM Data Migration | Move high priority historical water quality data sets to EIM |  |  | July 1, 1999- Dec 31, 1999 |  | Agency / Low risk | Provides access to high priority environmental data |  |  |  | Bill Backous | Lynn Singleton
Transmit large quantities of data to partners -- EPA, cities |  |  |  | TBD |  | Agency/ Low Risk | Will improve the efficiency and transfer costs of moving data between partners |  |  |  | Carol Fleskes | Lynn Singleton
(See Air Quality Program's PM 2.5 database project)
Billing & Revenue Tracking System (BARTS) | Application redevelopment project for system to collect and track $20 million each biennium | 280000 | 1.8 | Complete by Dec 31, 1999 |  | Agency / Medium risk | Ability to track revenue for Wastewater Discharge Permits, Biosolids Permits, etc. | X | X | X | Megan White; Carol Fleskes | Debbie Stewart, ADS Mgr, 360-407-7048, dste461@ecy.wa.gov
Central Records Index and Inventory System (CRIIS) | Develop a system to automate records tracking activities of the Central Records Office |  |  | TBD |  | Agency / Low risk | Improve efficiency |  | X | X | Carol Fleskes | Bob Monn, Debbie Stewart
Enforcement Tracking System Enhancements | Streamline agency docket number processing |  |  | Complete by October, 1999 |  | Agency / Low risk | Improve efficiency | X | X | X | Tom Eaton | Debbie Stewart
Heat System - Conversion to Sybase or MS SQL | Support Agency Help Desk | TBD |  | TBD |  | Agency / Low risk | Agency Computer Support Services Help Desk Support |  | X | X | Carol Fleskes | Debbie Stewart; Mary Ellen Bradley
News Release Distribution System | Develop web-based system for the automated distribution of news releases via E-mail, FAX, and web | TBD |  |  |  | Comm & Ed / Low risk | Improve efficiency |  | X | X | Sheryl Hutchison, Communications & Education Director | Michael Sosnow
Public Review / Responsiveness Summary System | Develop web-based system for collection of public comments on draft rules | TBD | TBD | TBD |  | Intergovt. Relations / Low risk | Governor's Quality Initiative |  | X | X | Bill Alkire, Intergovt. Relations Director, 360-407-7003, walk461@ecy.wa.gov | Michael Sosnow
Air Applications
Strip Chart Replacement Software | Develop Windows NT based software to provide graphical interface to one-minute telemetered data | Funded with existing staff | 1 | Sept 1, 1999 - March 31, 2000 | Will require purchasing agency standard software development tools (about $5,000) | Air / Medium risk | Eliminates need to purchase new, expensive strip chart recorders |  | X | X | Mary Burg | Kathy Sundburg
PM 2.5 Database | New EPA reporting requirements require collecting this data. | Funded with existing staff | 0.5 | Sept 1, 1999 - March 31, 2000 |  | Air /Low | Will integrate with EIM | X | X |  | Mary Burg | Kathy Sundburg
Application conversions from Informix to MS-SQL Server | Porting Informix databases to MS-SQL server and redeveloping the associated applications as required. | Funded with existing staff | 0.25 | Complete by 12/31/99 |  | Air/ Low Risk | AQP will spend less $ in support contracts for new platform. New platform conforms to agency standards. |  |  | X | Mary Burg | Kathy Sundburg
----- Emission Check Database | A). Port Informix databases to MS-SQL server and redevelop Powerbuilder using PFC library. B). Enhancement: Integrate this database with I/M history database. | Funded with existing staff | 0.5 | a) deploy beta version by 12/31/99 b) TBD |  | Air/ Low Risk | AQP will spend less $ in support contracts for new platform. New platform conforms to agency standards. | X |  | X | Mary Burg | Kathy Sundburg
----- Site Master Database | A). Port Informix databases to MS-SQL server and redevelop Powerbuilder using PFC library. System currently has a text base user interface. | Funded with existing staff | 0.5 | BAA beginning in October, 1999 |  | Air/Low Risk | AQP will spend less $ in support contracts for new platform. New platform conforms to agency standards. |  |  | X | Mary Burg | Kathy Sundburg
EAP Applications
TMDL Milestone Database | Track progress on projects and TMDL settlement. |  | 0.1 | Complete by June 30, 2000 |  | Agency / Low risk | TMDL Settlement, intra-program integration |  |  |  | Bill Backous | Steve Barrett, 407-6673
Environmental Assessment Public Website | Re-development for better usability and ease of maintenance |  | 0.1 | Ongoing |  | Agency / Low risk | Improve usability of the site, reduce maintance socts |  |  |  | Bill Backous | Steve Barrett, 407-6673
HWTR Applications
HWIMSy - Hazardous Waste Management System | Manages data on Hazardous Waste generation and waste management | 19000 | 0.05 | on-going |  | Agency / Low risk | Essential business function to serve data users statewide and the public on hazardous waste generation and management. | X | X | X | Greg Sorlie | Dan Kruger
Turbo Waste | Personal computer application that allows companies to enter data into the system, validates the data, prints reports, and allows for electronic submittal of the data. | 5000 | 0.2 | on-going |  | Agency / Low Risk | Streamline the submission of HW Annual report data. Reports are submitted in electronic format that has been "audited" for quality assurance. Data is then able to be directly loaded into HWIMSy and available to use. We now get data from 350 companies which represents 95% of all data reported to the agency via TurboWaste. |  | X | X | Greg Sorlie | Dan Kruger
EPCRA - Emergency Planning and Community Right to Know Act | Manages data relating to toxic chemical inventories (TIER 2) and releases (TRI) to the environment as required under Federal law. We are implementing new capabilities for electronic reporting. | 40000 | 0.5 | on-going |  | Agency / Low risk | Essential business function to serve the public statewide on a community right-to-know data, including chemical storage inventories and toxic chemical releases. | X | X | X | Greg Sorlie | Bob Lemcke
HWInfo - Hazardous Waste Information | Provide a way to integrate many data sources into a simple user interface to answer most of the common business questions. This reporting tool is now used by the entire program including the regional offices, industrial section, and Nuclear waste program. | 0 | 0.5 | 1999-09-15 |  | Agency / Low Risk | Making information retrieval easier and more available in a simple user interface on every desktop. | X | X | X | Greg Sorlie | Ed Bentley
Fertilizer Database | Waste in Fertilizer database application that tracks industrial wastes used in the manufacturing of commercial pesticides. Access to the data is through the Internet. | 0 | 0.2 | completed 3/9/2000 |  | Agency / Low Risk | Allows easy access via the world wide web to the waste in fertilizer information. |  | X | X | Greg Sorlie | Ed Bentley
TRIDS | Interactive personal computer application that displays customer selected Toxic Chemical Release (TRI) data in a graphic representation format where the picture is related in size to the amount of data. This makes it simple for the public to see our information.. | primarily funded through EPA grant | 0.4 | on-going |  | Agency / Low Risk | Promotes awareness of chemical releases in our communities through a unique method of displaying Toxic Chemical Release (TRI) data. |  | X | X | Greg Sorlie | Ed Bentley
P2 Tool Box | To promote the integration of pollution prevention (P2) into all work performed by HWTR staff. | 0 |  | on-going |  | Agency / Low Risk | Provide all staff the capability to provide basic P2 opportunity information to all our clients. |  | X | X | Greg Sorlie | Judy Kennedy
HWTR Application Development Environment | Develop the infrastructure in the program for three sepeerate environments: Development, Test, and Production, along with the same environments for the intranet/intrenet. | 0 | 0.5 | completed 6/30/99 |  | Agency / Low Risk | Create a stable and reiable platform for rapid edvelopment of applciatoins for improved service to our clients. | X | X | X | Greg Sorlie | Ed Bentley
NWP Applications
Project Planning system | System to input planned hours for a 15 month period | 5000 | 0.2 | 2000-03-03 |  | NWP/Low risk | Have a streamlined data entry system, various reporting |  | X | X | Mike Wilson / Joy Turner | Ron Riedner
Milestone tracking System | Track and report on Dept of Energy milestone status | 5000 | 1 | 2000-07-01 |  | NWP/Low risk | Have a streamlined data entry system, various reporting |  | X | X | Mike Wilson / Joy Turner | Ron Riedner
SEA Applications
Shorelands Aerial Photo Web Project - Internet | Make current system available on the Internet |  |  | Schedule dependent upon DIS CSA |  | Agency / Low risk | Provide agency and public access to marine aerial photos. |  | X | X | Gordon White | Brian Lynn, Debbie Stewart
Spills Applications -- none
SWFA Applications
Develop CPG outcome tracking system | Track the outcomes of local government grants. Provide data on use of grant dollars. | 0 | 0.25 | ? |  | SWFA / Low risk | Environmental outcome funding |  |  |  | Cullen Stephenson / Jay Shepard | Gloria Dreyer, 407-6108 gdre461@ecy.wa.gov
Develop and update CLCP outcome tracking system | Track the outcomes of local govlitter cleanup contracts. Provide data on use dollars. |  | 0.1 |  |  | SWFA / Low risk | Environmental outcome funding |  |  |  | Cullen Stephenson / Jay Shepard / Kyle Dorsey | Judy Freeze
Regional Access | Create regional access for data entry to the CPG, CLCP, and BDMS |  | ? | Staggered from 12/00 to 6/01 |  | SWFA / Low risk | Efficiency/accountability/work load distribution |  |  |  | Cullen Stephenson / Jay Shepard | Kyle Dorsey
Develop SWFA Program document management system information, working documents, etc. Jay Shepard, 407-6071, jshe461@ecy.wa.gov Mike Sosnow | Provide desktop access to program-specific data, |  |  | Complete by June 30, 2001 |  | SWFA HQ / Low risk | Establish program file management system |  |  |  | Cullen Stephenson / Jay Shepard | Kyle Dorsey
Biosolids Data Management System | Track statewide biosolids management data for EPA |  | 0.25 | By 12/00 |  | SWFA / Low risk | Data collection Required EPA reporting of delegated program |  |  |  | Cullen Stephenson / Jay Shepard | Kyle Dorsey
TCP Applications
Integrated Site Information System (ISIS) - Complete Additional Modules | Complete modules for Voluntary Cleanup Program (VCP) and Institutional Controls, other minor enhancements as needed. (Work in progress.) | Grant funded |  | Complete by March 30, 2000 |  | TCP / Low risk | Integrating data from a small user-developed Access database. Need to meet changing requirements of the Voluntary Cleanup Program. Policy Advisory Committee work resulted in additional requirements for tracking institutional controls. |  |  |  | Jim Pendowski / Tim Nord | Wayne Allenton
USTBASE - Integration with F/S ID | Data conversion & data cleaning effort to integrate USTBASE into the agency's F/S ID System. (Includes data for 16,000 tanks) | $34,000 (IIP funds) | 1 | July 1999 through June 2000 | Will add value and utility to the agency Facility/Site system by improving access to Underground Storage Tank data. | TCP / Low risk | A long-term goal of the agency is to integrate existing program-specific data with agency-wide facility data. Other agencies (DOH and PLIA) and other Ecology programs have been requesting increased access to UST data for some time. |  |  |  | Jim Pendowski / Tim Nord | Lisa Shriver
USTBASE - Upgrade | Re-image the front-end application in Powerbuilder 6.5 (or >). Convert the back-end database to MS SQL-Server 7.0 (or >). Upgrade DOL interface. Add new functionality as appropriate. |  | 2 | October 1999 through December 2000 | Will improve performance and functionality of an existing mission-critical system. | TCP / Low risk | Need to retire old technology--the existing application is 16-bit. Improve efficiency by reducing the amount of database administration workload required by the current Sybase database. |  |  |  | Jim Pendowski / Tim Nord | Wayne Allenton
Water Quality Applications
Water Permit Life Cycle System (WPLCS) - Y2K conversion | Ensure Y2k Compliance for both hardware and software. | 158000 | 2 | Complete by September 30, 1999 |  | WQ / Low Risk | Continue tracking of permit, compliance, inspection and enforcement of water dischargers. |  |  |  | Megan White | Warren Opfer
Whole Effluent Toxicity (WET) Tracking System | Finalize purchase of replacement system. | 8000 | 0 | Complete by Ocotber 29, 1999 |  | WQ / Low Risk | Current system in based on early version of Access and replacement version is to become available before June 30, 1999. |  |  |  | Melodie Selby | Warren Opfer
Water Resources Appplications (to be updated)
Groundwater Database (GWDB) | Used by HQ, ERO, and SWRO to track water use information submitted by certificated water right holders. Also tracks water level measurements for Ecology monitoring wells, water level measurements for certificated water wells, and water quality data (chloride, etc) |  | Data entry at ROs and HQ | Ongoing admin. and maintenance. System under development to move GWDB to IIP |  | Water Resources / Low Risk | Regional data management of submitted and field data for wells in the state. Data will be accessed via the IIP (EIM). Data used by agency programs to investigate groundwater projects. |  |  |  | Keith Philips, Bill Backous | Chris Anderson, Lynn Singleton, Will Kendra
Water Rights Adjudication Report Writing System | Used by HQ and CRO to track the Yakima Adjudication. Provides information pertinant to the issuance of water right certificates for adjudicated water right claims. |  | Data entry at HQ and CRO | Ongoing admin. and maintenance. System under development to complete the system to allow printing of certificates when issued. |  | Water Resources / Low Risk | Data management system required to meet the requirements of a tracking system for the Yakima Adjudication. System is accessed by HQ, CRO and the court during the adjudication process. This system resides on the AS400 and is supported by ADS. |  |  |  | Keith Philips | Sam Bailey, EP3, 360-407-6641 sbai461@ecy.wa.gov
Yakima Adjudication GIS | GIS work specific to the Yakima Adjudication, includes WAWIS (CRO project plotting place of use for water rights) |  | Data entry at HQ and CRO. 0.50 at HQ | Ongoing admin. and maintenance, GIS work continues to complete Yakima Adjudication coverages |  | Water Resources / Low Risk | GIS data entry to support the Yakima Adjudication. Regional and HQ staff enter data to be mapped for court presentations |  |  |  | Keith Philips | Anna Trombley, Carto2, 36-407-6078 atro@ecy.wa.gov
Regional Office Applications (to be updated)
Develop Help Desk System for regional offices | Develop Help Desk application using MS Exchange for real time data. |  | 0.15 | Completed by Dec 31, 1999 |  | Regions / Low risk | Provide real time help desk for Regions. Obtain statistical data for HQ IS Staff concerning hardware/software support. |  |  |  | Carol Fleskes | Bob Monn / Jim Kozisek
Develop PPR origination and tracking system | Develop in house PPR tracking application |  | 0.15 | Completed by June 30,1999 |  | Regions / Low risk | Provide capability for regional staff to prepare PPRs at individual workstations including sequential numbering. |  |  |  | Polly Zehm | Jim Kozisek
Develop agency vehicle tracking system for regional offices | Develop tracking system for vehicle use and maintenance |  | 0.1 | Completed by June 30, 1999 |  | Regions / Low risk | Develop a speedsheet for tracking maintenance performed on Agency vehicles . |  |  |  | Polly Zehm | Jim Kozisek
* Risk criteria (Word document)
Go to Section 5. Planned/Proposed Projects/Investments (Excel spreadsheet)
Go to Table of Contents