## issuescurrent
| Phase | Issue | Category | Date Recorded | Status | Response
X | Planning | Lack of communication to all zones. Once system is implemented small counties may be forgotten | Communication | 2003-04-03 | In Progress | Hired project executive for communications. Communication plan to be developed. Zone meetings scheduled on quarterly bases. Tech support included in RFP
X | Planning | Who pays the cost for conversion to the new system? | Financial | 2003-03-03 | Under Review
X | Planning | How is funding going to be handled? Who pays if counties can't afford all requirements to meet mandate. Counties have fixed budgets. | Financial | 2003-04-03 | In Progress
X | Planning | Sunk cost in current systems. Who pays for new required hardware? Counties have limited budgets | Financial | 2003-04-03 | Under Review
X | Planning | Will the state or other counties be allowed to enter information for voters who do not reside in their county? If so, how will the physical card be handled? | Policy/Data Management | 2003-04-07 | Under Review
X | Planning | Who owns the address street files? | Policy/Data Management | 2003-04-03 | Under Review
X | Planning | Who maintains the address/street files? If it is not done in the counties it may not be done correctly and could cause problems with redistricting. | Policy/Data Management | 2003-04-03 | Under Review
X | Planning | Loss of local control. They need the ability to maintain data. | Policy/Data Management | 2003-04-03 | In Progress | Included as RFP requirement
X | Planning | Quality control will be an issue if information is entered anywhere other than the local county where the voter resides. | Policy/Data Management | 2003-04-03 | In Progress | All election management responsibilities will remain the same.
X | Planning | Fast growing counties have concerns about districting. How are the street files going to be handled? | Policy/Data Management | 2003-04-03 | Under Review
X | Planning | When a voter moves to a new county will they need a new registration card? (statue currently says yes) With the new system will an address update be sufficient? | Policy/Process | 2003-04-03 | Under Review
X | Planning | Need to continue high level of customer service at county level (specifically during elections) Don't want to send voters to Salem. Need to serve locally | Policy/Process | 2003-04-03 | In Progress | Counties maintain management of election process.
X | Execution | Ability to solve registration problems on a local level. | Policy/Process | 2003-04-03 | In Progress | Included in RFP access to all information needed at counties to resolve issues.
X | Planning | How is SOS going to handle requests from political parties and/or the public for copies of digitized signatures? Public perception of personal data stored outside the county. Security and privacy issues. | Policy/Process | 2003-04-03 | In Progress | Signatures to be stored centrally and secured or masked to view by authorized access only. Get an exemption to the public records law 2004 legislature.
X | Planning | Avoid extra workload and processes in the counties. Who redesigns work processes? | Policy/Process | 2003-04-03 | Under Review
X | Planning | Need same or higher level of on-site local support. Currently vendors are very responsive. | Policy/Process | 2003-04-03 | In Progress | Require support levels in RFP
| Planning | Communication from SOS very important to aid in county purchasing decisions. Need to know timing of new system and requirements to avoid purchasing unneeded hardware. | Communication | 2003-04-03 | In Progress | Communication Plan, Web page with schedule.
| Execution | Educate people requesting list. The info is not static. List are outdated the minute they are pulled. Perception of bad data comes from this not the counties processes. | Education | 2003-04-03 | Under Review
| Planning | Ongoing training on new system is a must at all levels. | Education | 2003-04-03 | In Progress | Including in RFP - user training and manuals
| Planning | Conversion of data. Who does it and who pays? | Financial | 2003-04-03 | Under Review
| Planning | Cost of system. Currently counties amortize hardware/software and maintenance costs and bill out to the districts during elections billing process. Need to have a uniform approach for distributing funds from the feds. | Financial | 2003-03-03 | Under Review
| Initiation | Vendor "price fixing" Charging by registered voter doesn't reflect true cost of system. We don't want to pay for vendor development on a ongoing basis. | Financial | 2003-04-03 | In Progress | Contract language and negotiations
| Planning | Consider cost to build vs. buy. Building and owning the source code my be less expensive in the long run. | Financial | 2003-04-03 | In Progress | Options included in RFP.
| Planning | Who buys the needed new hardware? | Financial | 2003-04-03 | In Progress | SOS will pay for the counties who begin using all functionality of the system right away.
| Planning | Who will have access to the log that records who made changes to records? What will these logs be used for? | Policy | 2003-05-03 | Under Review
| Planning | Will we accept DMV state ID card number as identification? | Policy/Process | 2003-04-17 | Under Review
| Planning | How will the existing state petition management system be used with the new system? (enhancement scheduled for '04) | Policy/Process | 2003-05-03 | Under Review
| Planning | Smaller counties don't have all the needs of larger counties (i.e. splits) Don't want to be required to go through un necessary screens and/or processes. | Policy/Process | 2003-04-03 | In Progress | included in RFP.
| Planning | Timing of implementation. If not done by 2005 need to get an extension due to election. | Schedule | 2003-04-03 | Under Review
| Execution | OCVR project interfering with elections during peak election periods. | Schedule | 2003-04-03 | In Progress
| Planning | Need to develop uniform use of identifiers (active, canceled, pending, inactive..) | Standards | 2003-05-03 | Under Review
| Planning | Standards needed for sending memorandum cards. | Standards | 2003-05-03 | Under Review
| Planning | Will SOS take over petition checking? Standards needed for petition checking. | Standards | 2003-04-03 | Under Review
| Planning | Set standard default fields | Standards | 2003-04-17 | Under Review
| Planning | We need address standards to ensure all counties entry data the same. | Standards | 2003-04-03 | Under Review
| Planning | Determine a standard for using "pending" in the system | Standards | 2003-05-03 | Under Review
| Planning | Use of existing county codes. Since the counties are used to them can they be used for identification? | Standards | 2003-04-07 | Under Review
| Planning | Unique ID Number, how is it going to be assigned and used? | Standards |  | Under Review
| Planning | Need to identify statewide system flags | Standards | 2003-05-03 | Under Review
| Planning | Response time and reliability of new system. Need at least what we have now. | System | 2003-04-03 | In Progress
| Planning | System must be VERY secure | System | 2003-04-03 | In Progress
| Planning | Redundant information or mirrored systems at local level to ensure work continuation if central system goes down. | System | 2003-04-03 | In Progress | Include redundant, load balanced systems in RFP
| Planning | Accessibility to local information on a local bases. | System | 2003-04-03 | In Progress | Included as RFP requirement
| Planning | Some counties have limited web access. How is this going to be handled if we go with a web based solution? | System | 2003-04-03 | In Progress | Included in technical RFP requirements. Equal access to all counties.
| Planning | All counties on system at the same time, concerns about response times especially during peak periods. | System | 2003-04-03 | In Progress | Included in RFP expected response time, and number of users
| Planning | Real time voter history updates | System | 2003-05-03 | In Progress | Included in RFP C-26
| Planning | System must allow manual override to delete tax codes. | System | 2003-05-03 | In Progress | Included in RFP D-33
| Planning | User option for printing labels and user defined reports | System | 2003-03-05 | In Progress | Included in RFP tech and business requirements
| Planning | Ease of data entry. User friendly system | System | 2003-04-03 | In Progress | Included in RFP screen design requirements A20
| Planning | Absentee Module needed | System | 2003-04-03 | In Progress | Included in RFP A14-38
| Planning | Need to consider CASS Certification | System | 2003-04-03 | In Progress | Included in RFP
| Planning | We need direct envelop and file extraction capabilities | System | 2003-04-03 | In Progress | Included in RFP P-53
| Planning | Data interfaces or pass-through to multiple ballot tally systems. |  | 2003-05-03 | Closed | OCVR does not include ballot tally systems. Data extraction is included in RFP