## SCHEDULE
8.1 'Milestones, Deliverables and Schedule': example for the bar chart
|  |  | 1st year |  |  |  | 2nd year |  |  |  | 3rd year
|  | Month: | 1 - 2 - 3 | 4 - 5 - 6 | 7 - 8 - 9 | 10 - 11 - 12 | 1 - 2 - 3 | 4 - 5 - 6 | 7 - 8 - 9 | 10 - 11 - 12 | 1 - 2 - 3 | 4 - 5 - 6 | 7 - 8 - 9 | 10 - 11 - 12
Milestone
| 1. | LCD analysis
| 2. | Computer modeling
2.1 Software for computer modeling
2.2 Basic optical measuring system
2.3 Complete optical measuring system
| 3. | Compensated filter assembly
3.1 Patent application for comp. LCD
3.2 NR layers development
3.3 PT filter with compensated LCD
3.4 Development of optimum filter config.
3.5 Experimental evalution
3.6 Development of tech. for small scale production
| 4. | Low power consumption electronics
4.1 PT of low power discrete electronics
4.2 Design and development of custom IC
4.3 Production PT series of custom IC
| 5. | Implementation at industrial end-user
5.1 Integration of NR into manufactuirng process
5.2 Production PT of filter module with comp. LCD
5.3 Small scale production of filter module with comp. LCD
[6 empty] | * Prototypes of low power consuming electronics * Patent for comp. LCD | * Software package for IBM PC | * optimal measuring system for demonstration |  |  |  |  | * Prototype of optimal LCD light shutter | * Commercially available optimized LCD light shutter | Deliverable:
Page 13 |  |  |  |  | * 1st Progress Report |  | * 2nd Progress Report |  | * 3rd Progress Report |  | * 4th Progress Report |  | * 5th Progress Report | * Final Report | Reporting: | Annex 3a
(This bar chart should be designed to suit the Project's requirements; it should be as detailed as possible and self-explanatory.)

## ORGANIGRAM
Annex 3b
PROJECT STRUCTURES AND ACTIVITIES
8.2 'Organization and Management': example for a detailed task describtion and distribution
| Name of participant, location (city, country) | Affiliation (institution, company) | Position | Involvement in the project (% of his/her time) | Task in the project *
1. | Prof. A., Ljubljana, Slovenia | Institute A | Physicist, sen. researcher | 30 | PPD; establishment of software for computer modeling; participation in regular coordination meetings; visit to institute D in USA.
2. | Ms. B., Ljubljana, Slovenia | Institute A | PhD student, young scientist | 100 | Development of software for computer modeling; training at institute D, USA (supervised by Dr. I.).
3. | Dr. C., Ljubljana, Slovenia | Institute B | IC designer, electronics | 50 | Design and development of custom IC; involvement in patent application for comp. LCD; participation at regular coordination meetings.
4. | Mr. D., Ljubljana, Slovenia | Institute B | MSc student, young scientist | 100 | Design and development of custom IC (supervised by Dr. C.); training at institute D, USA (supervised by Dr. I.).
5. | Ms. E., Ljubljana, Slovenia | Company A | General director, end-user | 5 | Involvement in patent application for comp. LCD; participation in regular meetings.
6. | Dr. F., Ljubljana, Slovenia | Company A | Technical director, end-user | 20 | Commercialisation of final LCD light shutter; demonstration of protoype; intensive cooperation with participant no. 4, Mr. D., during final phase of the project.
7. | Prof. G., Moscow, Russia | Institute C | Physicist; sen. researcher | 50 | Design and development of custom IC; participation at regular co-ordination meetings; intensive cooperation with participant 3, Dr. C., during final phase of the project.
8. | Mr. H., Moscow, Russia | Company B | General director, end-user | 20 | Commercialisation of final LCD light shutter; intensive cooperation with participant no. 7, Prof. G.
9. | Dr. I., Kent, USA | Institute D | Assistant director | 15 | NPD; development of low frequency electronic driving waveforms; supervisor of the training of participant no. 2, Ms. B, and 4, Mr. D.; regular visits to the institutes and end-users in Slovenia and Russia.
10. | Mr. J., MSc, Kent, USA | Institute D | researcher, electronics | 70 | PT of low power discrete electronic; training of participant no. 2, Ms. B, and 4, Mr. D.
(continued)
* To be described in detail |  |  |  |  | Page 14