## Sheet1
Project information report
Project ID |  | 10022
Project name |  | Project Management System (PMS) v. 2.10
Description |  | Project Management System v 2.10. Project's purpose is to add following features to existing PMS system: "What's new?", "Tasks", "Announces" plus do few minor bug fixes and other minor changes.
Customer
Supervisor |  | Malinen Teemu
Starting date |  | 08. helmikuuta 2001
Estimated ending date |  | 12. maaliskuuta 2001
Ending date |  | 2001-03-04
Event date | Employee |  | Event | Event description | Dur.
14.02.2001 | Lahtiranta Janne |  | Database design | Created a testing environment for development purposes. | 0.75
15.02.2001 | Lahtiranta Janne |  | Database design | Created first specification about the DB. | 4
16.02.2001 | Lahtiranta Janne |  | Documentation | Created and updated project documentation. | 5
03.04.2001 | Lahtiranta Janne |  | Testing | Inspected and corrected invalid data structure relationships with Janne Talvio. | 1
17.04.2001 | Lahtiranta Janne |  | Documentation | Inspected and updated Stored Procedure Documentation. | 0.5
23.04.2001 | Lahtiranta Janne |  | Documentation | Updated and fixed documentation. | 4
04.05.2001 | Lahtiranta Janne |  | Documentation | Finalised the project documentation. | 2.5
17.75
08.02.2001 | Malinen Teemu |  | Planning (Basic) | making of project plan | 0.5
08.02.2001 | Malinen Teemu |  | Planning (Basic) | "New features & bug fixes" design plan | 2
09.03.2001 | Malinen Teemu |  | UI Design | two buttons (transparent & high importance) | 1.6667
19.03.2001 | Malinen Teemu |  | UI Design | UI Buttons | 0.75
26.03.2001 | Malinen Teemu |  | UI Design | Warranty icon | 0.58333
28.03.2001 | Malinen Teemu |  | UI Design | Del interest group member -button | 0.41667
5.9167
12.02.2001 | Talvio Janne |  | Studying/Research | Reading VBasic, ASP and MS SQL - codes. | 7
13.02.2001 | Talvio Janne |  | Studying/Research | Reading and studying Project Management System's code. | 3.5
15.02.2001 | Talvio Janne |  | ASP | Studying PMS and starting to code new features. | 5.3333
15.02.2001 | Talvio Janne |  | VB | Studying PMS and starting to code new features. | 5
16.02.2001 | Talvio Janne |  | VB | Programming PMS (announcements) | 8.5
19.02.2001 | Talvio Janne |  | ASP | Programming PMS (announcements). | 3
19.02.2001 | Talvio Janne |  | VB | Programming PMS (announcements). | 3
19.02.2001 | Talvio Janne |  | SQL/Stored Procedures | Programming PMS (announcements). | 2
21.02.2001 | Talvio Janne |  | VB | Programming and debugging PMS (announcements, Nowire today) | 8.3333
22.02.2001 | Talvio Janne |  | VB | Programming Nowire today page, and inspecting the security issues on PMS login and logout. | 3.3333
26.02.2001 | Talvio Janne |  | VB | Programming and debugging PMS (announcements, tasks) | 5
26.02.2001 | Talvio Janne |  | SQL/Stored Procedures | Programming and debugging PMS (announcements, tasks) | 2
01.03.2001 | Talvio Janne |  | VB | Programming and debugging PMS (announcements, tasks) | 7
08.03.2001 | Talvio Janne |  | VB | Programming PMS (announcements, tasks) | 6.8333
09.03.2001 | Talvio Janne |  | VB | Programming PMS (announcements, tasks) | 5
12.03.2001 | Talvio Janne |  | VB | Programming PMS (announcements, tasks) | 7.5
13.03.2001 | Talvio Janne |  | VB | Programming PMS (announcements, tasks) | 3
14.03.2001 | Talvio Janne |  | VB | Programming and debugging PMS (announcements, tasks) | 3
15.03.2001 | Talvio Janne |  | VB | Finalizing announcements and tasks) | 6.1667
16.03.2001 | Talvio Janne |  | VB | Programming Tasks user interface. | 7.1667
19.03.2001 | Talvio Janne |  | ASP | Adding email notifications to Tasks. | 3.8333
19.03.2001 | Talvio Janne |  | VB | Programming Task user interfafe. | 3.3333
20.03.2001 | Talvio Janne |  | ASP | Adding email notifications to Tasks and finalizing code. | 4.3333
22.03.2001 | Talvio Janne |  | ASP | Debugging asp code. | 3.1667
22.03.2001 | Talvio Janne |  | SQL/Stored Procedures | Adding new tables an stored procedures to server database. | 3.3333
23.03.2001 | Talvio Janne |  | VB | Debugging and installing new Pms.dll to server. | 3
23.03.2001 | Talvio Janne |  | ASP | Testing and debugging new pms and studying possible security enhancements to pms. | 7.1667
02.04.2001 | Talvio Janne |  | ASP | Programming bug fixes considering email notifications. | 1.6667
03.04.2001 | Talvio Janne |  | SQL/Stored Procedures | Fixing database relations. | 1
03.04.2001 | Talvio Janne |  | ASP | Testing and debugging PMS. | 2.5
05.04.2001 | Talvio Janne |  | VB | Finalizing and debugging PMS code. | 6.1667
06.04.2001 | Talvio Janne |  | VB | UI designing and debugging PMS code. | 3.1667
09.04.2001 | Talvio Janne |  | VB | Programming Tasks. | 8.6667
10.04.2001 | Talvio Janne |  | ASP | Programming Tasks. | 2.8333
12.04.2001 | Talvio Janne |  | ASP | Programming Tasks | 4.5
17.04.2001 | Talvio Janne |  | Documentation | Documenting stored procedure and vb codes. | 6.6667
17.04.2001 | Talvio Janne |  | VB | Setting up new .dll to server and adding new stored procedures to database. | 1
18.04.2001 | Talvio Janne |  | Documentation | Finalizing source code comments and studying self documenting policies. | 8.6667
19.04.2001 | Talvio Janne |  | Documentation | Documenting PMS v. 2.1. | 6.3333
19.04.2001 | Talvio Janne |  | Documentation | Documenting PMS 2.1. | 2.6667
23.04.2001 | Talvio Janne |  | Documentation | Finalizing PMS documents. | 3
25.04.2001 | Talvio Janne |  | Documentation | Documenting. | 2.8333
26.04.2001 | Talvio Janne |  | Documentation | Documenting. | 4.5
30.04.2001 | Talvio Janne |  | Documentation | Documenting. | 1.5
02.05.2001 | Talvio Janne |  | ASP | Updates and bug fixes. | 3.6667
03.05.2001 | Talvio Janne |  | VB | Updates and bug fixes. | 6.6667
04.05.2001 | Talvio Janne |  | Documentation | Finalizing document. | 2
209.8333
Warranty total (h) |  |  |  |  | 0
Grand total (h) |  |  |  |  | 233.5