## Sheet1
Task | TEAM | MARP | FINA | IS | Check when Complete | Notes
Week 1 - Teambuilding
Divide into Teams | ●
Get to know your Team members | ●
Form Groups within Teams | ●
Familiarize yourself with Venture Out! | ●
Week 2 - Roles & Rules
Refresh names, welcome new members, and collect/e-mail a Team member list | ● |  |  | ●
Set Team rules and boundaries | ●
Write a Team mission statement | ●
Homework: Attend ACU's Service Expo | ●
Homework: Watch for campus opportunities | ●
Week 3 - Organizing
Divide Group tasks |  | ● | ● | ●
Develop accounting procedures |  |  | ●
Get to know your market |  | ●
Review loan review and annual report and plan photo shoot |  |  |  | ●
Generate possible product ideas | ●
Homework: Bring your product, beneficiary, and supplier ideas next week! | ●
Week 4 - Exploring
Identify beneficiary(ies) | ●
Identify possible products | ●
Estimate tentative Group budgets |  | ● | ● | ●
Team and Group photo shoot |  |  |  | ●
Homework: Prepare a tentative Team budget |  |  | ●
Week 5 - Researching
Decide on a Beneficiary | ●
Design your market research survey and gather results | ●
Homework: Tabulate the research results and prepare a recommendation |  | ●
Homework: Begin assembling items for your application to the Loan Review Board |  |  |  | ●
Week 6 - Proposing
Decide on product (Market research data and recommendations provided by MARP) |  | ●
Approve a team budget (Data and recommendations provided by FINA) |  |  | ●
Choose a Team name | ●
Decide legal status of Team and complete assumed name certificate | ●
Arrange to meet with the Loan Review Board | ●
Homework: Prepare your application for the Loan Review Board |  |  |  | ●
Week 7 - Funding
Present application to Loan Review Board | ●
Make revisions requested by Loan Review Board | ●
Order product (MARP) |  | ●
Weeks 8 - 10: Selling
Establish sales policy, schedule, and logistics |  | ●
Advertise your product |  | ●
Gather and record weekly budget variance |  |  | ●
Sell, Sell, Sell! | ●
Manage your business processes |  | ● | ● | ●
Week 11 - Documenting
Assess your readiness for completing the annual report |  | ● | ● | ●
Week 12 - Reporting
Assemble a professional annual report (IS with the help of all members) |  |  |  | ●
Week 13 - Cashflow
Play Cashflow game (optional)
Week 15 - Celebrating
Celebrate! | ●