## Open Action Items
Action Item Number | Related Issue Number | Action Description | Assigned To | Status | Last Status Date | Resolution/Status Comment | SECAB Document Impact
49 | Admin | Review section 7.3 for the correct placement of the asterisks. The asterisk represents that the data element is defined in Section 7.4 with valid values. Once the asterisks are identified as being on the correct data elements, remove the asterisk and place a note in the “What to Populate” column that reads “Refer to Section 7.4 for Valid Values.” Remove the language explaining the meaning of the asterisks from Section 7.1. | Dawn Coleman | Open | 2002-01-28 | waiting for issue 10 | Chapter 7
52 | Admin | Review Section 5.0 to identify which scenarios could possibly be eliminated, added or corrected. | SECAB PARTICIPANTS | Open | 2002-03-14 |  | Chapter 5
53 | Admin | 1. With the new “Call Set-Up” rate element, is there a need for a new description code for the new rate element, or is the current one sufficient? 2. Participants to review the current use and definition of description codes in order to determine if all values are needed or whether the rate element Indicator be added to replace some of the current description values. | SECAB PARTICIPANTS | Open | 2002-03-14 | Chapter 7, Section 7.6
54 |  | 1. With the new “Call Delivery Charge” rate element, is there a need for a new description code for the new rate element, or is the current one sufficient? 2. Participants to review the current use and definition of description codes in order to determine if all values are needed or whether a rate element Indicator be added to replace some of the current description values. | SECAB PARTICIPANTS | Open | 2002-03-14 | Chapter 7, Section 7.6
55 | Admin | Review of revised Chapter 4 submitted by Bruce Walth to mirror Chapter 3. | SECAB PARTICIPANTS | Open | 2002-03-14 | Chapter 4

## Completed Action Items
Action Item Number | Related Issue Number | Action Description | Assigned To | Status | Last Status Date | Resolution/Status Comment | SECAB Document Impact
1 | Admin | Compare information in Chapters 3,4,7 and note inconsistencies for review by Subcommittee | Shellie Kaiser | Complete | 2001-12-13 | Discrepancies and questions will be documented in a new tracking matrix which will be reviewed and approved by the SECAB Subcommittee prior to updating the SECAB document. SECAB Subcommittee agreed that due to the large MPB impacts on Chapter 4, changes to this chapter will be addressed with SECAB Issue 9. Shellie will status and transition findings at year end. | Chapters 3,4,7
2 | Admin | Compare "Customer Preference" fields for paper bill to Required/Not Required fields for mechanized bill | Bruce Walth | COMPLETE | 2002-03-14 | Two versions of Chapter 4 are currently posted with the draft SECAB 9 Document. The second version reflects the work that Shellie Kaiser has completed thus far. Mr. Bruce Walth will continue this effort and use the second version as the master document for the purposes of completing this Action Item. The chapter will be reviewed on a bill type-by-bill type basis. This section also address multi bill options. | Chapters 3, 4
3 | Admin | Consistent Data Element sequencing between Chapters 3 and 4 for paper bill | Shellie Kaiser | COMPLETE | 2001-12-13 | Discrepancies and questions will be documented in a new tracking matrix which will be reviewed and approved by the SECAB Subcommittee prior to updating the SECAB document. Effort will continue into Issue 9 due to magnitute of changes in document. | Chapters 3,4
5 | Admin | Cross reference Table of Contents Chapters with Chapter headings and numbers | Shellie Kaiser | COMPLETE | 2001-12-13 | Discrepancies and questions will be documented in a new tracking matrix which will be reviewed and approved by the SECAB Subcommittee prior to updating the SECAB document. Effort will continue into Issue 9 due to magnitute of changes in document. | Entire document
6 | Admin | Correct Chapter 7 "Paper References" to reflect the corrected numbering | Shellie Kaiser | Complete | 2001-12-13 | Discrepancies and questions will be documented in a new tracking matrix which will be reviewed and approved by the SECAB Subcommittee prior to updating the SECAB document. Effort will continue into Issue 9 due to magnitute of changes in document. Shellie will status and transition findings at year end. | Chapter 7
10 | Admin | Add agenda item: Address enhancement of the Bill Examples | Dara Moschetta | COMPLETE | 2001-12-13 | Will be addressed with MPB Issues in SECAB Issue 9. | Chapter 5
12 | 1548 | Identify instances where the following fields need to be deleted from SECAB document: IBC/SBC, IBC BAN, IBC BILL DATES, IBC FROM/THRU DATES, BAR, BACR | Barb Vrahnos | COMPLETE | 2001-12-13 | Findings submitted to Subcommittee. Participants asked to review prior to 7/31/01 conference call. Will be addressed with MPB Issues in SECAB Issue 9. | Entire document
16 | 2138 | Add agenda item to discuss the addition of (OCN) Company Code to the bill | Dara Moschetta | COMPLETE | 2001-12-13 | This item will remain open until MPB topics are scheduled to be addressed and the item can be added to the appropriate SECAB agenda. | Chapter 7
17 | 2138 | Participants are requested to review the Issue 2138 attachment prior to this discussion | All participants | COMPLETE | 2001-12-13 | Will be addressed with MPB Issues in SECAB Issue 9.
18 | 2162 | Identify references to Pass-through Options which should be deleted from SECAB. | Barb Vrahnos | COMPLETE | 2001-12-13 | Related to Action Item 12. Will be addressed with MPB Issues in SECAB Issue 9. | Entire document
19 | 2162 | Identify the instances where Multi-Multi and Multi-Single Bills are referenced in the SECAB document. These instances will require changes to correlate with the MECAB definition | Barb Vrahnos | COMPLETE | 2001-12-13 | Related to Action Item 12. Will be addressed with MPB Issues in SECAB Issue 9. | Entire document
24 | 2240 | Readdress Meet Point Billing sentence in SECAB Scope after the "multi-multi" bill issues are addressed - discuss adding reference to MECAB. Review reference to MECAB in Paragraph 3.2 of Section 3.0 | SECAB Subcommittee | COMPLETE | 2002-01-28 | The following sentence was added to the last paragraph in Section 1.4 Scope: The MECAB contains the recommended guidelines for the billing of access/interconnection services provided to a customer by two or more providers. That document should be consulted for specific meet point criteria. | Entire document
37 | Homework | Participants will consult with their company regarding the use of Jurisdiction Indicator on Adjustment and OC&C records. For companies both producing and receiving these records, how do you handle the jurisdiction indicator for non-jurisdictional adjustments (e.g. adjustment against balance due)? | All participants | COMPLETE | 2001-12-13 | Homework Items assigned - see Action Items 40 and 41. | Chapter 7
38 | Homework | Participants are to consult with their companies with regard to how they use Physical Locations 1 and 2 on the SCSPCA Records to help determine if the definitions of these fields need to be updated. | All participants | COMPLETE | 2001-12-13 | The field names of Physical Locations 1 and 2 were changed to End User Locations 1 and 2 to be consistent with paper bills. Additionally, the "What to Populate" column was changed to reflect the definition of End User Location in Chapter 3. Homework Action Item 42 was assigned and it was agreed to address with SECAB Issue 9. | Chapter 7
42 | Homework | Participants will go home and see if their companies want both A and Z physical address locations in the records, and, if so, is a thirty character field enough or should the field be bigger. | All participants | COMPLETE | 2001-12-13 | Participants will observe if changes to field names and definitions resolve the problem and bring further concerns to SECAB in future. | Chapter 7
44 | Admin | Participants to review proposed final draft SECAB Issue 8 and send comments to Shellie Kaiser, with copy to Syl-Vonna Mabie and Dawn Coleman by October 12, 2001. | All participants | COMPLETE | 2001-12-13 | SECAB Issue 8 approved and published | Entire document
40 | Homework | Participants will look at the current list of Description Codes and define which codes would apply to non-jurisdictional adjustment amounts. | All participants | COMPLETE | 2002-01-09 | Participants require more time to investigate. At minimum, the 7 codes having to do with payment could be non-jurisdictional because you are referring to total balance on the account. This was limited to adjustments because non-jurisdictiona is not valid on OC&C. This Item was completed on 1/9/02 conf. call; Payment Codes are only codes that are Non-Jurisdictional; Jurisdictional Ind. data element was modified; SCDAJ1 and SCSUM1 records for all bill types were modified in Section 7.3. | Chapter 7
41 | Homework | Participants will identify and review which mechanized records within each bill type would be affected and whether new fields would need to be added for non-jurisdictional adjustment totals. | All participants | COMPLETE | 2002-01-09 | Participants require more time to investigate. At minimum, the 7 codes having to do with payment could be non-jurisdictional because you are referring to total balance on the account. This was limited to adjustments because non-jurisdictional is not valid on OC&C. This Item was completed on 1/9/02 conf. call; Payment Codes are only codes that are Non-Jurisdictional; Jurisdictional Ind. data element was modified; SCDAJ1 and SCSUM1 records for all bill types were modified in Section 7.3. | Chapter 7
45 | SCOCC1 | Ms. Janet Kiernan volunteered to create a sample SCOCC2. | Janet Kiernan | COMPLETE | 2001-12-13 | A sample SCOCC 2 record was submitted and reviewed on 1/9/02 conference call | Chapter 7
46 | SCOCC1 | Ms. Shellie Kaiser will create a checklist of items that need to be considered when creating a new record and forward it to Janet Kiernan to aid her in her creation of a draft SCOCC2. | Shellie Kaiser | COMPLETE | 2001-12-13 | Checklist was forwarded to Administrator on 12/28/01. | Chapter 7
47 | Admin | Move the Unbundled Line Number Report in Section 7.0 from behind the Unbundled Bill to after the Switched Access Bill | Dawn Coleman | COMPLETE | 2002-03-14 | Moved the Unbundled Line Number Report in Section 7.0 from behind the Unbundled Bill to after the Switched Access Bill | Chapter 7
48 | Admin | Review Section 8.0 Acronyms for consistency | Janet Kiernan | COMPLETE | 2002-03-14 | Reviewed Section 8.0 Acronyms for consistency, there were no inconsistenices, therefore, no changes | Chapter 8
50 | Admin | Review Section 5.0 bill examples to identify which scenarios could possibly be eliminated, added or corrected. | Jeff Simpkins, Judy Mutzenburg and Syl-Vonna Mabie. | COMPLETE | 2002-03-14 | Reviewed Section 5.0 revisions. Agreed to incorporate into Issue 9. | Chapter 5
51 | Admin | Review the use of the terms Multi Bill/Single Tariff and Multi Bill/Multi Tariff to ensure consistency of how they are defined in MECAB | Syl-Vonna Mabie | COMPLETE | 2002-03-14 | Found inconsistencies, provided changes to administrator for incorporation into Draft Issue 9 | Entire Document