## 751 timeline
TIMELINE FOR SFS UPGRADE TO VERSION 7.52
NOTE: Data in red font represents changes made to this schedule
|  |  |  | Sept. 29-30 |  |  | Oct. 20-21 |  |  | Nov. 19-20 |  | Nov. 21-25 |  |  | Nov. 26
(1)
[5 empty] | DoIT performs tools upgrade |  |  | All final testing for "go live" moves to the
[5 empty] | and applies SP 2 patches/fixes |  |  | SF75GOLD database. Use of SFNEWT stops
Items done by users
[7 empty] | Items done by DoIT staff |  | and by UWSA staff
* All development for Phase 3 |  |  | * UWSA staff and DoIT |  |  |  | * Perform final database/tools/ |  | * Final user testing |  |  | * Move SF75GOLD to production SFS
is done in version 7.02 |  |  | staff perform testing, |  |  |  | upgrade troubleshooting using |  | * Delta training for |  |  | 1. Scoop SF75GOLD tools
* Payroll Intfc develop |  |  | apply patches, etc. to |  |  |  | SF75GOLD |  | end users |  |  | 2. Upgrade SFS 7.02 non-People tools data to create SFS 7.52
ment continues in |  |  | get the database ready |  | * 7.5 service pack 2 upgrade script |  | * Test/streamline move to
SFDV of 7.02 |  |  | for user testing |  | documentation is here by Sept. 29 |  | production (SF75GOLD) | [5 empty] | * Final user acceptance testing is done
* Will move all Payroll Intf |  |  | * Campus users are dir- |  | * Run new "Compare" reports | [7 empty] | * Make individual user password changes
development to SFS |  |  | ected to start using |  | * Evaluate Compare reports |  | * Perform final PS |  | * Core Team members |  |  |  | as needed in SFS 7.52
production before the |  |  | SFNEWT for 7.5 testing |  | * Apply 7.02 customizations |  | application trouble- |  | need to be keeping track |  |  |  | * Copy SFS 7.52 to SFDV and SFQA
SFS copy is made |  |  | as of Sept. 17, 2001 |  |  |  | shooting (SF75GOLD) |  | of any tree, query, and |  |  |  | * Move new development from
|  |  | * DoIT staff begins up- |  | UWSA staff performs these items |  | * Adapt & test interfaces |  | security changes during |  |  |  | SF75DV to SFDV as needed
|  |  | grading SFNEWT to |  | * Update security in SF75GOLD |  | (SF75GOLD) |  | this period.
|  |  | service pack 2 on |  | * Perform upgrade task 2 |  | * Resume development
|  |  | Sept. 15, 2001 |  | * Core Team members need to be |  | (Payroll Intfc, etc.) in
[5 empty] | keeping track of any tree, query, and |  | SF75DV
security changes during this period.
| A |  |  | B |  | C |  | D |  | E | F | G |  | H
DETAILS BY SEGMENT
A | Development (by staff at DoIT) referred in this segment is the bolt-on functionality for Payroll Interface, PO form changes, etc. that can be completed by Sept. 28
New development for Payroll Interface will continue in version 7.02 and will be moved to production SFS prior to the date on which a copy of SFS is made to
create the SF75GOLD database.
B | Once the SF75GOLD database is created, no further development will be done in version 7.02.
Development of any new trees or queries needed by SFS units should be completed as much as possible before the version 7.02 freeze occurs.
NOTE: SFNEWT does not have "real" security. Users will be able to see almost all the panels that PeopleSoft has.
C | As soon as the SF75GOLD database is available, staff at DoIT will begin upgrading the PeopleSoft tools to version 7.52. SFS units will not be using
SF75GOLD for testing during this period.
SFS units will continue to use the SFNEWT database for testing during the 2-3 week period when the tools upgrade is being done on SF75GOLD.
All version 7.02 customizations will also be applied to SF75GOLD during this period.
The UW security classes will need to be modified in SF75GOLD to add back all missing panels.
We will need to keep track of (on paper) any changes to security authorizations, trees, queries, etc. created during this period. Those changes will need to be applied to the
SF75GOLD database before it is copied to create SF75DV.
D & E | SF75GOLD will be copied to create SF75DV over the Oct. 20-21 weekend.
Version 7.52 training for SFS units will also be done using the SF75GOLD database.
Once SF75DV is created, it will only be used by DoIT developers for continuing work on projects such as Payroll Interface.
Any setup, security, tree, SQR, bolt-on, etc. changes made in SFS production or SF75DV during this period must also be made in SF75GOLD.
F | A short period of time (one or two days) will be allocated to allow SFS units to get data cleaned up in SFS (e.g. all journals posted, PO's and invoices posted, etc.)
in preparation for the "go live" build process.
G | The start date for the "go live" database build process will be Nov. 21. DoIT staff estimate it may take 4-6 days to complete this process.
Thus, the SFS production system could be down for 3 business days.
H | After the 7.52 production database is created, final user testing will need to be done to verify that all systems are functioning properly. That work will need to be completed
within the 4-6 day window for the "go live" build operations.
Filling in the timeline dates
1 | SFS production will be shut down for the "go live" build as of 7:00 a.m on Wednesday, November 21. UWSA staff will prepare a "go live" checklist.
SFS production on version 7.52 will be implemented as of 7:00 a.m. on Monday, November 26, 2001
SFS units will not be able to run a Pay Cycle process to generate ZBA checks during the period from Nov. 21 through Nov. 26.
SFS units will perform final version 7.52 acceptance testing on Monday, Nov. 26, 2001 to insure the new database is ready for full use.
Full use will resume on Nov. 27, 2001
July 1, 2001
Copy 7.02 SFS to a new 7.52 database SF75GOLD.
Freeze 7.02 development.
2-3 weeks allowed
for this process
Copy upgraded SF75GOLD to create SF75DV.
BU's perform SFS clean-up to get ready for 7.52 go live.
7.52 "go live" build is performed at DoIT.
SFS production system is shut down
7.52 final user acceptance testing is completed in the 7.52 production system
July 10- new 7.51 test database SFNEWT is created
Databases no longer needed are deleted (e.g. SFGOLD, SF751, SFDV