## Sheet1
Catoctin Creek TMDL Implementation Plan Development |  |  |  | Duration | Resources | [6 empty] | Working Groups |  |  |  |  | Calendar
[17 empty] | July |  |  |  |  | August | [5 empty] | September |  |  |  |  | October |  |  |  |  | November |  |  |  |  | December |  |  |  |  | January | [5 empty] | February |  |  |  |  | March | [5 empty] | April |  |  |  |  | May |  |  |  |  | June
[5 empty] | MapTech | DCR Management | LSWCD Management | EHRP Management | DEQ | Rural Economic | Planning | Agriculture | Residential | Environmental | Government | Steering Committee |  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 |  | 29 |  | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 |  | 7 | 14 | 21 | 28 |  | 5 | 12 | 19 | 26 | 2 | 9 | 16 |  | 23 | 30 |  | 6 | 13 | 20 | 27 |  | 5 | 12 |  | 19 | 26 | 2 | 9 | 16 | 23 | 30 |  | 7 | 14 | 21 | 28 |  | 4 | 11 | 18 | 25
[42 empty] | H |  |  |  |  | H | H
Steering Committee |  |  |  | - | [37 empty] | O |  |  |  |  | O | O
| Invitations for Membership | [40 empty] | L |  |  |  |  | L | L
| Establish Committee | [40 empty] | I |  |  |  |  | I | I
| Initial Committee Meeting |  |  | 1 day | [28 empty] | 1st MTG, Sep 29, 2003 | [8 empty] | D |  | 2nd MTG, Dec 3, 2003 |  |  | D | D
| Second Committee Meeting (Working Groups Report on Corrective Action Efforts) |  |  | 1 day | [37 empty] | A |  |  |  |  | A | A | [6 empty] | 3rd MTG, TBD
| Joint Committee and Working Group Meeting (Set Measurable Goals and Implementation Milestones) |  |  | 1 day | [37 empty] | Y |  |  |  |  | Y | Y | [10 empty] | 4th MTG, TBD
| Fourth Committee Meeting |  |  | 1 day
Working Groups |  |  |  | -
Initial Announcement and Call for Membership (Agriculture, Residential, Environmental, Government)
| First Working Group Meetings (Four Separate Meetings, One Each Per Working Group) | [21 empty] | Aug 8, Noon, Press Release to County PIO |  |  |  | Initial Interest Taken | [23 empty] | Ag Jan 14
| Second Working Group Meetings (Four Separate Meetings, One Each Per Working Group) | [24 empty] | Aug 25, Web Page Done and Press Release Run | [8 empty] | Ag Rescheduled, Res Nov 18, Env Nov 19, Govt Nov 18 | [18 empty] | Ag TBD
| Third Working Group Meetings (One Meeting with Environmental and Government Working Groups) | [48 empty] | Res Jan 13, Env TBD, Govt TBD
Public Participation |  |  |  | -
Public Announcement for Kickoff
| Kickoff Meeting (Project Explained, Steering Committee Introduced, Working Groups Finalized) |  |  | 1 day | [18 empty] | Aug 8, Noon, Announcement Info to DEQ |  |  |  | 4 Weeks, Public Notice | [5 empty] | KICKOFF, Sep 30
| Prefinal Meeting (Project Update, Barriers Checked, Potential Solution Providers Identified) |  |  | 1 day | [21 empty] | Aug 25, Notice Published | [35 empty] | PREFINAL Project Review
| Final Meeting (Report Presentation) |  |  | 1 day | [62 empty] | FINAL Report Presentation
| Public Comment Period |  |  | 30 days
30 Day Public Comment Period
Corrective Actions |  |  |  | -
| Assess Needs |  |  | -
|  | Confirm TMDL Assessment Results (Direct and Land-Based Load Modeling Results) |  | Done
|  | Identify BMPs (What's Available, Existing and Potential, Agriculture and Residential) |  | 1 week
| Define Constraints (Define Resources Needed to Achieve) |  |  | -
|  | Staffing Assessment (Ability to Assist, Organizations and Programs) |  | 1 week
|  | Financial Assessment |  | -
|  |  | Census Income and Poverty Analysis (Ability to Pay, Cost-Share Impacts) | 1 week
|  |  | Identify Funding Sources (Programs, Incentives, Nonprofits, Trusts, Foundations, etc.) | 1 week
|  | Technical Assessment (What Works, Agriculture and Residential BMPs) |  | 2 weeks
|  | Business and Social Assessment (Agriculture and Rural Economy, Age, Lease/Own, Rent/Own) |  | 1 week
| Quantify Needs (BMPs and Technical Assistance) |  |  | -
|  | Verify Land Use / Land Cover Changes (Since 2001 Assessment Baseline Year) |  | 2 weeks
|  | Quantify BMPs (How Many in Each Subwatershed, Spatial Analysis) |  | 1 week
|  | Quantify Technical Assistance (How Much Support, Projected from Historic Trends) |  | 1 week
| Staged Approach |  |  | -
|  | Spatial Targeting (Where Best Applied, Ratios, Prioritization, Impact Modeling) |  | 2 weeks
|  | Temporal Targeting (When Best Applied, Seasonal, Impact Modeling) |  | 3 days
|  | Available Funds Comparison (Needs vs. Availability, Scheduling Impacts) |  | 2 days
Measurable Goals |  |  |  | -
| Preparation (Logistics and Strawmen) |  |  | 4 days
Timeline & Milestones |  |  |  | -
| Implementation Milestones (5-10 Years, Estimate Time to Achieve Measurable Goals) |  |  | 2 days
| Identify Monitoring Locations (Existing) and Confirm Monitoring Needs (Needed to Verify Implementation) |  |  | 1 week
| Interim Water Quality Milestones (Modeling, Anticipated Quality Improvements for Implementation Milestones) |  |  | 2 weeks
Cost/Benefit Analysis |  |  |  | -
| Assess Cost (Staged Implementation and Full) |  |  | 4 weeks
| Evaluate Water Quality Benefit (Update Spatial and Temporal Targeting Models, Qualify) |  |  | 2 days
Prepare Report |  |  |  | -
| Prefinal Report Summary and Meeting Logistics |  |  | 1 week
| Final Report for Public Review |  |  | 1 week
| Integrate Public Comments |  |  | 1 week
| Final |  |  | 2 weeks